## Turn SCE-006 #Q7
2021 Wildfire Mitigation Plan
TURN Data Request
Data Request Number: TURN-SCE-006
Date Sent: March 12, 2021
Response Due: March 17, 2021
Please provide an electronic response to the following question. A hard copy response is unnecessary. The response should be provided on a CD sent by mail or as attachments sent by e-mail to the following people:
Katy Morsony
The Utility Reform Network (TURN)
785 Market Street, Suite 1400
San Francisco, CA 94103
kmorsony@turn.org
Stephen Green
The Utility Reform Network (TURN)
785 Market Street, Suite 1400
San Francisco, CA 94103
sgreen@turn.org
Eric Borden
The Utility Reform Network (TURN)
785 Market Street, Suite 1400
San Francisco, CA 94103
eborden@turn.org
Marcel Hawiger
The Utility Reform Network (TURN)
785 Market Street, Suite 1400
San Francisco, CA 94103
marcel@turn.org
For each question, please provide the name of each person who materially contributed to the preparation of the response. If different, please also identify the SCE witness who would be prepared to respond to cross-examination questions regarding the response.
For any questions requesting numerical recorded data, please provide all responses in working Excel spreadsheet format if so available, with cells and formulae functioning.
For any question requesting documents, please interpret the term broadly to include any and all hard copy or electronic documents or records in SCE’s possession.
1. Please explain and provide all supporting calculations for why SCE chose 4,000 miles as the appropriate target for covered conductor installation by 2022.
2. If SCE does not install covered conductor on a given circuit in the HFRA, will there be no other risk mitigation measures in place on that circuit? If the answer is no, please identify other mitigation measures that SCE will deploy on that circuit.
3. Please provide the amount of risk reduction (percent) from the deployment of these 4,000 miles of covered conductor and all other mitigations deployed on these miles. Please provide all supporting workpapers.
4. Please provide the amount of risk reduction (percent) from just the deployment of
the 4,000 miles of covered conductor. Please provide all supporting workpapers.
5. Please identify whether enhanced vegetation management will also be required on
miles where covered conductor is deployed. If the answer is yes, please quantify
the cost of enhanced vegetation management on miles where covered conductor is
deployed. | Table 3-2 | Summary of WMP Expenditures by Category
6. Does the cost of the covered conductor program included in the WMP rely on the | WMP Category | 2020 WMP Planned | 2020 Actual | Difference | 2021 Planned | 2022 Planned | 2020-22 Planned (w/2020 Actual)
same unit costs for installation of covered conductor as the utility used to develop | Risk and Mapping | 0 | 0 | 0 | 0 | 0 | 0
SCE’s 2021 General Rate Case request in A.19-08-013. | Situational Awareness (+ Alt Tech) | 23964 | 21800.3295 | -2163.6705 | 45846.5953 | 42308.3466 | 109955.2715
7. Table 3-2 on pages 30-31 of SCE’s WMP (Grid Design & System Hardening) shows a difference of $379,259 for | Grid Design and System Hardening | 962705 | 583445.8139 | -379259.1861 | 835979.2836 | 1035462.2742 | 2454887.3717
planned versus actual expenditures in 2020. Please provide all reasons for the | Asset Management and Inspections | 59942 | 308822.5192 | 248880.5192 | 352617.5694 | 234710.0681 | 896150.1567
lower actual spend than planned. | Vegetation Management | 137221 | 332579.0832 | 195358.0832 | 353099.374 | 362946.0352 | 1048624.4925
| Grid Operations (PSPS + Op Rel) | 22447 | 36145.5375 | 13698.5375 | 68364.3374 | 62434.0779 | 166943.9528
| Data Governance | 0 | 1796.1108 | 1796.1108 | 16761.183 | 15950.24 | 34507.5338
| Resource Allocation | 78519 | 47767.8285 | -30751.1715 | 7917.2645 | 6086.0525 | 61771.1455
| Emergency Planning | 23472 | 615.6675 | -22856.3325 | 1721.6811 | 1721.6811 | 4059.0298
| Stakeholder Cooperation and Community Engagement | 0 | 3954.725 | 3954.725 | 23364.5321 | 23478.7001 | 50797.9573
| Total | 1308270 | 1336927.6152 | 28657.6152 | 1705671.8205 | 1785097.4758 | 4827696.9115

## WMP Program Reconciliation
2020 WMP ID | 2021 WMP Update ID | WMP Activities in 2020 WMP and 2021 WMP Update | 2020 WMP Categorization | 2021 WMP Update Categorization | 2020 WMP forecast ($ thousands) | 2020 WMP Actuals ($ thousands) | 2020 Forecast vs. Actuals ($ thousands) | 2020 Forecast vs. Actuals Comments | Reconciliation Notes
SH-1 | SH-1 | Covered Conductor | Grid Design and System Hardening | Grid Design and System Hardening | 454368.671 | 546151.289 | 91782.618 | Major Drivers of cost variance: 1) the 2020 WMP forecast did not include Fire Resistant (FR)Poles under SH-1. In 2020, FR poles and costs were included in SH-3. In 2021, SCE included FR poles in SH-1. 2020 FR poles recorded costs were $56.8M, now reflected in SH-1) 2) SCE's initial covered conductor cost estimate (2018) was based on a bottoms-up analysis using its Overhead Conductor Program (OCP) as a basis. This unit cost was used in the 2020 WMP (escalated as appropriate with time). For the 2021 WMP, SCE was able to update estimates using a recorded actual unit cost for covered conductor work. Increases between the two estimates were driven primarily by an ~20% increase in electrical crew contracted rates, due to local market conditions. Additionally, to meet execution requirements, SCE increased contractor utilization in the design and planning phase by 18%. | Remains an activity in 2021 WMP Update
SH-2 | SH-2 | Undergrounding Overhead Conductor | Grid Design and System Hardening | Grid Design and System Hardening | 0 | 961.3883 | 961.3883 | Targeted Undergrounding commences in 2021 and continues to expand into 2022. | Remains an activity in 2021 WMP Update
SH-3 | SH-1 | WCCP Fire Resistant Poles | Grid Design and System Hardening | N/A | 56832.5745 | 0 | -56832.5745 | Existing wood poles are identified for FR upgrades as part of the WCCP where appropriate. FR Pole options include composite pole with a fire resistant sleeve or a wood pole with a fire resistant wrap. This activity is merged into SH-1 as part of the 2021 WMP Update. | Not a standalone activity in 2021 WMP; discussed as a part of SH-1 Covered Conductor
SH-4 | SH-4 | Branch Line Protection Strategy | Grid Design and System Hardening | Grid Design and System Hardening | 16798.587 | 10283.835 | -6514.752 | Current Limiting Fuses underrun was primarily driven by lower construction costs, offset by accelerated 2020 units, originally planned in 2021-22. | Remains an activity in 2021 WMP Update
SH-5 | SH-5 | Installation of System Automation Equipment – RAR/RCS | Grid Design and System Hardening | Grid Design and System Hardening | 8639.9018 | 5866.6214 | -2773.2804 | RAR/RCS's slightly under-ran by 33% primarily due to lower units completed than planned. The reduced scope was a direct result of SCE’s refined strategy to utilize RCSs and PSs in place of RARs where applicable. | Remains an activity in 2021 WMP Update
SH-6 | SH-6 | Circuit Breaker Relay Hardware for FC | Grid Design and System Hardening | Grid Design and System Hardening | 5170.0123 | 9776 | 4605.9877 | Cost increase is primarily due increase in units compared to forecast | Remains an activity in 2021 WMP Update
SH-7 | SH-7 | PSPS-Driven Grid Hardening Work / Circuit Evaluation for PSPS-Driven Grid Hardening Work | Grid Design and System Hardening | Grid Design and System Hardening | 0 |  | 0 |  | Remains an activity in 2021 WMP Update; Renamed Circuit Evaluation for PSPS-Driven Grid Hardening Work
SH-8 | SH-8 | Transmission Open Phase Detection | Grid Design and System Hardening | Grid Design and System Hardening | 0 | 124.6627 | 124.6627 |  | Remains an activity in 2021 WMP Update
SH-9 | N/A | Transmission Overhead Standards (TOH) Review | Grid Design and System Hardening | N/A | 0 | 554.4 | 554.4 |  | Not an activity in 2021 WMP; evaluation complete in 2020
SH-10 | SH-10 | Tree Attachment Remediation | Grid Design and System Hardening | Grid Design and System Hardening | 15182.9007 | 9653.5501 | -5529.3506 | Underrun on tree attachment remediations compared to forecast were largely driven by halt in construction activities in September 2020 due to the Sequoia and Creek fires. | Remains an activity in 2021 WMP Update
SH-11 | SH-11 | Legacy Facilities | Grid Design and System Hardening | Grid Design and System Hardening | 2173.733 | 74.4882 | -2099.2448 | The primary underrun was due to the Creek Fire, which delayed SCE's ability to do assessments and pre-engineering studies for the Big Creek Hydro facilities as originally planned. SCE also determined that avian risk to potential legacy faciity ignited fires was very low and thus did not proceed with added avian wildlife protections for legacy facilities, which resulted in reduced incremental work. | Remains an activity in 2021 WMP Update
SH-12.1 | IN-1.1 | Remediations – Distribution | Grid Design and System Hardening | N/A | 327535.32 | 0 | -327535.32 | 2020 recorded $190,772. Remediations driven by high fire risk informed inspections moved to Asset Management & Inspections. | Not a standalone activity in 2021 WMP; discussed as a part of IN-1.1
SH-12.2 | IN-1.2 | Remediations – Transmission | Grid Design and System Hardening | N/A | 71320.128 | 0 | -71320.128 | 2020 recorded $87,755. Remediations driven by high fire risk informed inspections moved to Asset Management & Inspections. | Not a standalone activity in 2021 WMP; discussed as a part of IN-1.2
SH-12.3 | IN-5 | Remediations – Generation | Grid Design and System Hardening | N/A | 358 | 0 | -358 | 2020 recorded $403. Remediations driven by high fire risk informed inspections moved to Asset Management & Inspections. | Not a standalone activity in 2021 WMP; discussed as a part ofIN-5
PSPS-8 | SH-12 | Microgrid Assessment | Grid Operations and Protocols | Grid Design and System Hardening | 0 | 0 | 0 |  | Remains an activity in 2021 WMP Update; Activity renamed SH-12 and included in Section 7.3.3
N/A | SH-13 | C-Hooks | N/A | Grid Design and System Hardening | 0 | 0 | 0 |  | Not an activity in 2020 WMP; New Activity in 2021 WMP (SH-13)
N/A | SH-14 | Long Span Initiative (LSI) | N/A | Grid Design and System Hardening | 0 | 0 | 0 |  | Not an activity in 2020 WMP; New Activity in 2021 WMP (SH-14)
N/A | SH-15 | Vertical Switches | N/A | Grid Design and System Hardening | 0 | 0 | 0 |  | Not an activity in 2020 WMP; New Activity in 2021 WMP Update (SH-14)
AT-1 | N/A | Alternative Technology Pilots – Meter Alarming for Down Energized Conductor (MADEC) | Grid Design and System Hardening | N/A | 0 | 0 | 0 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.1 | N/A | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter - Ground Fault Neutralizer (GFN) | Grid Design and System Hardening | N/A | 2586.8161 | 0 | -2586.8161 | 2020 recorded of $1,855 for System Hardening Alternative Technology programs were in this category in 2020 but remapped to Situational Awareness to better align with 2021 WMP Guidelines structure in 2021. | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.2 | N/A | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter – Resonant Grounding with Arc Suppression Coil | Grid Design and System Hardening | N/A | 511.2285 | 0 | -511.2285 | 2020 recorded $0 System Hardening Alternative Technology programs were in this category in 2020 but remapped to Situational Awareness to better align with guideline structure in 2021. | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.3 | N/A | Alternative Technology Evaluations – Rapid Earth Fault Current Limiter and Resonant Grounded Transformer | Grid Design and System Hardening | N/A | 408.9828 | 0 | -408.9828 | 2020 recorded $0 System Hardening Alternative Technology programs were in this category in 2020 but remapped to Situational Awareness to better align with guideline structure in 2021. | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.4 | N/A | Alternative Technology Evaluations – Distribution Open Phase Detection | Grid Design and System Hardening | N/A | 511.2285 | 0 | -511.2285 | 2020 recorded $0 System Hardening Alternative Technology programs were in this category in 2020 but remapped to Situational Awareness to better align with guideline structure in 2021. | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-4 | N/A | Alternative Technology Implementation – Vibration Dampers | Grid Design and System Hardening | N/A | 0 | 0 | 0 |  | Not an activity in 2021 WMP; work complete in 2020
AT-8 | N/A | High Impedance Relay Evaluations | Grid Design and System Hardening | N/A | 306.7371 | 0 | -306.7371 | 2020 recorded $0 System Hardening Alternative Technology programs were in this category in 2020 but remapped to Situational Awareness to better align with guideline structure in 2021. | Not an activity in 2021 WMP; discussed in Section 7.1.D
Total |  |  |  |  | 962704.8214 | 583446.2347 | -379258.5867
|  |  |  | Table 3-2 | 962705 | 583445.8139
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jen Medina did we complete all the units we planned + more from future years? Reply: That was a part of a comment I found in S&S #3 slides.