## SCE - Table 12_v2
Utility | SCE | Notes:
Table No. | 12 | Risk-Spend-Efficiency (RSE) is defined as "An estimate of the cost-effectiveness of initiative, calculated by dividing the mitigation risk reduction benefit by the mitigation cost estimate based on the full set of risk reduction benefits estimated from the incurred costs."
Date Modified | 2021-02-05 | CAPEX = Capital expenditure; OPEX = Operating expenditure. In future submissions update planned spend, line miles treated, RSE, etc. with updated projections and actuals. Additional instructions can be found in QR information.
All dollars shown are in nominal, thousands of dollars (000s).
[19 empty] | Planned - (Projected spend for 2020 cycle as reported in 2020 but using 2021 reporting method, which includes HFTD and non-HFTD spend) | [7 empty] | Planned - (Projected spend for 2021 as reported in 2020 but using 2021 reporting method, which includes HFTD and non-HFTD spend) | [7 empty] | Planned - (Projected spend for 2022 as reported in 2020 but using 2021 reporting method, which includes HFTD and non-HFTD spend) | [7 empty] | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected
[19 empty] | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total
Table 12: Mitigation initiative financials | [18 empty] | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used)
Metric type | WMP Table # / Category | WMP Initiative # | Initative activity | WMP Identifier | Primary driver targeted | Secondary driver targeted | Year initiated | Estimated RSE in non-HFTD region | Estimated RSE in HFTD Zone 1 | Estimated RSE in HFTD Tier 2 | Estimated RSE in HFTD Tier 3 | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by this activity, note activity where relevant spend is tracked in or mark "general operations" | Alternative units in which initiative is reported (if not line miles); still required to report line miles | Comments | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022
Other | Risk Assessment & Mapping | 7.3.1.1. | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment | NA | Equipment failure | Other contact with object | 2020 | NA | NA | NA | NA | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA |  |  | Costs included in SA-4 | [26 empty] | 265 | 175 | 265 | 175 | 0 |  | 0 |  | 0 | 315.28 |  | 315.28 | 0 |  | 0 |  | 0 | 175 |  | 175 | 0 |  | 0
Other | Risk Assessment & Mapping | 7.3.1.2. | Climate-driven risk map and modelling based on various relevant weather scenarios | NA | Equipment failure | Other contact with object | 2020 | NA | NA | NA | NA |  |  |  |  | General operations |  | Not started, to be further discussed - Start date TBD
Other | Risk Assessment & Mapping | 7.3.1.3. | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | NA | Equipment failure | Other contact with object | 2020 | NA | NA | NA | NA | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA |  |  | Costs included in SA-4 | [26 empty] | 265 | 175 | 265 | 175 | 0 |  | 0 |  | 0 | 315.28 |  | 315.28 | 0 |  | 0 |  | 0 | 175 |  | 175 | 0 |  | 0
Other | Risk Assessment & Mapping | 7.3.1.4. | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | NA | Equipment failure | Other contact with object | 2020 | NA | NA | NA | NA |  |  |  |  | General operations |  | Not started, to be further discussed - Start date TBD
Other | Risk Assessment & Mapping | 7.3.1.5. | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | NA | Equipment failure | Other contact with object | 2020 | NA | NA | NA | NA | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA |  |  | Costs included in SA-4 | [26 empty] | 265 | 175 | 265 | 175 | 0 |  | 0 |  | 0 | 315.28 |  | 315.28 | 0 |  | 0 |  | 0 | 175 |  | 175 | 0 |  | 0
Other | Situational Awareness & Forecasting | 7.3.2.1. | Advanced weather monitoring and weather stations | SA-1 |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations |  | NA | # of weather station installs | [25 empty] | 7602.9462 | 4308.7145 | 7602.9462 | 4308.7145 | 0 |  | 593 | 593 | 5273.376 | 7359.5193 | 5273.376 | 7359.5193 | 0 |  | 475 | 475 | 5273.375 | 7870.5835 | 5273.375 | 7870.5835 | 0 |  | 475 | 475
Other | Situational Awareness & Forecasting | 7.3.2.2. | Continuous monitoring sensors | SA-9 | Equipment failure | Other contact with object | 2018 | 925.2316 |  | 4456.1205 | 2756.4505 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA; WMPMA | Exceeding compliance with regulations |  | NA | # of devices | [25 empty] | 260.4045 | 215.1821 | 260.4045 | 215.1821 | 0 |  | 0 |  | 9554.4118 | 251.5244 | 9554.4118 | 251.5244 | 0 |  | 150 | 150 | 19608.6804 | 0 | 19608.6804 |  | 0 |  | 300 | 300
Other | Situational Awareness & Forecasting | 7.3.2.3. | Fault indicators for detecting faults on electric lines and equipment | NA |  |  | NA | [5 empty] | NA |  |  | General operations | # of installations (395 are in HFRA) | This activity is not considered by SCE to be a WMP activity and only units have been provided as the dollars are not disaggregated in SCE's accounting system at this level. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [31 empty] | 1566 | [7 empty] | 1566 | [7 empty] | 1566
Other | Situational Awareness & Forecasting | 7.3.2.4.1 | Forecast of a fire risk index, fire potential index, or similar | SA-2 | [11 empty] | Costs included with SA-3
Other | Situational Awareness & Forecasting | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar | SA-5 |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA | Exceeding compliance with regulations |  | NA | # of square miles | [25 empty] | 0 | 192.8959 |  | 192.8959 | 0 |  | 0 |  | 0 | 320 |  | 320 | 0 |  | 6500 | 6500 | 0 | 604.022 |  | 604.022 | 0 |  | 6500 | 6500
Other | Situational Awareness & Forecasting | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar | SA-7 |  |  | 2020 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations |  | NA | [26 empty] | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 1466.63 |  | 1466.63 | 14000 | 14000 | 0 |  | 0 | 1711.064 |  | 1711.064 | 14000 | 14000 | 0
Other | Situational Awareness & Forecasting | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar | SA-8 |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations |  | NA | [26 empty] | 0 | 414.23 |  | 414.23 | 14000 | 14000 | 0 |  | 0 | 891.109 |  | 891.109 | 14000 | 14000 | 0 |  | 0 | 500 |  | 500 | 14000 | 14000 | 0
Other | Situational Awareness & Forecasting | 7.3.2.5. | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | NA |  |  | NA | [5 empty] | NA |  |  | General operations |  | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 25218.052 |  | 14000 | [5 empty] | 24098.7909 |  | 14000 | [5 empty] | 24782.3712 |  | 14000
Other | Situational Awareness & Forecasting | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment | SA-3 |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA; WMPMA | Exceeding compliance with regulations |  | NA | # of HPCCs in 2021 | Not intending to install new HPCCs in 2022 | [24 empty] | 3310.9963 | 1132.6793 | 3311 | 1132.6793 | 0 |  | 0 |  | 6552.4384 | 3726.82 | 6552.4384 | 3726.82 | 0 |  | 2 | 2 | 700 | 3142.318 | 700 | 3142.318 | 0 |  | 0
Other | Situational Awareness & Forecasting | 7.3.2.6.2 | Weather forecasting and estimating impacts on electric lines and equipment | SA-4 |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA | Exceeding compliance with regulations |  | NA | [26 empty] | 0 | 1028.791 |  | 1028.791 | 14000 | 14000 | 0 |  | 0 | 1147.74 |  | 1147.74 | 14000 | 14000 | 0 |  | 0 | 827.788 |  | 827.788 | 14000 | 14000 | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.1. | Capacitor maintenance and replacement program | NA |  |  | NA | [5 empty] | NA | In compliance with regulations | GO 95; GO 165 | General operations | 2020: 112 OH Caps; 10 PM Caps; 23 Removals 2021: 41 OH Caps; 10 PM Caps; 6 Removals 2022: 55 OH Caps; 14 PM Caps; 8 Removals | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [26 empty] | 5274.944 |  |  |  |  | 145 |  |  | 2444.4346 |  |  |  |  | 57 |  |  | 3413.4028 |  |  |  |  | 77
Grid hardening | Grid Design & System Hardening | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault | SH-6 | Equipment failure | Other contact with object | 2018 |  |  | 1957.8119 | 3307.9782 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations | GO 95; GO 165 | NA | # of relays | [25 empty] | 9785.6956 | -9.2988 | 9785.6956 | -9.2988 | 0 |  | 109 | 109 | 12897.8392 | 0 | 12897.8392 |  | 0 |  | 86 | 86 | 8583.1597 | 0 | 8583.1597 |  | 0 |  | 113 | 113
Grid hardening | Grid Design & System Hardening | 7.3.3.3.1 | Covered conductor installation | SH-1 | Other contact with object | Wire-to-wire contact | 2018 |  |  | 3513.6466 | 4191.6824 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations | GO 95, Rule 31.1 | NA | # of miles of covered conductor installs | In 2020, there were 814 WCCP circuit miles and 151 non-WCCP circuit miles installed. | [24 empty] | 546151.289 | 0 | 546151.289 |  | 0 |  | 965 | 965 | 753659.2664 | 0 | 753659.2664 |  | 0 |  | 1400 | 1400 | 883812.5928 | 0 | 883812.5928 |  | 0 |  | 1600 | 1600
Grid hardening | Grid Design & System Hardening | 7.3.3.3.2 | Covered conductor installation | SH-10 | Other contact with object | Wire-to-wire contact | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations | GO 95, Rule 31.1 | NA | # of remediations | 405 tree attachments were remediated in 2020. The majority, 369, of these tree attachments were scoped for future years but were removed as a result of wildfires in the second half of the year. | [24 empty] | 9653.5501 | 0 | 9653.5501 |  | 0 |  | 405 | 405 | 22230.7053 | 0 | 22230.7053 |  | 0 |  | 688.9 | 688.9 | 26090.0335 | 0 | 26090.0335 |  | 0 |  | 787.9 | 787.9
Grid hardening | Grid Design & System Hardening | 7.3.3.4. | Covered conductor maintenance | NA | [9 empty] | In compliance with regulations | GO 95 | General operations
Grid hardening | Grid Design & System Hardening | 7.3.3.5. | Crossarm maintenance, repair, and replacement | NA | [9 empty] | In compliance with regulations | GO 95 | General operations
Grid hardening | Grid Design & System Hardening | 7.3.3.6. | Distribution pole replacement and reinforcement, including with composite poles | NA |  |  | NA | [5 empty] | NA | In compliance with regulations | GO 95 | General operations | # of pole remediations | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [26 empty] | 181874.339 |  |  |  |  | 9511 |  |  | 306564.8402 |  |  |  |  | 15265 |  |  | 219403.2361 |  |  |  |  | 11611
Grid hardening | Grid Design & System Hardening | 7.3.3.7. | Expulsion fuse replacement | SH-4 | Equipment failure | Other contact with object | 2018 |  |  | 1362.5192 | 3303.9847 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations | GO 95 | NA | Location count | [25 empty] | 7022.0357 | 3261.7993 | 7022.0357 | 3261.7993 | 0 |  | 3025 | 3025 | 0 | 1153.706 |  | 1153.706 | 0 |  | 421 | 421 | 0 | 1333.607 |  | 1333.607 | 0 |  | 481 | 481
Grid hardening | Grid Design & System Hardening | 7.3.3.8.1 | Grid topology improvements to mitigate or reduce PSPS events | SH-7 | [7 empty] | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. |  | Exceeding compliance with regulations | GO 95 | NA |  | SCE does not plan to incur incremental costs for this initiative.
Grid hardening | Grid Design & System Hardening | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events | SH-12 |  |  | 2020 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | MGOIR | Exceeding compliance with regulations | GO 95 | NA | [26 empty] | 0 | 0 |  |  | 0 |  | 0 |  | 4000 | 0 | 4000 |  | 9715 | 9715 | 0 |  | 7000 | 0 | 7000 |  | 9715 | 9715 | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.9. | Installation of system automation equipment | SH-5 |  |  | 2018 | [5 empty] | GSRPBA; FHPMA | Exceeding compliance with regulations | GO 95 | NA | # of devices | [25 empty] | 5866.6214 | 0 | 5866.6214 |  | 0 |  | 49 | 49 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.10. | Maintenance, repair, and replacement of connectors, including hotline clamps | NA | [9 empty] | In compliance with regulations | GO 95 | General operations
Grid hardening | Grid Design & System Hardening | 7.3.3.11. | Mitigation of impact on customers and other residents affected during PSPS event | NA | [11 empty] | General operations
Grid hardening | Grid Design & System Hardening | 7.3.3.12. | Other corrective action | SH-14 | Wire-to-wire contact | Equipment failure | 2019 |  |  | 1867.0931 | 1956.5373 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 95 | NA |  | Units to be determined by field assessments being conducted in Q1/Q2 2021. | [24 empty] | 0 | 554.1823 |  | 554.1823 | 9715 | 9715 | 0 |  | 5943.3443 | 2221.4047 | 5943.3443 | 2221.4047 | 9715 | 9715 | 0 |  | 33589.9313 | 14027.2623 | 33589.9313 | 14027.2623 | 9715 | 9715 | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.13. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program | NA |  |  | NA | [5 empty] | NA | In compliance with regulations | GO 95 | General operations | # of pole remediations | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [26 empty] | 97292.42 |  |  |  |  | 3805 |  |  | 209875.4302 |  |  |  |  | 1072 |  |  | 307949.2338 |  |  |  |  | 15135
Grid hardening | Grid Design & System Hardening | 7.3.3.14. | Transformers maintenance and replacement | NA |  |  | NA | [5 empty] | NA | In compliance with regulations | GO 95 | General operations | Includes overhead, padmount and BURD transformers, and associated inspections. | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [26 empty] | 96400 | 3800.42 |  |  |  | 31947 |  |  | 96262.0708 | 5704 |  |  |  | 33408 |  |  | 98187.3065 | 6045.083 |  |  |  | 32335
Grid hardening | Grid Design & System Hardening | 7.3.3.15. | Transmission tower maintenance and replacement | SH-13 | Contamination | Equipment failure | 2020 | 0.005938 |  | 1.1505e-14 | 81.5993 |  | WMPMA | Exceeding compliance with regulations | GO 95 | NA | # of structures | [25 empty] | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 1000 |  | 1000 | 0 |  | 53 | 53 | 0 | 0 |  |  | 0 |  | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.16. | Undergrounding of electric lines and/or equipment | SH-2 | Other contact with object | Wire-to-wire contact | 2019 |  |  | 447.0314 | 347.2735 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 95 | NA |  | In 2020, only design work was completed. | [24 empty] | 961.3883 | 0 | 961.3883 |  | 0 |  | 0 |  | 26350.0583 | 0 | 26350.0583 |  | 6 | 6 | 0 |  | 54347.1445 | 0 | 54347.1445 |  | 11 | 11 | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.17.1 | Updates to grid topology to minimize risk of ignition in HFTDs | SH-15 | Equipment failure |  | 2019 |  |  |  | 12.9104 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 95 | NA | # of replacements | [25 empty] | 0 | 0 |  |  | 0 |  | 0 |  | 852.9594 | 0 | 852.9594 |  | 0 |  | 30 | 30 | 1750.543 | 0 | 1750.543 |  | 0 |  | 60 | 60
Grid hardening | Grid Design & System Hardening | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs | SH-11 |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 95 | NA | [26 empty] | 0 | 73.8882 |  | 73.8882 | 9715 | 9715 | 0 |  | 4450 | 820 | 4450 | 820 | 9715 | 9715 | 0 |  | 3953 | 225 | 3953 | 225 | 9715 | 9715 | 0
Grid hardening | Grid Design & System Hardening | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs | SH-8 |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 95 | NA | Cicuit miles within HFRA | [25 empty] | 0 | 124.6627 |  | 124.6627 | 0 |  | 6 | 6 | 0 | 400 |  | 400 | 0 |  | 10 | 10 | 0 | 750 |  | 750 | 0 |  | 13 | 13
Asset inspection | Asset Management & Inspections | 7.3.4.1. | Detailed inspections of distribution electric lines and equipment | NA |  |  | NA | [6 empty] | In compliance with regulations | GO 165 | General operations | 2020: 56,895 inspections in HFRA; 205,875 inspections in non-HFRA 2021: 27,000 inspections in HFRA; 244,000 inspections in non-HFRA 2022: 27,000 inspections in HFRA; 244,000 inspections in non-HFRA | Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 8960 |  |  |  | 262770 |  |  |  | 4222.9057 |  |  |  | 271000 |  |  |  | 4331.9908 |  |  |  | 271000
Asset inspection | Asset Management & Inspections | 7.3.4.2. | Detailed inspections of transmission electric lines and equipment | NA |  |  | NA | [6 empty] | In compliance with regulations | GO 165 | General operations | # of inspections | Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 3567.333 |  |  |  | 1313 |  |  |  | 7604.269 |  |  |  | 1313 |  |  |  | 7802.2789 |  |  |  | 1313
Asset inspection | Asset Management & Inspections | 7.3.4.3. | Improvement of inspections | IN-8 |  |  | 2021 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations |  | NA | [26 empty] | 28718.5992 | 0 | 28718.5992 |  | 9715 | 9715 | 0 |  | 17422 | 6183 | 17422 | 6183 | 9715 | 9715 | 0 |  | 6600 | 5240.7 | 6600 | 5240.7 | 9715 | 9715 | 0
Asset inspection | Asset Management & Inspections | 7.3.4.4. | Infrared inspections of distribution electric lines and equipment | IN-3 | Equipment failure |  | 2017 |  |  | 156.1043 | 1878.7442 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations | GO 95, Rule 31.2; GO 95, Rule 31.1 | NA | [26 empty] | 0 | 790.7734 |  | 790.7734 | 4416 | 4416 | 0 |  | 0 | 426.5578 |  | 426.5578 | 4425 | 4425 | 0 |  | 0 | 426.5578 |  | 426.5578 | 4425 | 4425 | 0
Asset inspection | Asset Management & Inspections | 7.3.4.5. | Infrared inspections of transmission electric lines and equipment | IN-4 | Equipment failure |  | 2019 |  |  |  | 173.7768 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 95, Rule 31.2; GO 95, Rule 31.1 | NA | [26 empty] | 0 | 383.5504 |  | 383.5504 | 1005 | 1005 | 0 |  | 0 | 208.6865 |  | 208.6865 | 1000 | 1000 | 0 |  | 0 | 215.9556 |  | 215.9556 | 1000 | 1000 | 0
Asset inspection | Asset Management & Inspections | 7.3.4.6. | Intrusive pole inspections | NA |  |  | NA | [6 empty] | In compliance with regulations | GO 95 | General operations |  | Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [35 empty] | 4222.9057 |  | 14000 | [5 empty] | 4331.9908 |  | 14000
Asset inspection | Asset Management & Inspections | 7.3.4.7. | LiDAR inspections of distribution electric lines and equipment | NA | [11 empty] | General operations
Asset inspection | Asset Management & Inspections | 7.3.4.8. | LiDAR inspections of transmission electric lines and equipment | NA | [11 empty] | General operations
Asset inspection | Asset Management & Inspections | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | IN-1.1 | Equipment failure |  | 2018 |  |  | 2636.0793 | 2776.9884 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA; GSRPBA; WMPMA | Exceeding compliance with regulations | GO 95, Rule 31.2; GO 95, Rule 31.1; GO 165 | NA | 2020: # of Ground Inspections: 199,050; # of Aerial Inspections: 168,017; # of Remediations: 26,915 2021: # of Ground Inspections: 198,000; # of Aerial Inspections: 198,000; # of Remediations: 24,584 2022: # of Ground Inspections: 171,000; # of Aerial Inspections: 198,468; # of Remediations: 14,354 | [25 empty] | 85218.9688 | 105553.2628 | 85218.9688 | 105553.2628 | 0 |  | 393982 | 393982 | 147937.768 | 104185.2191 | 147937.768 | 104185.2191 | 0 |  | 420584 | 420584 | 88697.9096 | 91606.0157 | 88697.9096 | 91606.0157 | 0 |  | 383822.4144 | 383822.4144
Asset inspection | Asset Management & Inspections | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations | IN-5 |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA; WMPMA | Exceeding compliance with regulations | GO 95 Rule 31.2; GO 165 | NA | [26 empty] | 0 | 402.545 |  | 402.545 | 0 |  | 268 | 268 | 0 | 315 |  | 315 | 0 |  | 181 | 181 | 0 | 0 |  |  | 0 |  | 102 | 102
Asset inspection | Asset Management & Inspections | 7.3.4.10. | Other discretionary inspection of transmission electric lines and | IN-1.2 | Equipment failure |  | 2018 |  |  | 540.3791 | 763.5109 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA; GSRPBA; WMPMA | Exceeding compliance with regulations | GO 95, Rule 31.2; GO 95, Rule 31.1; GO 165 | NA | 2020: # of Ground Inspections: 35,562; # of Aerial Inspections: 31,381; # of Remediations: 6,486 2021: # of Ground Inspections: 22,800; # of Aerial Inspections: 22,800; # of Remediations: 5,902 2022: # of Ground Inspections: 14,902; # of Aerial Inspections: 22,834; # of Remediations: 3,605 | [25 empty] | 35934.3099 | 51820.5097 | 35934.3099 | 51820.5097 | 0 |  | 73429 | 73429 | 50758.4 | 25180.938 | 50758.4 | 25180.938 | 0 |  | 51502 | 51502 | 18098.1159 | 23824.8134 | 18098.1159 | 23824.8134 | 0 |  | 41341 | 41341
Asset inspection | Asset Management & Inspections | 7.3.4.11. | Patrol inspections of distribution electric lines and equipment | NA |  |  | NA | [8 empty] | General operations |  | Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 25218.052 |  | 9715 | [5 empty] | 24098.7909 |  | 9715 | [5 empty] | 24782.3712 |  | 9715
Asset inspection | Asset Management & Inspections | 7.3.4.12. | Patrol inspections of transmission electric lines and equipment | NA | [11 empty] | General operations
Asset inspection | Asset Management & Inspections | 7.3.4.13. | Pole loading assessment program to determine safety factor | NA |  |  | NA | [6 empty] | In compliance with regulations | GO 95 | General operations | # of assessments | Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 14477.0821 |  |  |  | 121268 |  |  |  | 3209.9608 |  |  |  | 14400
Asset inspection | Asset Management & Inspections | 7.3.4.14. | Quality assurance / quality control of inspections | NA | [11 empty] | General operations
Asset inspection | Asset Management & Inspections | 7.3.4.15. | Substation inspections | NA |  |  | NA | [5 empty] | NA | In compliance with regulations | GO 174 | General operations | # of inspections | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 2671.657 |  |  |  | 4209 |  |  |  | 2854.962 |  |  |  | 4426 |  |  |  | 2986.492 |  |  |  | 5644
Vegetation management project | Vegetation Management & Inspections | 7.3.5.1. | Additional efforts to manage community and environmental impacts | NA | [11 empty] | General operations
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.2. | Detailed inspections of vegetation around distribution electric lines and equipment | NA |  |  | NA | [5 empty] | NA | In compliance with regulations | GO 95; GO 174 | General operations | # of ground inspection and aerial inspections | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 25755.7217 |  |  |  | 1760000 |  |  |  | 15020.37 |  |  |  | 1149000 |  |  |  | 15470.984 |  |  |  | 1149000
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.3. | Detailed inspections of vegetation around transmission electric lines and equipment | NA |  |  | NA | [5 empty] | NA | In compliance with regulations | GO 95; GO 174 | General operations | # of inspections | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA. Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [27 empty] | 1773.7554 |  |  |  | 321000 |  |  |  | 2752.7 |  |  |  | 234000 |  |  |  | 2835.281 |  |  |  | 234000
Vegetation management project | Vegetation Management & Inspections | 7.3.5.4. | Emergency response vegetation management due to red flag warning or other urgent conditions | NA | [11 empty] | General operations
Vegetation management project | Vegetation Management & Inspections | 7.3.5.5.1 | Fuel management and reduction of “slash” from vegetation management activities | VM-2 | Equipment failure |  | 2019 |  |  | 1426.4149 | 1881.0953 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | PRC 4292 | NA | # of poles brushed | [25 empty] | 0 | 7459.0831 |  | 7459.0831 | 0 |  | 234000 | 234000 | 0 | 8271.6173 |  | 8271.6173 | 0 |  | 229190 | 229190 | 0 | 6787.1583 |  | 6787.1583 | 0 |  | 229190 | 229190
Vegetation management project | Vegetation Management & Inspections | 7.3.5.5.2 | Fuel management and reduction of “slash” from vegetation management activities | VM-3 |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FHPMA | Exceeding compliance with regulations | PRC 4291; PRC 4293 | NA | [26 empty] | 0 | 0 |  |  | 0 |  | 61 | 61 | 0 | 900 |  | 900 | 0 |  | 46 | 46 | 0 | 1089 |  | 1089 | 0 |  | 49 | 49
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.6. | Improvement of inspections | NA | [11 empty] | General operations
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.7. | LiDAR inspections of vegetation around distribution electric lines and equipment | NA | [11 empty] | General operations
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.8. | LiDAR inspections of vegetation around transmission electric lines and equipment | NA |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | FAC-003-4 | NA | [26 empty] | 0 | 4092.2315 |  | 4092.2315 | 1227 | 1227 | 0 |  | 0 | 1485.4906 |  | 1485.4906 | 1227 | 1227 | 0 |  | 0 | 1502.4868 |  | 1502.4868 | 1227 | 1227 | 0
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.9. | Other discretionary inspections of vegetation around distribution electric lines and equipment | NA | [11 empty] | General operations
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.10. | Other discretionary inspections of vegetation around transmission electric lines and equipment | NA | [11 empty] | General operations
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.11. | Patrol inspections of vegetation around distribution electric lines and equipment | NA | [8 empty] | NA |  |  | Costs included in WMP Initiative 7.3.5.20. |  | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA.
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.12. | Patrol inspections of vegetation around transmission electric lines and equipment | NA | [8 empty] | NA |  |  | Costs included in WMP Initiative 7.3.5.20. |  | This activity is not considered by SCE to be a WMP activity and dollars/units represent SCE's full service area, not just its HFRA.
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.13. | Quality assurance / quality control of vegetation inspections | VM-5 |  |  | 2019 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 95; PRC 4293; FAC-003-4 | NA | [26 empty] | 0 | 3966.0336 |  | 3966.0336 | 14000 | 14000 | 0 |  | 0 | 5546.7819 |  | 5546.7819 | 14000 | 14000 | 0 |  | 0 | 6158.9773 |  | 6158.9773 | 14000 | 14000 | 0
Vegetation management project | Vegetation Management & Inspections | 7.3.5.14. | Recruiting and training of vegetation management personnel | NA | [11 empty] | General operations
Vegetation management project | Vegetation Management & Inspections | 7.3.5.15. | Remediation of at-risk species | NA | [11 empty] | General operations
Vegetation management project | Vegetation Management & Inspections | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment | VM-1 | Contact with vegetation |  | 2018 |  |  | 1404.6941 | 1602.1656 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations | GO 95 Rule 35; PRC 4293 | NA | # of tree assessments | [25 empty] | 0 | 46684.7626 |  | 46684.7626 | 0 |  | 99523 | 99523 | 0 | 80722.0319 |  | 80722.0319 | 0 |  | 200000 | 200000 | 0 | 89161.7805 |  | 89161.7805 | 0 |  | 200000 | 200000
Vegetation management project | Vegetation Management & Inspections | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment | VM-4 | Contact with vegetation |  |  |  |  | 2284.1583 | 2413.127 |  |  |  |  | Costs included in WMP Initiative 7.3.5.20
Vegetation inspection | Vegetation Management & Inspections | 7.3.5.17. | Substation inspection | NA | [11 empty] | General operations
Vegetation management project | Vegetation Management & Inspections | 7.3.5.18. | Substation vegetation management | NA | [11 empty] | General operations
Vegetation management project | Vegetation Management & Inspections | 7.3.5.19. | Vegetation inventory system | VM-6 |  |  | 2021 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA; GSRPBA | Exceeding compliance with regulations |  | NA | [26 empty] | 16127.8644 | 1055.6305 | 16127.8644 | 1055.6305 | 14000 | 14000 | 0 |  | 9940 | 4152.1774 | 9940 | 4152.1774 | 14000 | 14000 | 0 |  | 4475 | 4690.5012 | 4475 | 4690.5012 | 14000 | 14000 | 0
Vegetation management project | Vegetation Management & Inspections | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment | NA | Contact with vegetation |  | NA |  |  | 3217.8792 | 3591.7725 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FHPMA | Exceeding compliance with regulations | GO 95; PRC 4293; FAC-003-4 | NA |  | Year initiated noted as "NA" as initiative started pre-GSRP/WMP. | [24 empty] | 0 | 253193.4774 |  | 253193.4774 | 14000 | 14000 | 0 |  | 0 | 242081.2749 |  | 242081.2749 | 14000 | 14000 | 0 |  | 0 | 249081.131 |  | 249081.131 | 14000 | 14000 | 0
Other | Grid Operations & Operating Protocols | 7.3.6.1. | Automatic recloser operations | NA | [11 empty] | General operations
Other | Grid Operations & Operating Protocols | 7.3.6.2. | Crew-accompanying ignition prevention and suppression resources and services | NA | [11 empty] | General operations
Other | Grid Operations & Operating Protocols | 7.3.6.3. | Personnel work procedures and training in conditions of elevated fire risk | NA | [11 empty] | General operations
Other | Grid Operations & Operating Protocols | 7.3.6.4. | Protocols for PSPS re-energization | NA | [11 empty] | General operations
Other | Grid Operations & Operating Protocols | 7.3.6.5. | PSPS events and mitigation of PSPS impacts | PSPS-2 |  |  | 2018 |  |  | 107.5247 | 188.1622 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA; GSRPBA; WMPMA | Exceeding compliance with regulations | SB 167 | NA |  | This is the RSE for Community Resource Centers/Community Crew Vehicles. An RSE was calculated for Critical Care Backup Battery which is 12 and 22 for Tier 2 and Tier 3 respectively | [24 empty] | 6843.2439 | 23977.0414 | 6843.2439 | 23977.0414 | 14000 | 14000 | 0 |  | 7247.3697 | 48525.9686 | 7247.3697 | 48525.9686 | 14000 | 14000 | 0 |  | 1250 | 48378.2279 | 1250 | 48378.2279 | 14000 | 14000 | 0
Other | Grid Operations & Operating Protocols | 7.3.6.6. | Stationed and on-call ignition prevention and suppression resources and services | NA | [11 empty] | General operations
Other | Data Governance | 7.3.7.1. | Centralized repository for data | DG-1 |  |  | 2021 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations |  | NA | [26 empty] | 1796.1108 | 0 | 1796.1108 |  | 14000 | 14000 | 0 |  | 15709.183 | 1052 | 15709.183 | 1052 | 14000 | 14000 | 0 |  | 13698.24 | 2252 | 13698.24 | 2252 | 14000 | 14000 | 0
Other | Data Governance | 7.3.7.2. | Collaborative research on utility ignition and/or wildfire | NA | [11 empty] | General operations
Other | Data Governance | 7.3.7.3. | Documentation and disclosure of wildfire-related data and algorithms | NA | [11 empty] | General operations
Other | Data Governance | 7.3.7.4. | Tracking and analysis of near miss data | NA | [11 empty] | General operations
Other | Resource Allocation Methodology | 7.3.8.1. | Allocation methodology development and application | NA |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA; WMPMA | Exceeding compliance with regulations |  | NA | [26 empty] | 0 | 47767.8285 |  | 47767.8285 | 14000 | 14000 | 0 |  | 0 | 7917.2645 |  | 7917.2645 | 14000 | 14000 | 0 |  | 0 | 6086.0525 |  | 6086.0525 | 14000 | 14000 | 0
Other | Resource Allocation Methodology | 7.3.8.2. | Risk reduction scenario development and analysis | NA | [11 empty] | General operations
Other | Resource Allocation Methodology | 7.3.8.3. | Risk spend efficiency analysis | NA | [11 empty] | General operations
Other | Emergency Planning & Preparedness | 7.3.9.1. | Adequate and trained workforce for service restoration | DEP-2 |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | GO 166 | NA | [26 empty] | 0 | 615.6675 |  | 615.6675 | 14000 | 14000 | 0 |  | 0 | 2544.9991 |  | 2544.9991 | 14000 | 14000 | 0 |  | 0 | 1956.9148 |  | 1956.9148 | 14000 | 14000 | 0
Other | Emergency Planning & Preparedness | 7.3.9.2. | Community outreach, public awareness, and communications efforts | NA | [11 empty] | General operations
Other | Emergency Planning & Preparedness | 7.3.9.3 | Customer support in emergencies | NA | [11 empty] | General operations
Other | Emergency Planning & Preparedness | 7.3.9.4. | Disaster and emergency preparedness plan | NA | [11 empty] | General operations
Other | Emergency Planning & Preparedness | 7.3.9.5. | Preparedness and planning for service restoration | NA |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations |  | NA | [26 empty] | 0 | 5325.2522 |  | 5325.2522 | 14000 | 14000 | 0 |  | 200 | 11567.6811 | 200 | 11567.6811 | 14000 | 14000 | 0 |  | 600 | 11970.6163 | 600 | 11970.6163 | 14000 | 14000 | 0
Other | Emergency Planning & Preparedness | 7.3.9.6. | Protocols in place to learn from wildfire events | NA | [11 empty] | General operations
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1.1 | Community engagement | DEP-1.2 |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA | Exceeding compliance with regulations | R-1812005 | NA | # of meetings | [25 empty] | 0 | 141.9413 |  | 141.9413 | 0 |  | 9 | 9 | 0 | 109.9585 |  | 109.9585 | 0 |  | 18 | 18 | 0 | 109.9585 |  | 109.9585 | 0 |  | 18 | 18
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1.3 | Community engagement | DEP-1.3 |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA; GSRPBA | Exceeding compliance with regulations | R-1812005 | NA | [26 empty] | 0 | 1654.7838 |  | 1654.7838 | 14000 | 14000 | 0 |  | 0 | 3820.5736 |  | 3820.5736 | 14000 | 14000 | 0 |  | 0 | 3903.7416 |  | 3903.7416 | 14000 | 14000 | 0
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1.4 | Community engagement | DEP-4 |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | FRMMA | Exceeding compliance with regulations |  | NA | # of surveys | [25 empty] | 0 | 0 |  |  | 0 |  | 5 | 5 | 0 | 1434 |  | 1434 | 0 |  | 4 | 4 | 0 | 1465 |  | 1465 | 0 |  | 3 | 3
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside CA | NA | [11 empty] | General operations
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.3 | Cooperation with suppression agencies | DEP-5 |  |  | 2020 |  |  | 1961.6509 | 3306.4653 | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | WMPMA | Exceeding compliance with regulations | PRC 4292; PRC 4293 | NA | # of aerial suppression resources | [25 empty] | 0 | 2158 |  | 2158 | 0 |  | 1 | 1 | 0 | 18000 |  | 18000 | 0 |  | 5 | 5 | 0 | 18000 |  | 18000 | 0 |  | 5 | 5
Other | Stakeholder Cooperation & Community Engagement | 7.3.10.4 | Forest service and fuel reduction cooperation and joint roadmap | NA | [11 empty] | General operations
Other |  | 7.1.D | Alternative Technologies | NA |  |  | 2018 |  |  |  |  | This activity was not included in SCE's 2018 GRC, but is included in its pending 2021 GRC. | GSRPBA; WMPMA | Exceeding compliance with regulations |  | NA |  | SCE has included costs related to alternative technology projects described in Section 7.1.D. | [24 empty] | 1854.5692 | 158.9205 | 1854.5692 | 158.9205 | 14000 | 14000 | 0 |  | 8357.1864 | 0 | 8357.1864 |  | 14000 | 14000 | 0 |  | 1545.5157 | 0 | 1545.5157 |  | 14000 | 14000 | 0