## Summary
NOTE: SCE HAS CATEGORIZED THE ACTIVITIES THAT ARE UNDERTAKEN TO REDUCE WILDFIRE RISK AS WMP ACTIVITIES. PROGRAMS THAT WERE INCLUDED IN WMP REQUIREMENTS, BUT WHICH ARE NOT PRIMARILY DRIVEN BY WILDFIRE MITIFATION ARE CATEGORIED AS NON-WMP PROGRAMS.
To get SCE WMP Program spend only: For 2020 WMP, go to "DATA_Tables 21-30 Rev2," filter column F to show only “2020-2022 Plan Total” and filter column V to show only “WMP Program.” For 2021, go to Table 12, filter column O to remove "NA & (Blanks)."
| Region of SCE territory | Total cycle spend reported in 2020 WMP ($B) | Total cycle spend reported in 2021 WMP ($B) | % change from 2020 reported to 2021 | Notes
SCE WMP activities and non-WMP programs | Territory-wide | 5.9453 | 6.7512 | 13.56% | WSD's estimate of $6.431B is incorrect. Please see correct amount provided which is sum of (1) what was included for SCE WMP activities in rows titled "2020-2022 plan total" in column C of tables 21-30 from the 2020 WMP which are the same for HFRA and territory-wide, and (2) the forecasts for the SCE non-WMP programs at the time of SCE's 2020 WMP submittal, which are territory wide. The costs included for SCE non-WMP programs in tables 21-30 in the 2020 WMP were estimates for HFRA only. Please see Tab "WSD Request" for the breakdown by category
SCE WMP activities and non-WMP programs | HFTD-only | 4.4902 | N/A | N/A | SCE did not split non-WMP program costs into HFRA and non-HFRA in 2021. 2020 costs however include non-WMP programs as SCE had estimated the HFRA portion of these costs in the 2020 WMP
SCE WMP activities | HFTD-only | 3.8233 | 4.8277 | 26.27% | Please see "WMP Program Reconciliation" for the breakdown by WMP Activity.
| Region of SCE territory | Grid hardening cycle spend reported in 2020 WMP ($B) | Grid hardening cycle spend reported in 2021 WMP ($B) | % change from 2020 reported to 2021
SCE WMP activities and non-WMP programs | Territory-wide | 4.5991 | 4.0954 | -10.95% | WSD's estimate of $4.803B is incorrect. Please see correct amount provided which is sum of (1) what was included for SCE WMP activities in rows titled "2020-2022 plan total" in column C of tables 23 from the 2020 WMP which are th esame for HFRA and territory-wide, and (2) the forecasts for the SCE non-WMP programs at the time of SCE's 2020 WMP submittal, which are territory wide. The costs included for SCE non-WMP programs in tables 23 in the 2020 WMP were estimates for HFRA only. Please see Tab "Grid Hardening Reconciliation" for the difference in WMP-activities.
SCE WMP activities and non-WMP programs | HFTD-only | 3.1623 | N/A | N/A | SCE did not split non-WMP program costs into HFRA and non-HFRA in 2021. 2020 costs however include non-WMP programs as SCE had estimated the HFRA portion of these costs in the 2020 WMP
SCE WMP activities | HFTD-only | 2.9137 | 2.4549 | -15.75% | See Tab "Grid Hardening Reconciliation"

## WMP Forecast Comparison
2020-2022 WMP Forecast
Table # | WSD Category | WMP/Non-WMP Activity or Programs | HFRA/Non-HFRA | 2020 WMP Submittal (Rev02) | 2021 WMP Submittal | Variance | Variance Explanation
21 | Risk Assessment & Mapping | WMP Activities | HFRA
|  | Non-WMP Programs | HFRA
Combined
|  | SUBTOTAL |  | 0 | 0
22 | Situational Awareness & Forecasting | WMP Activities | HFRA | 83461.9858 | 109955.2715 | 26493.2857 | Increase in weather stations, fire science and modeling activities, and distribution fault anticipation as well as re-mapping certain Alternative Technology programs to Situational Awareness & Forecasting.
|  | Non-WMP Programs | HFRA
|  |  | Combined | 6694.794 | 74099.2141
|  | SUBTOTAL |  | 90156.7798 | 184054.4856
23 | Grid Design & System Hardening | WMP Activities | HFRA | 2913668.4426 | 2454887.3717 | -458781.0709 | Remediations driven by high fire risk informed inspections moved to Asset Management & Inspections; System Hardening Alternative Technology programs were in this category in 2020 but removed to better align with guideline structure in 2021.
|  | Non-WMP Programs | HFRA | 248669.9769
|  |  | Combined |  | 1640491.161
|  | SUBTOTAL |  | 3162338.4195 | 4095378.5326
24 | Asset Management & Inspections | WMP Activities | HFRA | 154551.9273 | 896150.1567 | 741598.2295 | Remediations driven by high fire risk informed inspections represented here in 2021 to better align to guideline structure in 2021 (versus Grid Design & System Hardening in 2020). Increase in the number of inspections and the subsequent number and cost of remediations as well as moving inspection-related technology project costs from Resource Allocation Methodology.
|  | Non-WMP Programs | HFRA | 77853.4029
|  |  | Combined |  | 145343.0419
|  | SUBTOTAL |  | 232405.3302 | 1041493.1987
25 | Vegetation Management & Inspections | WMP Activities | HFRA | 407366.9652 | 1048624.4925 | 641257.5272
|  | Non-WMP Programs | HFRA | 161733.8
|  |  | Combined | 14000 | 63608.8121
|  | SUBTOTAL |  | 583100.7652 | 1112233.3046
26 | Grid Operations & Operating Protocols | WMP Activities | HFRA | 58595.7937 | 136221.8516 | 77626.0579 | Driven by the addition of new customer care programs and inclusion of PSPS line patrols in 2021 (was in Emergency Planning & Preparedness in 2020).
|  | Non-WMP Programs | HFRA | 139840
Combined
|  | SUBTOTAL |  | 198435.7937 | 136221.8516
27 | Data Governance | WMP Activities | HFRA |  | 34507.5338 |  | Inclusion of central data repository.
|  | Non-WMP Programs | HFRA | 38791.243
Combined
|  | SUBTOTAL |  | 38791.243 | 34507.5338
28 | Resource Allocation Methodology | WMP Activities | HFRA | 133328.914 | 61771.1455 | -71557.7685 | Reallocated technology support to specific programs
|  | Non-WMP Programs | HFRA
Combined
|  | SUBTOTAL |  | 133328.914 | 61771.1455
29 | Emergency Planning & Preparedness | WMP Activities | HFRA | 72288.8922 | 34781.131 | -37507.7612 | Wildfire cost to patrol lines differs from Table 3-2 because it was placed in Grid Operations & Operating Protocols in Table 3-2.
|  | Non-WMP Programs | HFRA
Combined
|  | SUBTOTAL |  | 72288.8922 | 34781.131
30 | Stakeholder Cooperation & Community Engagement | WMP Activities | HFRA |  | 50797.9573 |  | Added aerial suppression and moved external outreach items from Emergency Planning & Preparedness.
|  | Non-WMP Programs | HFRA
Combined
|  | SUBTOTAL |  | 0 | 50797.9573
| TOTAL |  |  | 4510846.1376 | 6751239.1406
|  |  |  | 2021 WMP (WMP Activities) Total | 4827696.9115
|  |  |  | 2021 WMP (WMP Activities and non-WMP Programs) Total | 6751239.1406

## WMP Program Reconciliation
2020 WMP ID | 2021 WMP Update ID | WMP Activities in 2020 WMP and 2021 WMP Update | 2020 WMP Categorization | 2021 WMP Update Categorization | 2020 WMP forecast for 2021-2022 costs ($ thousands) | 2021 WMP update forecast for 2021-2022 costs ($ thousands) | Notes
RA-1 | N/A | Expansion of Risk Analysis | Risk Assessment and Mapping | N/A |  |  | Not an activity in 2021 WMP; implementation complete in 2020
SA-1 | SA-1 | Weather Stations | Situational Awareness | Situational Awareness | 18399.595 | 37688.5145 | Remains an activity in 2021 WMP Update
SA-2 | SA-2 | Fire Potential Index (FPI) Phase II / Fire Potential Index (FPI) | Situational Awareness | Situational Awareness | 0 |  | Remains an activity in 2021 WMP Update; Renamed "Fire Potential Index (FPI)"
SA-3 | SA-3 | HPCC Weather Modeling System / Weather and Fuels Modeling System | Situational Awareness | Situational Awareness | 7191.921 | 20935.252 | Remains an activity in 2021 WMP Update; Renamed "Weather and Fuels Modeling System"
SA-4 | SA-4 | Asset Reliability & Risk Analytics Capability / Fire Spread Modeling | Situational Awareness | Situational Awareness | 6692.174 | 3425.159 | Remains an activity in 2021 WMP Update; Renamed "Fire Spread Modeling"
SA-5 | SA-5 | Fuel Sampling Program | Situational Awareness | Situational Awareness | 1936.224 | 1116.9179 | Remains an activity in 2021 WMP Update
SA-6 | SA-4 | Surface and Canopy Fuels Mapping | Situational Awareness | N/A | 1803.015 |  | Not a standalone activity in 2021 WMP; discussed as a part of SA-4
SA-7 | SA-7 | Remote Sensing / Satellite Fuel Moisture | Situational Awareness | Situational Awareness | 3361.931 | 3177.694 | Remains an activity in 2021 WMP Update
SA-8 | SA-8 | Fire Science Enhancements | Situational Awareness | Situational Awareness | 4701.348 | 1805.339 | Remains an activity in 2021 WMP Update
AT-7 | N/A | Early Fault Detection (EFD) Evaluation | Situational Awareness | N/A | 3098.811 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
SH-1 | SH-1 | Covered Conductor | Grid Design and System Hardening | Grid Design and System Hardening | 1882536.2084 | 2183623.1483 | Remains an activity in 2021 WMP Update
SH-2 | SH-2 | Undergrounding Overhead Conductor | Grid Design and System Hardening | Grid Design and System Hardening | 64964.7496 | 81658.5911 | Remains an activity in 2021 WMP Update
SH-3 | SH-1 | WCCP Fire Resistant Poles | Grid Design and System Hardening | N/A | 194485.5577 |  | Not a standalone activity in 2021 WMP; discussed as a part of SH-1 Covered Conductor
SH-4 | SH-4 | Branch Line Protection Strategy | Grid Design and System Hardening | Grid Design and System Hardening | 19285.9 | 12771.148 | Remains an activity in 2021 WMP Update
SH-5 | SH-5 | Installation of System Automation Equipment – RAR/RCS | Grid Design and System Hardening | Grid Design and System Hardening | 8639.9018 | 5866.6214 | Remains an activity in 2021 WMP Update
SH-6 | SH-6 | Circuit Breaker Relay Hardware for FC | Grid Design and System Hardening | Grid Design and System Hardening | 26754.2531 | 31257.3957 | Remains an activity in 2021 WMP Update
SH-7 | SH-7 | PSPS-Driven Grid Hardening Work / Circuit Evaluation for PSPS-Driven Grid Hardening Work | Grid Design and System Hardening | Grid Design and System Hardening | 0 |  | Remains an activity in 2021 WMP Update; Renamed Circuit Evaluation for PSPS-Driven Grid Hardening Work
SH-8 | SH-8 | Transmission Open Phase Detection | Grid Design and System Hardening | Grid Design and System Hardening | 864.96 | 1274.6627 | Remains an activity in 2021 WMP Update
SH-9 | N/A | Transmission Overhead Standards (TOH) Review | Grid Design and System Hardening | N/A | 0 | 0 | Not an activity in 2021 WMP; evaluation complete in 2020
AT-1 | N/A | Alternative Technology Pilots – Meter Alarming for Down Energized Conductor (MADEC) | Grid Design and System Hardening | N/A | 0 | 0 | Not an activity in 2021 WMP; discussed in Section 7.1.D
SH-10 | SH-10 | Tree Attachment Remediation | Grid Design and System Hardening | Grid Design and System Hardening | 63992.3731 | 57974.2889 | Remains an activity in 2021 WMP Update
SH-11 | SH-11 | Legacy Facilities | Grid Design and System Hardening | Grid Design and System Hardening | 11263.51 | 9521.8882 | Remains an activity in 2021 WMP Update
SH-12.1 | IN-1.1 | Remediations – Distribution | Grid Design and System Hardening | N/A | 537596.484 |  | Not a standalone activity in 2021 WMP; discussed as a part of IN-1.1
SH-12.2 | IN-1.2 | Remediations – Transmission | Grid Design and System Hardening | N/A | 93980.237 |  | Not a standalone activity in 2021 WMP; discussed as a part ofIN-1.2
SH-12.3 | IN-5 | Remediations – Generation | Grid Design and System Hardening | N/A | 400 |  | Not a standalone activity in 2021 WMP; discussed as a part ofIN-5
IN-1.1 | IN-1.1 | Distribution High Fire Risk Informed Inspections in HFRA | Asset Management and Inspections | Asset Management and Inspections | 7890.7938 | 623199.1441 | Remains an activity in 2021 WMP Update
IN-1.2 | IN-1.2 | Transmission High Fire Risk Informed Inspections in HFRA | Asset Management and Inspections | Asset Management and Inspections | 3401.2211 | 205617.0869 | Remains an activity in 2021 WMP Update
IN-2 | N/A | Quality Oversight / Quality Control | Asset Management and Inspections | N/A | 0 |  | Not an activity in 2021 WMP; operationalized
IN-3 | IN-3 | Infrared Inspection of energized overhead distribution facilities and equipment | Asset Management and Inspections | Asset Management and Inspections | 1216.7561 | 1643.889 | Remains an activity in 2021 WMP Update
IN-4 | IN-4 | Infrared Inspection, Corona Scanning, and HD imagery of energized overhead Transmission facilities and equipment | Asset Management and Inspections | Asset Management and Inspections | 10601.2319 | 808.1925 | Remains an activity in 2021 WMP Update
IN-5 | IN-5 | Generation High Fire Risk Informed Inspections in HFRA | Asset Management and Inspections | Asset Management and Inspections | 320.1216 | 717.545 | Remains an activity in 2021 WMP Update
IN-6.1 | IN-1.1 | Aerial Inspections – Distribution | Asset Management and Inspections | N/A | 92745.3238 |  | Not a standalone activity in 2021 WMP; discussed as a part of IN-1.1
IN-6.2 | IN-1.2 | Aerial Inspections – Transmission | Asset Management and Inspections | N/A | 35912.0836 |  | Not a standalone activity in 2021 WMP; discussed as a part of IN-1.2
IN-7 | N/A | Failure Modes and Effects Analysis (FMEA) | Asset Management and Inspections | N/A | 0 | 0 | Not an activity in 2021 WMP; evaluation complete in 2020
VM-1 | VM-1 | Hazard Tree Management Program | Vegetation Management | Vegetation Management | 185608.4163 | 216568.575 | Remains an activity in 2021 WMP Update
VM-2 | VM-2 | Expanded Pole Brushing | Vegetation Management | Vegetation Management | 12621.1826 | 22517.8587 | Remains an activity in 2021 WMP Update
VM-3 | VM-3 | Expanded Clearances for Legacy Facilities | Vegetation Management | Vegetation Management | 3362.1568 | 1989 | Remains an activity in 2021 WMP Update
VM-4 | VM-4 | Drought Relief Initiative / Dead and Dying Tree Removal | Vegetation Management | Vegetation Management | 0 |  | Remains an activity in 2021 WMP Update; renamed "Dead and Dying Tree Removal"
VM-5 | VM-5 | Quality Control | Vegetation Management | Vegetation Management |  | 15671.7928 | A WMP activity, but does not have an SCE ID such as VM-X
PSPS-1 | PSPS-2 | De-Energization Notifications | Grid Operations and Protocols | N/A | 4337.1502 | 0 | Not a standalone activity in 2021 WMP; discussed as a part of PSPS-2
PSPS-1.1 | N/A | De-Energization Notifications | Grid Operations and Protocols | N/A |  | 0 | Not an activity in 2021 WMP, discussed in Chapter 8
PSPS-1.2 | N/A | De-Energization Notifications | Grid Operations and Protocols | N/A |  | 0 | Not an activity in 2021 WMP, discussed in Chapter 8
PSPS-1.3 | N/A | De-Energization Notifications | Grid Operations and Protocols | N/A |  | 0 | Not an activity in 2021 WMP, discussed in Chapter 8
PSPS-1.4 | N/A | De-Energization Notifications | Grid Operations and Protocols | N/A |  | 0 | Not an activity in 2021 WMP; work complete in 2020
PSPS-2 | PSPS-2 | Community Resource Centers / Customer Care Programs | Grid Operations and Protocols | Grid Operations and Protocols | 5751.394 | 136221.8516 | Remains an activity in 2021 WMP Update; renamed "Customer Care Programs"
PSPS-3 | PSPS-2 | Customer Resiliency Equipment Incentives | Grid Operations and Protocols | N/A | 7443.616 |  | Not a standalone activity in 2021 WMP; discussed as a part of PSPS-2
PSPS-4 | PSPS-2 | Critical Care Battery Backup | Grid Operations and Protocols | N/A | 12135.3387 |  | Not a standalone activity in 2021 WMP; discussed as a part of PSPS-2
PSPS-5 | N/A | MICOP Partnership | Grid Operations and Protocols | N/A | 0 |  | Not a standalone activity in 2021 WMP; discussed in Stakeholder Cooperation and Community Engagement Section 7.3.10
PSPS-6 | N/A | Independent Living Centers Partnership | Grid Operations and Protocols | N/A | 0 |  | Not a standalone activity in 2021 WMP; discussed in Stakeholder Cooperation and Community Engagement Section 7.3.10
PSPS-7 | PSPS-7 | Community Outreach | Grid Operations and Protocols | N/A | 1105.512 |  | Not a standalone activity in 2021 WMP, CCVs discussed as a part of PSPS-2
PSPS-8 | SH-12 | Microgrid Assessment | Grid Operations and Protocols | Grid Design and System Hardening |  | 11000 | Remains an activity in 2021 WMP Update; Activity renamed SH-12 and included in Section 7.3.3
OP-1 | N/A | Annual SOB 322 Review | Grid Operations and Protocols | N/A | 0 |  | Not an activity in 2021 WMP; operationalized
OP-2 | N/A | Wildfire Infrastructure Protection Team Additional Staffing | Emergency Preparedness and Planning | N/A | 5453.7457 |  | Not an activity in 2021 WMP; work complete in 2020
OP-3 | N/A | Unmanned Aerial Systems (UAS) Operations Training | Emergency Preparedness and Planning | N/A | 1357.232 |  | Not a standalone activity in 2021 WMP; discussed in Stakeholder Cooperation and Community Engagement Section 7.3.10
DEP-1.1 | DEP-1.3 | Customer Education and Engagement – Dear Neighbor Letter | Emergency Preparedness and Planning | N/A | 27916.257 |  | Not a standalone activity in 2021 WMP; discussed as a part of DEP-1.3. DEP-1.1, DEP-1.3, and DEP-3 were combined in 2020 WMP
DEP-1.2 | DEP-1.2 | Customer Education and Engagement - Community Meetings | Stakeholder Cooperation & Community Engagement | Stakeholder Cooperation & Community Engagement | 0 | 361.8582 | Remains an activity in 2021 WMP Update
DEP-1.3 | DEP-1.3 | Customer Education and Engagement - Marketing Campaign | Emergency Preparedness and Planning | Stakeholder Cooperation & Community Engagement |  | 9379.099 | Remains an activity in 2021 WMP Update. DEP-1.1, DEP-1.3, and DEP-3 were combined in 2020 WMP
DEP-2 | DEP-2 | SCE Emergency Responder Training | Emergency Preparedness and Planning | Emergency Preparedness and Planning | 5276.0892 | 5117.5815 | Remains an activity in 2021 WMP Update
DEP-3 | N/A | IOU Customer Engagement | Emergency Preparedness and Planning | N/A |  |  | Not an activity in 2021 WMP Update; Discontinued in Off Ramp report. DEP-1.1, DEP-1.3, and DEP-3 were combined in 2020 WMP
DEP-4 | DEP-4 | Customer Research and Education | Emergency Preparedness and Planning | Stakeholder Cooperation & Community Engagement | 4308.571 | 2899 | Remains an activity in 2021 WMP Update
AT-2.1 | SA-9 | Distribution Fault Anticipation (DFA) | Situational Awareness | Situational Awareness | 30002.356 | 29890.2032 | Remains an activity in 2021 WMP Update; renamed SA-9
AT-2.2 | N/A | Advanced Unmanned Aerial Systems Study | Asset Management and Inspections | N/A | 1107.1633 |  | Not an activity in 2021 WMP; Complete in 2020
AT-3.1 | N/A | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter - Ground Fault Neutralizer (GFN) | Grid Design and System Hardening | N/A | 6271.5344 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.2 | N/A | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter – Resonant Grounding with Arc Suppression Coil | Grid Design and System Hardening | N/A | 1235.7517 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.3 | N/A | Alternative Technology Evaluations – Rapid Earth Fault Current Limiter and Resonant Grounded Transformer | Grid Design and System Hardening | N/A | 1444.016 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.4 | N/A | Alternative Technology Evaluations – Distribution Open Phase Detection | Grid Design and System Hardening | N/A | 511.2285 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-4 | N/A | Alternative Technology Implementation – Vibration Dampers | Grid Design and System Hardening | N/A | 0 |  | Not an activity in 2021 WMP; work complete in 2020
AT-5 | N/A | Asset Defect Detection Using Machine Learning Object Detection | Asset Management and Inspections | N/A | 0 |  | Not an activity in 2021 WMP; work complete in 2020
AT-6 | N/A | Assessment of Partial Discharge for Transmission Facilities | Asset Management and Inspections | N/A | 0 |  | Not an activity in 2021 WMP; work complete in 2020
AT-8 | N/A | High Impedance Relay Evaluations | Grid Design and System Hardening | N/A | 306.7371 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
N/A | SH-13 | C-Hooks | N/A | Grid Design and System Hardening |  | 1000 | Not an activity in 2020 WMP; New Activity in 2021 WMP (SH-13)
N/A | SH-14 | Long Span Initiative (LSI) | N/A | Grid Design and System Hardening |  | 56336.1249 | Not an activity in 2020 WMP; New Activity in 2021 WMP (SH-14)
N/A | SH-15 | Vertical Switches | N/A | Grid Design and System Hardening |  | 2603.5025 | Not an activity in 2020 WMP; New Activity in 2021 WMP Update (SH-14)
N/A | DG-2 | Wildfire Safety Data Mart and Data Management (WiSDM / Ezy) | N/A | Data Governance |  |  | Not an activity in 2020 WMP; New Activity in 2021 WMP Update (DG-1)
N/A | IN-9 | Inspection Work Management Tools | N/A | Asset Management and Inspections |  |  | Not an activity in 2020 WMP; New Activity in 2021 WMP Update (IN-8)
N/A | VM-7 | VM Work Management Tool (Arbora) | N/A | Vegetation Management |  |  | Not an activity in 2020 WMP; New Activity in 2021 WMP Update (VM-6)
N/A | DEP-5 | Aerial Suppression | N/A | Stakeholder Cooperation & Community Engagement |  | 38158 | Not an activity in 2020 WMP; New Activity in 2021 WMP Update
N/A | DG-1 | Centralized repository for data | N/A | Data Governance | 0 | 34507.5338 | New Activity in 2021 WMP Update
N/A | IN-8 | Improvement of inspections | N/A | Asset Management and Inspections |  | 64164.2992 | New Activity in 2021 WMP Update
N/A | VM-6 | Vegetation inventory system | N/A | Vegetation Management |  | 40441.1735 | New Activity in 2021 WMP Update
N/A | N/A | Vegetation management to achieve clearances around electric lines and equipment | Vegetation Management | Vegetation Management | 201319.791 | 744355.8834 | A WMP activity, but does not have an SCE ID such as VM-X
N/A | N/A | LiDAR inspections of vegetation around transmission electric lines and equipment | Vegetation Management | Vegetation Management | 4455.4185 | 7080.209 | A WMP activity, but does not have an SCE ID such as VM-X
N/A | N/A | Allocation methodology development and application | N/A | Resource Allocation Methodology |  | 61771.1455 | A WMP activity, but does not have an SCE ID such as DEP-X
N/A | N/A | Preparedness and planning for service restoration |  | Emergency Planning & Preparedness | 34787.975 | 29663.5496 | A WMP activity, but does not have an SCE ID such as DEP-X
N/A | PSPS-2 | PSPS events and mitigation of PSPS impacts | Grid operations and protocols |  | 22369.037 |  | A WMP activity, but does not have an SCE ID such as PSPS-X. Discussed as a part of PSPS-2.
N/A | N/A | Organizational Support - PMO, OCM, and wildfire-related IT support | Resource allocation methodology |  | 133328.914 |  | Not a standalone activity in 2021 WMP and is discussed as part of IN-8, PSPS-2, and Resource Allocation Methodology.
N/A | SA-1 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Situational Awareness |  | 5409.6508 |  | Cost now included as part of SA-1 in 2021 WMP.
N/A | N/A | Alternative Technologies | N/A | Situational Awareness |  | 11916 | Were separate activities AT-X activities in 2020 WMP. Not an activity in 2021 WMP; discussed in Section 7.1.D
Total |  |  |  |  | 3823262.9208 | 4827696.7196

## Grid Hardening Reconciliation
2020 WMP ID | 2021 WMP Update ID | WMP Activities in 2020 WMP and 2021 WMP Update | 2020 WMP Categorization | 2021 WMP Update Categorization | 2020 WMP forecast for 2021-2022 costs ($ thousands) | 2021 WMP update forecast for 2021-2022 costs ($ thousands) | Notes | GRID HARDENING CHANGES RECONCILIATION
SH-1 | SH-1 | Covered Conductor | Grid Design and System Hardening | Grid Design and System Hardening | 1882536.2084 | 2183623.1483 | Remains an activity in 2021 WMP Update | ID | Description | Costs ($ thousands)
SH-2 | SH-2 | Undergrounding Overhead Conductor | Grid Design and System Hardening | Grid Design and System Hardening | 64964.7496 | 81658.5911 | Remains an activity in 2021 WMP Update | a | 2020 WMP Activities Costs for Grid Design and System Hardening | 2914533.4027
SH-3 | SH-1 | WCCP Fire Resistant Poles | Grid Design and System Hardening | N/A | 194485.5577 |  | Not a standalone activity in 2021 WMP; discussed as a part of SH-1 Covered Conductor | b | MOVED OUT: SH-12.1, SH-12.2, SH-12.3 to Asset Management Combined with IN-1.1, IN_1.2 and IN-5 respectively | 631976.721
SH-4 | SH-4 | Branch Line Protection Strategy | Grid Design and System Hardening | Grid Design and System Hardening | 19285.9 | 12771.148 | Remains an activity in 2021 WMP Update | c | NOT INCLUDED AS WMP ACTIVITY: AT-1, AT-3.1, AT-3.2, AT-3.3, AT-3.4, AT-4, AT-8 | 9769.2677
SH-5 | SH-5 | Installation of System Automation Equipment – RAR/RCS | Grid Design and System Hardening | Grid Design and System Hardening | 8639.9018 | 5866.6214 | Remains an activity in 2021 WMP Update | d | MOVED IN: SH-12 from Grid Operations and Protocols | 11000
SH-6 | SH-6 | Circuit Breaker Relay Hardware for FC | Grid Design and System Hardening | Grid Design and System Hardening | 26754.2531 | 31257.3957 | Remains an activity in 2021 WMP Update | e | ADDED: SH-13, SH-14, SH-15 newly in 2021 | 59939.6274
SH-7 | SH-7 | PSPS-Driven Grid Hardening Work / Circuit Evaluation for PSPS-Driven Grid Hardening Work | Grid Design and System Hardening | Grid Design and System Hardening | 0 |  | Remains an activity in 2021 WMP Update; Renamed Circuit Evaluation for PSPS-Driven Grid Hardening Work | f | Changes in costs for activities that are same in 2020 WMP and 2021 Update | 111160.3304
SH-8 | SH-8 | Transmission Open Phase Detection | Grid Design and System Hardening | Grid Design and System Hardening | 864.96 | 1274.6627 | Remains an activity in 2021 WMP Update | g=a-b-c+d+e+f | 2021 WMP Update Costs for Grid Design and System Hardening | 2454887.3717
SH-9 | N/A | Transmission Overhead Standards (TOH) Review | Grid Design and System Hardening | N/A | 0 | 0 | Not an activity in 2021 WMP; evaluation complete in 2020
AT-1 | N/A | Alternative Technology Pilots – Meter Alarming for Down Energized Conductor (MADEC) | Grid Design and System Hardening | N/A | 0 | 0 | Not an activity in 2021 WMP; discussed in Section 7.1.D
SH-10 | SH-10 | Tree Attachment Remediation | Grid Design and System Hardening | Grid Design and System Hardening | 63992.3731 | 57974.2889 | Remains an activity in 2021 WMP Update
SH-11 | SH-11 | Legacy Facilities | Grid Design and System Hardening | Grid Design and System Hardening | 11263.51 | 9521.8882 | Remains an activity in 2021 WMP Update
SH-12.1 | IN-1.1 | Remediations – Distribution | Grid Design and System Hardening | N/A | 537596.484 |  | Not a standalone activity in 2021 WMP; discussed as a part of IN-1.1
SH-12.2 | IN-1.2 | Remediations – Transmission | Grid Design and System Hardening | N/A | 93980.237 |  | Not a standalone activity in 2021 WMP; discussed as a part ofIN-1.2
SH-12.3 | IN-5 | Remediations – Generation | Grid Design and System Hardening | N/A | 400 |  | Not a standalone activity in 2021 WMP; discussed as a part ofIN-5
PSPS-8 | SH-12 | Microgrid Assessment | Grid Operations and Protocols | Grid Design and System Hardening |  | 11000 | Remains an activity in 2021 WMP Update; Activity renamed SH-12 and included in Section 7.3.3
AT-3.1 | N/A | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter - Ground Fault Neutralizer (GFN) | Grid Design and System Hardening | N/A | 6271.5344 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.2 | N/A | Alternative Technology Evaluations: Rapid Earth Fault Current Limiter – Resonant Grounding with Arc Suppression Coil | Grid Design and System Hardening | N/A | 1235.7517 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.3 | N/A | Alternative Technology Evaluations – Rapid Earth Fault Current Limiter and Resonant Grounded Transformer | Grid Design and System Hardening | N/A | 1444.016 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-3.4 | N/A | Alternative Technology Evaluations – Distribution Open Phase Detection | Grid Design and System Hardening | N/A | 511.2285 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
AT-4 | N/A | Alternative Technology Implementation – Vibration Dampers | Grid Design and System Hardening | N/A | 0 |  | Not an activity in 2021 WMP; work complete in 2020
AT-8 | N/A | High Impedance Relay Evaluations | Grid Design and System Hardening | N/A | 306.7371 |  | Not an activity in 2021 WMP; discussed in Section 7.1.D
N/A | SH-13 | C-Hooks | N/A | Grid Design and System Hardening |  | 1000 | Not an activity in 2020 WMP; New Activity in 2021 WMP (SH-13)
N/A | SH-14 | Long Span Initiative (LSI) | N/A | Grid Design and System Hardening |  | 56336.1249 | Not an activity in 2020 WMP; New Activity in 2021 WMP (SH-14)
N/A | SH-15 | Vertical Switches | N/A | Grid Design and System Hardening |  | 2603.5025 | Not an activity in 2020 WMP; New Activity in 2021 WMP Update (SH-14)
Total |  |  |  |  | 2914533.4027 | 2454887.3717

## DATA_Tables 21-30 Rev2
2021 WMP Mapping
Mitigation | Table # | Initiative # | Table-Initiative # | Initiative Activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments | WMP Program/Non-WMP Program | HFRA/Non-HFRA/Combined/No Forecast | 2021 WMP Initiative Number | 2021 WMP Initiative
Risk assessment and mapping | 21 | 1 | 21-1 | 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 1 | 21-1 | 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 1 | 21-1 | 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 1 | 21-1 | 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 1 | 21-1 | 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 1 | 21-1 | 1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 2 | 21-2 | 2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 2 | 21-2 | 2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 2 | 21-2 | 2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 2 | 21-2 | 2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 2 | 21-2 | 2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 2 | 21-2 | 2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 3 | 21-3 | 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 3 | 21-3 | 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 3 | 21-3 | 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 3 | 21-3 | 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 3 | 21-3 | 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 3 | 21-3 | 3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 4 | 21-4 | 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 4 | 21-4 | 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 4 | 21-4 | 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 4 | 21-4 | 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 4 | 21-4 | 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 4 | 21-4 | 4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 5 | 21-5 | 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 5 | 21-5 | 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 5 | 21-5 | 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 5 | 21-5 | 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 5 | 21-5 | 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 5 | 21-5 | 5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 6 | 21-6 | 6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 6 | 21-6 | 6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 6 | 21-6 | 6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 6 | 21-6 | 6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 6 | 21-6 | 6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Risk assessment and mapping | 21 | 6 | 21-6 | 6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Situational awareness and forecasting | 22 | 1 | 22-1 | 1. Advanced weather monitoring and weather stations (SA-1) | 2019 plan | 6031.067 | 5389.254 | 641.813 | 315 | 19.1462 | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 1 | 22-1 | 1. Advanced weather monitoring and weather stations (SA-1) | 2019 actual | 5520.099 | 4282.182 | 1237.917 | 357 | 15.4625 | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 1 | 22-1 | 1. Advanced weather monitoring and weather stations (SA-1) | 2020 | 6832.771 | 5535.885 | 1296.886 | 475 | 14.3848 | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 1 | 22-1 | 1. Advanced weather monitoring and weather stations (SA-1) | 2021 | 5766.528 | 4203.504 | 1563.024 | 475 | 12.1401 | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 1 | 22-1 | 1. Advanced weather monitoring and weather stations (SA-1) | 2022 | 5800.296 | 4203.504 | 1596.792 | 475 | 12.2111 | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 1 | 22-1 | 1. Advanced weather monitoring and weather stations (SA-1) | 2020-2022 plan total | 18399.595 | 13942.893 | 4456.702 | 1425 | 12.912 | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 2.1 | 22-2.1 | 2.1. Continuous monitoring sensors: Distribution Fault Anticipation (DFA) (AT-2.1) | 2019 plan | 69.205 | 0 | 69.205 | 10 | 6.9205 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.2. | Continuous monitoring sensors
Situational awareness and forecasting | 22 | 2.1 | 22-2.1 | 2.1. Continuous monitoring sensors: Distribution Fault Anticipation (DFA) (AT-2.1) | 2019 actual | 2485.151 | 0 | 2485.151 | 24 | 103.548 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | In 2019, SCE developed a plan to engineer, design, and construct 60 DFA units. 54 were constructed. Of those 54, 24 were fully commissioned. The costs for the 2019 work includes the engineering, design, construction of all DFAs and the commissioning of 24 units of the 60 units. The remaining will DFA units will be completed in 2020. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.2. | Continuous monitoring sensors
Situational awareness and forecasting | 22 | 2.1 | 22-2.1 | 2.1. Continuous monitoring sensors: Distribution Fault Anticipation (DFA) (AT-2.1) | 2020 | 251.524 | 0 | 251.524 | 36 | 6.9868 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | In the first quarter of 2020, the remaining 36 DFAs will be commissioned and monitored. In 2020 engineering will monitor the DFA pilot installations to assess the success of the pilot. No other DFAs will be deployed until the assessment in 2020 is complete. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.2. | Continuous monitoring sensors
Situational awareness and forecasting | 22 | 2.1 | 22-2.1 | 2.1. Continuous monitoring sensors: Distribution Fault Anticipation (DFA) (AT-2.1) | 2021 | 9900.683 | 9646.065 | 254.618 | 150 | 66.0046 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.2. | Continuous monitoring sensors
Situational awareness and forecasting | 22 | 2.1 | 22-2.1 | 2.1. Continuous monitoring sensors: Distribution Fault Anticipation (DFA) (AT-2.1) | 2022 | 19850.149 | 19850.149 | 0 | 300 | 66.1672 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.2. | Continuous monitoring sensors
Situational awareness and forecasting | 22 | 2.1 | 22-2.1 | 2.1. Continuous monitoring sensors: Distribution Fault Anticipation (DFA) (AT-2.1) | 2020-2022 plan total | 30002.356 | 29496.214 | 506.142 | 486 | 61.7332 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.2. | Continuous monitoring sensors
Situational awareness and forecasting | 22 | 2.2 | 22-2.2 | 2.2. Continuous monitoring sensors: Early Fault Detection (EFD) evaluation (AT-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Situational awareness and forecasting | 22 | 2.2 | 22-2.2 | 2.2. Continuous monitoring sensors: Early Fault Detection (EFD) evaluation (AT-7) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Situational awareness and forecasting | 22 | 2.2 | 22-2.2 | 2.2. Continuous monitoring sensors: Early Fault Detection (EFD) evaluation (AT-7) | 2020 | 511.228 | 0 | 511.228 | 25 | 20.4491 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Monitor DFA during 2020; Estimated 2.5 miles per sensor install. The mileage values are estimated total miles covered and may include HFRA, non-HFRA, and Underground circuitry. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Situational awareness and forecasting | 22 | 2.2 | 22-2.2 | 2.2. Continuous monitoring sensors: Early Fault Detection (EFD) evaluation (AT-7) | 2021 | 2587.583 | 0 | 2587.583 | 225 | 11.5004 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Monitor DFA during 2021; Estimated 2.5 miles per sensor install. The mileage values are estimated total miles covered and may include HFRA, non-HFRA, and Underground circuitry. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Situational awareness and forecasting | 22 | 2.2 | 22-2.2 | 2.2. Continuous monitoring sensors: Early Fault Detection (EFD) evaluation (AT-7) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns for 2022 for this Initiative are "UNKNOWN" as the scope and strategy are yet to be determined for 2022. This determination will be made after careful study and review of the 2020-2021 work. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Situational awareness and forecasting | 22 | 2.2 | 22-2.2 | 2.2. Continuous monitoring sensors: Early Fault Detection (EFD) evaluation (AT-7) | 2020-2022 plan total | 3098.811 | 0 | 3098.811 | 250 | 12.3952 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Situational awareness and forecasting | 22 | 2.3 | 22-2.3 | 2.3. Continuous monitoring sensors: transmission open phase detection (SH-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs
Situational awareness and forecasting | 22 | 2.3 | 22-2.3 | 2.3. Continuous monitoring sensors: transmission open phase detection (SH-8) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 actual. This initiative was successfully piloted in 2109 and cost were charged to internal overhead. | WMP Program | HFRA | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs
Situational awareness and forecasting | 22 | 2.3 | 22-2.3 | 2.3. Continuous monitoring sensors: transmission open phase detection (SH-8) | 2020 | 295.0149 | 0 | 295.0149 | 323.5 | 0.91195 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | Instead of "Line miles to be treated", select circuit miles within the HFRA is the unit of measure. The “Other risk drivers addressed” columns “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs
Situational awareness and forecasting | 22 | 2.3 | 22-2.3 | 2.3. Continuous monitoring sensors: transmission open phase detection (SH-8) | 2021 | 288.0542 | 0 | 288.0542 | 315.8671 | 0.91195 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | The "Line miles to be treated" and "Spend/ treated line mile" columns are "UNKNOWN" because the expansion of deployment is based on the success/fail criteria in 2020. The “Other risk drivers addressed” column is “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs
Situational awareness and forecasting | 22 | 2.3 | 22-2.3 | 2.3. Continuous monitoring sensors: transmission open phase detection (SH-8) | 2022 | 281.891 | 0 | 281.891 | 315.8671 | 0.89244 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | The "Line miles to be treated" and "Spend/ treated line mile" columns are "UNKNOWN" because the expansion of deployment is based on the success/fail criteria in 2020. The “Other risk drivers addressed” column is “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs
Situational awareness and forecasting | 22 | 2.3 | 22-2.3 | 2.3. Continuous monitoring sensors: transmission open phase detection (SH-8) | 2020-2022 plan total | 864.96 | 0 | 864.96 | 955.2343 | 0.90572 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | Instead of "Line miles to be treated", select circuit miles within the HFRA is the unit of measure. The “Other risk drivers addressed” columns “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.3.17.3 | Updates to grid topology to minimize risk of ignition in HFTDs
Situational awareness and forecasting | 22 | 3 | 22-3 | 3. Fault indicators for detecting faults on electric lines and equipment | 2019 plan | 4285.315 | 4285.315 | 0 | 265 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | Combined | 7.3.2.3. | Fault indicators for detecting faults on electric lines and equipment
Situational awareness and forecasting | 22 | 3 | 22-3 | 3. Fault indicators for detecting faults on electric lines and equipment | 2019 actual | 2134.572 | 2134.572 | 0 | 132 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | Combined | 7.3.2.3. | Fault indicators for detecting faults on electric lines and equipment
Situational awareness and forecasting | 22 | 3 | 22-3 | 3. Fault indicators for detecting faults on electric lines and equipment | 2020 | 1649.442 | 1649.442 | 0 | 102 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | Combined | 7.3.2.3. | Fault indicators for detecting faults on electric lines and equipment
Situational awareness and forecasting | 22 | 3 | 22-3 | 3. Fault indicators for detecting faults on electric lines and equipment | 2021 | 2522.676 | 2522.676 | 0 | 156 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | Combined | 7.3.2.3. | Fault indicators for detecting faults on electric lines and equipment
Situational awareness and forecasting | 22 | 3 | 22-3 | 3. Fault indicators for detecting faults on electric lines and equipment | 2022 | 2522.676 | 2522.676 | 0 | 156 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | Combined | 7.3.2.3. | Fault indicators for detecting faults on electric lines and equipment
Grid design and system hardening | 23 | 2.1 | 23-2.1 | 2.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: maintenance | 2020-2022 plan total | 600 | 0 | 600 | 414 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Situational awareness and forecasting | 22 | 4.1 | 22-4.1 | 4.1 .Forecast of a fire risk index, fire potential index, or similar: Fire Potential Index phase II (SA-2) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22 | Non-WMP Program | No Forecast
Situational awareness and forecasting | 22 | 4.1 | 22-4.1 | 4.1 .Forecast of a fire risk index, fire potential index, or similar: Fire Potential Index phase II (SA-2) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22 | Non-WMP Program | No Forecast
Situational awareness and forecasting | 22 | 4.1 | 22-4.1 | 4.1 .Forecast of a fire risk index, fire potential index, or similar: Fire Potential Index phase II (SA-2) | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22 | Non-WMP Program | No Forecast
Situational awareness and forecasting | 22 | 4.1 | 22-4.1 | 4.1 .Forecast of a fire risk index, fire potential index, or similar: Fire Potential Index phase II (SA-2) | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22 | Non-WMP Program | No Forecast
Situational awareness and forecasting | 22 | 4.1 | 22-4.1 | 4.1 .Forecast of a fire risk index, fire potential index, or similar: Fire Potential Index phase II (SA-2) | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22 | Non-WMP Program | No Forecast
Situational awareness and forecasting | 22 | 4.1 | 22-4.1 | 4.1 .Forecast of a fire risk index, fire potential index, or similar: Fire Potential Index phase II (SA-2) | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22 | Non-WMP Program | No Forecast
Situational awareness and forecasting | 22 | 4.2 | 22-4.2 | 4.2. Forecast of a fire risk index, fire potential index, or similar: fuel sampling program (SA-5) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.2 | 22-4.2 | 4.2. Forecast of a fire risk index, fire potential index, or similar: fuel sampling program (SA-5) | 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA | NA | NA | The "Total per initiative spend" for 2019 actual is "NA" as this initiative is covered in Initiative 4.3, Table 22. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.2 | 22-4.2 | 4.2. Forecast of a fire risk index, fire potential index, or similar: fuel sampling program (SA-5) | 2020 | 631.824 | 0 | 631.824 | 6500 | 0.097204 | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.2 | 22-4.2 | 4.2. Forecast of a fire risk index, fire potential index, or similar: fuel sampling program (SA-5) | 2021 | 645.23 | 0 | 645.23 | 6500 | 0.099266 | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.2 | 22-4.2 | 4.2. Forecast of a fire risk index, fire potential index, or similar: fuel sampling program (SA-5) | 2022 | 659.17 | 0 | 659.17 | 6500 | 0.10141 | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.2 | 22-4.2 | 4.2. Forecast of a fire risk index, fire potential index, or similar: fuel sampling program (SA-5) | 2020-2022 plan total | 1936.224 | 0 | 1936.224 | 19500 | 0.099294 | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.2 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.3 | 22-4.3 | 4.3. Forecast of a fire risk index, fire potential index, or similar: surface & canopy fuels mapping (SA-6) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this was not a 2019 activity. | WMP Program | HFRA | 7.3.2.6.2 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 4.3 | 22-4.3 | 4.3. Forecast of a fire risk index, fire potential index, or similar: surface & canopy fuels mapping (SA-6) | 2019 actual | 92.814 | 0 | 92.814 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.2 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 4.3 | 22-4.3 | 4.3. Forecast of a fire risk index, fire potential index, or similar: surface & canopy fuels mapping (SA-6) | 2020 | 1380.72 | 0 | 1380.72 | 14179 | 0.097378 | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.2 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 4.3 | 22-4.3 | 4.3. Forecast of a fire risk index, fire potential index, or similar: surface & canopy fuels mapping (SA-6) | 2021 | 208.891 | 0 | 208.891 | 14179 | 0.014732 | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.2 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 4.3 | 22-4.3 | 4.3. Forecast of a fire risk index, fire potential index, or similar: surface & canopy fuels mapping (SA-6) | 2022 | 213.404 | 0 | 213.404 | 14179 | 0.015051 | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.2 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 4.3 | 22-4.3 | 4.3. Forecast of a fire risk index, fire potential index, or similar: surface & canopy fuels mapping (SA-6) | 2020-2022 plan total | 1803.015 | 0 | 1803.015 | 42537 | 0.042387 | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.2 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 4.4 | 22-4.4 | 4.4. Forecast of a fire risk index, fire potential index, or similar: remote sensing / satellite fuel moisture (SA-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.4 | 22-4.4 | 4.4. Forecast of a fire risk index, fire potential index, or similar: remote sensing / satellite fuel moisture (SA-7) | 2019 actual | 0 | 0 | 0 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.4 | 22-4.4 | 4.4. Forecast of a fire risk index, fire potential index, or similar: remote sensing / satellite fuel moisture (SA-7) | 2020 | 1534.133 | 0 | 1534.133 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.4 | 22-4.4 | 4.4. Forecast of a fire risk index, fire potential index, or similar: remote sensing / satellite fuel moisture (SA-7) | 2021 | 1827.798 | 0 | 1827.798 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.4 | 22-4.4 | 4.4. Forecast of a fire risk index, fire potential index, or similar: remote sensing / satellite fuel moisture (SA-7) | 2022 | 0 | 0 | 0 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.4 | 22-4.4 | 4.4. Forecast of a fire risk index, fire potential index, or similar: remote sensing / satellite fuel moisture (SA-7) | 2020-2022 plan total | 3361.931 | 0 | 3361.931 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.3 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.5 | 22-4.5 | 4.5. Forecast of a fire risk index, fire potential index, or similar: fire science enhancements (SA-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.5 | 22-4.5 | 4.5. Forecast of a fire risk index, fire potential index, or similar: fire science enhancements (SA-8) | 2019 actual | 773.444 | 0 | 773.444 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.5 | 22-4.5 | 4.5. Forecast of a fire risk index, fire potential index, or similar: fire science enhancements (SA-8) | 2020 | 1534.133 | 0 | 1534.133 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.5 | 22-4.5 | 4.5. Forecast of a fire risk index, fire potential index, or similar: fire science enhancements (SA-8) | 2021 | 1566.684 | 0 | 1566.684 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.5 | 22-4.5 | 4.5. Forecast of a fire risk index, fire potential index, or similar: fire science enhancements (SA-8) | 2022 | 1600.531 | 0 | 1600.531 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 4.5 | 22-4.5 | 4.5. Forecast of a fire risk index, fire potential index, or similar: fire science enhancements (SA-8) | 2020-2022 plan total | 4701.348 | 0 | 4701.348 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.4.4 | Forecast of a fire risk index, fire potential index, or similar
Situational awareness and forecasting | 22 | 5 | 22-5 | 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2019 plan | 4900.349 | 2283.22 | 2617.129 | NA | NA | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 5 | 22-5 | 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2019 actual | 1436.1416 | 969.552 | 466.5895 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 5 | 22-5 | 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2020 | 1844.2773 | 219.8177 | 1624.4596 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 5 | 22-5 | 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2021 | 1763.6359 | 0 | 1763.6359 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 5 | 22-5 | 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2022 | 1801.7376 | 0 | 1801.7376 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 5 | 22-5 | 5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2020-2022 plan total | 5409.6508 | 219.8177 | 5189.833 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.1. | Advanced weather monitoring and weather stations
Situational awareness and forecasting | 22 | 6 | 22-6 | 6. Weather forecasting and estimating impacts on electric lines and equipment (SA-3) | 2019 plan | 4495.8845 | 3759.22 | 736.6645 | NA | NA | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 6 | 22-6 | 6. Weather forecasting and estimating impacts on electric lines and equipment (SA-3) | 2019 actual | 7006.235 | 5678.791 | 1327.444 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 6 | 22-6 | 6. Weather forecasting and estimating impacts on electric lines and equipment (SA-3) | 2020 | 2456.619 | 799.555 | 1657.064 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 6 | 22-6 | 6. Weather forecasting and estimating impacts on electric lines and equipment (SA-3) | 2021 | 2899.377 | 1102.466 | 1796.911 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 6 | 22-6 | 6. Weather forecasting and estimating impacts on electric lines and equipment (SA-3) | 2022 | 1835.925 | 0 | 1835.925 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 6 | 22-6 | 6. Weather forecasting and estimating impacts on electric lines and equipment (SA-3) | 2020-2022 plan total | 7191.921 | 1902.021 | 5289.9 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 7 | 22-7 | 7. Develop Asset & Reliability & Risk Analytics Capability (RA-1, SA-4) | 2019 plan | 509.798 | 509.798 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 7 | 22-7 | 7. Develop Asset & Reliability & Risk Analytics Capability (RA-1, SA-4) | 2019 actual | 857.51 | 857.51 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 7 | 22-7 | 7. Develop Asset & Reliability & Risk Analytics Capability (RA-1, SA-4) | 2020 | 6692.174 | 6692.174 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 7 | 22-7 | 7. Develop Asset & Reliability & Risk Analytics Capability (RA-1, SA-4) | 2021 | NA | NA | NA | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 7 | 22-7 | 7. Develop Asset & Reliability & Risk Analytics Capability (RA-1, SA-4) | 2022 | NA | NA | NA | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Situational awareness and forecasting | 22 | 7 | 22-7 | 7. Develop Asset & Reliability & Risk Analytics Capability (RA-1, SA-4) | 2020-2022 plan total | 6692.174 | 6692.174 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.2.6.1 | Weather forecasting and estimating impacts on electric lines and equipment
Grid design and system hardening | 23 | 1 | 23-1 | 1. Capacitor maintenance and replacement program | 2019 plan | 10300 | 10094 | 206 | 116 | 88.7931 | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.1. | Capacitor maintenance and replacement program
Grid design and system hardening | 23 | 1 | 23-1 | 1. Capacitor maintenance and replacement program | 2019 actual | 9700 | 9506 | 194 | 111 | 87.3874 | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.1. | Capacitor maintenance and replacement program
Grid design and system hardening | 23 | 1 | 23-1 | 1. Capacitor maintenance and replacement program | 2020 | 4994.914 | 4895.016 | 99.898 | 58 | 86.1192 | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.1. | Capacitor maintenance and replacement program
Grid design and system hardening | 23 | 1 | 23-1 | 1. Capacitor maintenance and replacement program | 2021 | 3694.425 | 3620.537 | 73.888 | UNKNOWN | UNKNOWN | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. The "Line miles to be treated" and "Spend/treated line mile" columns for 2021 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.1. | Capacitor maintenance and replacement program
Grid design and system hardening | 23 | 1 | 23-1 | 1. Capacitor maintenance and replacement program | 2022 | 3801.285 | 3725.259 | 76.026 | UNKNOWN | UNKNOWN | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. The "Line miles to be treated" and "Spend/treated line mile" columns for 2022 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.1. | Capacitor maintenance and replacement program
Grid design and system hardening | 23 | 15 | 23-15 | 15. Transmission tower maintenance and replacement | 2020-2022 plan total | 17075.3454 | 0 | 17075.3454 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.15. | Transmission tower maintenance and replacement
Grid design and system hardening | 23 | 2.1 | 23-2.1 | 2.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: maintenance | 2019 plan | 208.228 | 0 | 208.228 | 138 | 1.5089 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.1 | 23-2.1 | 2.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: maintenance | 2019 actual | 208.228 | 0 | 208.228 | 138 | 1.5089 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.1 | 23-2.1 | 2.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: maintenance | 2020 | 200 | 0 | 200 | 138 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.1 | 23-2.1 | 2.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: maintenance | 2021 | 200 | 0 | 200 | 138 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.1 | 23-2.1 | 2.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: maintenance | 2022 | 200 | 0 | 200 | 138 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Asset management and inspections | 24 | 1 | 24-1 | 1. Detailed inspections of distribution electric lines and equipment: distribution HFRA detailed inspections (previously ODI) | 2020-2022 plan total | 7890.7938 | 0 | 7890.7938 | 184383 | 0.042796 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.1. | Detailed inspections of distribution electric lines and equipment
Grid design and system hardening | 23 | 2.2 | 23-2.2 | 2.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - meter alarm down energized conductor (MADEC) (AT-1) | 2019 plan | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.2 | 23-2.2 | 2.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - meter alarm down energized conductor (MADEC) (AT-1) | 2019 actual | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.2 | 23-2.2 | 2.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - meter alarm down energized conductor (MADEC) (AT-1) | 2020 | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.2 | 23-2.2 | 2.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - meter alarm down energized conductor (MADEC) (AT-1) | 2021 | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.2 | 23-2.2 | 2.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - meter alarm down energized conductor (MADEC) (AT-1) | 2022 | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.2 | 23-2.2 | 2.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - meter alarm down energized conductor (MADEC) (AT-1) | 2020-2022 plan total | NA | NA | NA | 321264 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.1 | 23-2.3.1 | 2.3.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - ground fault neutralizer (GFN) (AT-3.1) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.1 | 23-2.3.1 | 2.3.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - ground fault neutralizer (GFN) (AT-3.1) | 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.1 | 23-2.3.1 | 2.3.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - ground fault neutralizer (GFN) (AT-3.1) | 2020 | 2586.8161 | 0 | 2586.8161 | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.1 | 23-2.3.1 | 2.3.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - ground fault neutralizer (GFN) (AT-3.1) | 2021 | 3684.7183 | 0 | 3684.7183 | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.1 | 23-2.3.1 | 2.3.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - ground fault neutralizer (GFN) (AT-3.1) | 2022 | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile" columns are "NA" because the pilot is currently only scheduled for 2020 and 2021. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.1 | 23-2.3.1 | 2.3.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - ground fault neutralizer (GFN) (AT-3.1) | 2020-2022 plan total | 6271.5344 | 0 | 6271.5344 | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.2 | 23-2.3.2 | 2.3.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - arc suppression coil (AT-3.2) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.2 | 23-2.3.2 | 2.3.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - arc suppression coil (AT-3.2) | 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.2 | 23-2.3.2 | 2.3.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - arc suppression coil (AT-3.2) | 2020 | 511.2285 | 0 | 511.2285 | 1 | 511.2285 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", units is the unit of measure. The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.2 | 23-2.3.2 | 2.3.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - arc suppression coil (AT-3.2) | 2021 | 724.5233 | 0 | 724.5233 | 1 | 724.5233 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", units is the unit of measure. The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.2 | 23-2.3.2 | 2.3.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - arc suppression coil (AT-3.2) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.2 | 23-2.3.2 | 2.3.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - arc suppression coil (AT-3.2) | 2020-2022 plan total | 1235.7517 | 0 | 1235.7517 | 2 | 617.8759 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", units is the unit of measure. The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.3 | 23-2.3.3 | 2.3.3. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - isolation transformer (AT-3.3) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.3 | 23-2.3.3 | 2.3.3. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - isolation transformer (AT-3.3) | 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.3 | 23-2.3.3 | 2.3.3. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - isolation transformer (AT-3.3) | 2020 | 408.9828 | 0 | 408.9828 | 1 | 408.9828 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", the number of pilot locations is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.3 | 23-2.3.3 | 2.3.3. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - isolation transformer (AT-3.3) | 2021 | 1035.0332 | 0 | 1035.0332 | 1 | 1035.0332 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", the number of pilot locations is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.3 | 23-2.3.3 | 2.3.3. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - isolation transformer (AT-3.3) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | NA | WMPMA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.3.3 | 23-2.3.3 | 2.3.3. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - isolation transformer (AT-3.3) | 2020-2022 plan total | 1444.016 | 0 | 1444.016 | 2 | 722.008 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", the number of pilot locations is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.4 | 23-2.4 | 2.4. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - distribution open phase detection (AT-3.4) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.4 | 23-2.4 | 2.4. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - distribution open phase detection (AT-3.4) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.4 | 23-2.4 | 2.4. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - distribution open phase detection (AT-3.4) | 2020 | 511.2285 | 0 | 511.2285 | 5 | 102.2457 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit locations is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.4 | 23-2.4 | 2.4. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - distribution open phase detection (AT-3.4) | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2021/2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.4 | 23-2.4 | 2.4. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - distribution open phase detection (AT-3.4) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2021/2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.4 | 23-2.4 | 2.4. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - distribution open phase detection (AT-3.4) | 2020-2022 plan total | 511.2285 | 0 | 511.2285 | 5 | 102.2457 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | UNKNOWN | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit locations is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.5 | 23-2.5 | 2.5. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - high impedance relay evaluations (AT-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.5 | 23-2.5 | 2.5. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - high impedance relay evaluations (AT-8) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.5 | 23-2.5 | 2.5. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - high impedance relay evaluations (AT-8) | 2020 | 306.7371 | 0 | 306.7371 | 2 | 153.3685 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", protection relay setting counts are the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.5 | 23-2.5 | 2.5. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - high impedance relay evaluations (AT-8) | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the 2021 scope and strategy for this initiative are not known at this time. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.5 | 23-2.5 | 2.5. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - high impedance relay evaluations (AT-8) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the 2022 scope and strategy for this initiative are not known at this time. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.5 | 23-2.5 | 2.5. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - high impedance relay evaluations (AT-8) | 2020-2022 plan total | 306.7371 | 0 | 306.7371 | 2 | 153.3685 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", protection relay setting counts are the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 2.6 | 23-2.6 | 2.6. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker installs/ replacements | 2019 plan | 1094.6142 | 1094.6142 | 0 | 8 | 136.8268 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.6 | 23-2.6 | 2.6. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker installs/ replacements | 2019 actual | 1094.6142 | 1094.6142 | 0 | 8 | 136.8268 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.6 | 23-2.6 | 2.6. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker installs/ replacements | 2020 | 2479.5502 | 2479.5502 | 0 | 16 | 154.9719 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.6 | 23-2.6 | 2.6. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker installs/ replacements | 2021 | 3506.1286 | 3506.1286 | 0 | 26 | 134.8511 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.6 | 23-2.6 | 2.6. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker installs/ replacements | 2022 | 3589.2027 | 3589.2027 | 0 | 24 | 149.5501 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Asset management and inspections | 24 | 2 | 24-2 | 2. Detailed inspections of Transmission electric lines and equipment | 2020-2022 plan total | 3401.2211 | 0 | 3401.2211 | 37957 | 0.089607 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.2. | Detailed inspections of transmission electric lines and equipment
Grid design and system hardening | 23 | 2.7 | 23-2.7 | 2.7. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker relay hardware for fast curve (SH-6) | 2019 plan | 9052.155 | 9052.155 | 0 | 189 | 47.895 | CFO: All EFF: All | 0.20024 | 22.1207 | NA | New | NA | GSRPMA | NA | NA | The original budget allocated in 2019 under the GS&RP consisted of relays actually being replaced in 2019. However, given resource, outage, procurement constraints, no relays were able to be replaced in 2019. Subsequent decision was to instead focus on developing a full deployment plan for relay replacements in years 2020, 2021 and 2022. This goal to develop a full execution plan was achieved by YE2019. Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.7 | 23-2.7 | 2.7. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker relay hardware for fast curve (SH-6) | 2019 actual | 838.6407 | 838.6407 | 0 | NA | NA | CFO: All EFF: All | NA | NA | NA | New | NA | GSRPMA | NA | NA | The "Line Miles to Be Treated", "Spend/treated line mile", "Risk reduction", and "Risk-spend efficiency" columns are "NA" because all 2019 spend was for project scoping and engineering/design charges for work to be done in 2020. No relays were replaced in 2019. Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.7 | 23-2.7 | 2.7. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker relay hardware for fast curve (SH-6) | 2020 | 5170.0123 | 5170.0123 | 0 | 55 | 94.0002 | CFO: All EFF: All | 0.05653 | 11.3578 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.7 | 23-2.7 | 2.7. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker relay hardware for fast curve (SH-6) | 2021 | 11091.9206 | 11091.9206 | 0 | 81 | 136.9373 | CFO: All EFF: All | 0.080815 | 7.8089 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.7 | 23-2.7 | 2.7. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker relay hardware for fast curve (SH-6) | 2022 | 10492.3202 | 10492.3202 | 0 | 74 | 141.7881 | CFO: All EFF: All | 0.07166 | 7.5317 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 2.7 | 23-2.7 | 2.7. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker relay hardware for fast curve (SH-6) | 2020-2022 plan total | 26754.2531 | 26754.2531 | 0 | 210 | 127.4012 | CFO: All EFF: All | 0.209 | 8.4138 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid design and system hardening | 23 | 3.1 | 23-3.1 | 3.1. Covered conductor installation: covered conductor (SH-1) | 2019 plan | 42231.377 | 42231.377 | 0 | 95.7026 | 441.2773 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 1.1417 | 27.0351 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 3.1 | 23-3.1 | 3.1. Covered conductor installation: covered conductor (SH-1) | 2019 actual | 239911.075 | 239911.075 | 0 | 372 | 644.9222 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 5.6187 | 22.5382 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure. The 372 miles includes some overhead conductor program and 4 kV cutover work. Costs also include design, engineering, and pre-construction for 2020 work. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 3.1 | 23-3.1 | 3.1. Covered conductor installation: covered conductor (SH-1) | 2020 | 454368.671 | 454368.671 | 0 | 1000 | 454.3687 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 11.5251 | 25.9579 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 3.1 | 23-3.1 | 3.1. Covered conductor installation: covered conductor (SH-1) | 2021 | 656352.963 | 656352.963 | 0 | 1400 | 468.8235 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 14.8451 | 23.8746 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 3.1 | 23-3.1 | 3.1. Covered conductor installation: covered conductor (SH-1) | 2022 | 771814.5744 | 771814.5744 | 0 | 1600 | 482.3841 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 15.1985 | 21.3876 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 3.1 | 23-3.1 | 3.1. Covered conductor installation: covered conductor (SH-1) | 2020-2022 plan total | 1882536.2084 | 1882536.2084 | 0 | 4000 | 470.6341 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 41.5686 | 23.4004 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 3.2 | 23-3.2 | 3.2. Covered conductor installation: tree attachment remediation (SH-10) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin as a stand-alone initiative until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.3.3.2 | Covered conductor installation
Grid design and system hardening | 23 | 3.2 | 23-3.2 | 3.2. Covered conductor installation: tree attachment remediation (SH-10) | 2019 actual | 9383.4546 | 9383.4546 | 0 | 101 | 92.9055 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.3.2 | Covered conductor installation
Grid design and system hardening | 23 | 3.2 | 23-3.2 | 3.2. Covered conductor installation: tree attachment remediation (SH-10) | 2020 | 15182.9007 | 15182.9007 | 0 | 481.244 | 31.5493 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 24 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.3.2 | Covered conductor installation
Grid design and system hardening | 23 | 3.2 | 23-3.2 | 3.2. Covered conductor installation: tree attachment remediation (SH-10) | 2021 | 22431.7113 | 22431.7113 | 0 | 689.0836 | 32.553 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 25 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.3.2 | Covered conductor installation
Grid design and system hardening | 23 | 3.2 | 23-3.2 | 3.2. Covered conductor installation: tree attachment remediation (SH-10) | 2022 | 26377.7612 | 26377.7612 | 0 | 787.5241 | 33.4945 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.3.2 | Covered conductor installation
Grid design and system hardening | 23 | 3.2 | 23-3.2 | 3.2. Covered conductor installation: tree attachment remediation (SH-10) | 2020-2022 plan total | 63992.3731 | 63992.3731 | 0 | 1957.8517 | 32.685 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 27 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.3.2 | Covered conductor installation
Grid design and system hardening | 23 | 3.3 | 23-3.3 | 3.3. Covered conductor installation: alternative technology implementation - vibration dampers (AT-4) | 2019 plan | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 3.3 | 23-3.3 | 3.3. Covered conductor installation: alternative technology implementation - vibration dampers (AT-4) | 2019 actual | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 3.3 | 23-3.3 | 3.3. Covered conductor installation: alternative technology implementation - vibration dampers (AT-4) | 2020 | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 3.3 | 23-3.3 | 3.3. Covered conductor installation: alternative technology implementation - vibration dampers (AT-4) | 2021 | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 3.3 | 23-3.3 | 3.3. Covered conductor installation: alternative technology implementation - vibration dampers (AT-4) | 2022 | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 3.3 | 23-3.3 | 3.3. Covered conductor installation: alternative technology implementation - vibration dampers (AT-4) | 2020-2022 plan total | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Grid design and system hardening | 23 | 4 | 23-4 | 4. Covered conductor maintenance | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 4 | 23-4 | 4. Covered conductor maintenance | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 4 | 23-4 | 4. Covered conductor maintenance | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 4 | 23-4 | 4. Covered conductor maintenance | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 4 | 23-4 | 4. Covered conductor maintenance | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 4 | 23-4 | 4. Covered conductor maintenance | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 5 | 23-5 | 5. Crossarm maintenance, repair, and replacement | 2019 plan | NA | NA | NA | 4714 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 51.3005 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 5 | 23-5 | 5. Crossarm maintenance, repair, and replacement | 2019 actual | NA | NA | NA | 6575 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 26.9372 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 5 | 23-5 | 5. Crossarm maintenance, repair, and replacement | 2020 | NA | NA | NA | 3570 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1309 | 13.8328 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 5 | 23-5 | 5. Crossarm maintenance, repair, and replacement | 2021 | NA | NA | NA | 21 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5837 | 30.5076 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 5 | 23-5 | 5. Crossarm maintenance, repair, and replacement | 2022 | NA | NA | NA | 79 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1013 | 25.7553 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. The numbers in future years are expected to increase as new work is identified from SCE's inspection programs. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 5 | 23-5 | 5. Crossarm maintenance, repair, and replacement | 2020-2022 plan total | NA | NA | NA | 3670 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 6.8159 | 21.2781 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. The numbers in future years are expected to increase as new work is identified from SCE's inspection programs. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 6.1 | 23-6.1 | 6.1. Distribution pole replacement and reinforcement, including with composite poles: composite poles and crossarms (SH-3) | 2019 plan | 5136.4128 | 5136.4128 | 0 | 1100 | 4.6695 | EFF: Other Equipment Types | 0.020945 | 4.0778 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 6.1 | 23-6.1 | 6.1. Distribution pole replacement and reinforcement, including with composite poles: composite poles and crossarms (SH-3) | 2019 actual | NA | NA | NA | 1421 | NA | EFF: Other Equipment Types | 0.027057 | 3.6015 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/ treated line mile" columns are "NA" as the activity is covered in Initiative 3.1, Table 23. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 6.1 | 23-6.1 | 6.1. Distribution pole replacement and reinforcement, including with composite poles: composite poles and crossarms (SH-3) | 2020 | 56832.5745 | 56832.5745 | 0 | 17304.48 | 3.2843 | EFF: Other Equipment Types | 0.20902 | 3.901 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. WCCP scope is 11,700 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 6.1 | 23-6.1 | 6.1. Distribution pole replacement and reinforcement, including with composite poles: composite poles and crossarms (SH-3) | 2021 | 64010.258 | 64010.258 | 0 | 18952.672 | 3.3774 | EFF: Other Equipment Types | 0.21875 | 3.7275 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. WCCP scope is 16,381 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 6.1 | 23-6.1 | 6.1. Distribution pole replacement and reinforcement, including with composite poles: composite poles and crossarms (SH-3) | 2022 | 73642.7252 | 73642.7252 | 0 | 21238.768 | 3.4674 | EFF: Other Equipment Types | 0.23398 | 3.558 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. WCCP scope is 18,721 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 6.1 | 23-6.1 | 6.1. Distribution pole replacement and reinforcement, including with composite poles: composite poles and crossarms (SH-3) | 2020-2022 plan total | 194485.5577 | 194485.5577 | 0 | 57495.92 | 3.3826 | EFF: Other Equipment Types | 0.66175 | 3.7171 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. 2020-2022 WCCP scope is 46,802 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.3.3.1 | Covered conductor installation
Grid design and system hardening | 23 | 6.2 | 23-6.2 | 6.2. Distribution pole replacement and reinforcement, including with composite poles: deteriorated pole | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because SCE did not forecast deteriorated poles in 2019 in the HFRA specifically. | Non-WMP Program | No Forecast | 7.3.3.6. | Distribution pole replacement and reinforcement, including with composite poles
Grid design and system hardening | 23 | 6.2 | 23-6.2 | 6.2. Distribution pole replacement and reinforcement, including with composite poles: deteriorated pole | 2019 actual | 78010.5 | 78010.5 | 0 | 3930 | 19.85 | EFF: Other Equipment Types | 0.069761 | 3.3574 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.6. | Distribution pole replacement and reinforcement, including with composite poles
Grid design and system hardening | 23 | 6.2 | 23-6.2 | 6.2. Distribution pole replacement and reinforcement, including with composite poles: deteriorated pole | 2020 | 64895.818 | 64895.818 | 0 | 3724 | 17.4264 | EFF: Other Equipment Types | 0.040377 | 3.5016 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.6. | Distribution pole replacement and reinforcement, including with composite poles
Grid design and system hardening | 23 | 6.2 | 23-6.2 | 6.2. Distribution pole replacement and reinforcement, including with composite poles: deteriorated pole | 2021 | 30041.011 | 30041.011 | 0 | 1698 | 17.692 | EFF: Other Equipment Types | 0.017841 | 3.3933 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.6. | Distribution pole replacement and reinforcement, including with composite poles
Grid design and system hardening | 23 | 6.2 | 23-6.2 | 6.2. Distribution pole replacement and reinforcement, including with composite poles: deteriorated pole | 2022 | 16506.094 | 16506.094 | 0 | 906 | 18.2186 | EFF: Other Equipment Types | 0.0092342 | 3.2916 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.6. | Distribution pole replacement and reinforcement, including with composite poles
Asset management and inspections | 24 | 3 | 24-3 | 3. Improvement of Inspections | 2020-2022 plan total | 382.576 | 0 | 382.576 | 5681 | 0.067343 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets. | Non-WMP Program | HFRA | 7.3.4.3. | Improvement of inspections
Grid design and system hardening | 23 | 6.3 | 23-6.3 | 6.3. Distribution pole replacement and reinforcement, including with composite poles: poles identified during inspections | 2019 plan | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 6.3 | 23-6.3 | 6.3. Distribution pole replacement and reinforcement, including with composite poles: poles identified during inspections | 2019 actual | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 6.3 | 23-6.3 | 6.3. Distribution pole replacement and reinforcement, including with composite poles: poles identified during inspections | 2020 | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 6.3 | 23-6.3 | 6.3. Distribution pole replacement and reinforcement, including with composite poles: poles identified during inspections | 2021 | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 6.3 | 23-6.3 | 6.3. Distribution pole replacement and reinforcement, including with composite poles: poles identified during inspections | 2022 | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 6.3 | 23-6.3 | 6.3. Distribution pole replacement and reinforcement, including with composite poles: poles identified during inspections | 2020-2022 plan total | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 7 | 23-7 | 7. Expulsion fuse replacement: branch line protection strategy (SH-4) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 17, Table 23. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.7. | Expulsion fuse replacement
Grid design and system hardening | 23 | 7 | 23-7 | 7. Expulsion fuse replacement: branch line protection strategy (SH-4) | 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 17, Table 23 Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.7. | Expulsion fuse replacement
Grid design and system hardening | 23 | 7 | 23-7 | 7. Expulsion fuse replacement: branch line protection strategy (SH-4) | 2020 | 16798.587 | 9053.603 | 7744.984 | 3025 | 5.5533 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.13224 | 8.1174 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.7. | Expulsion fuse replacement
Grid design and system hardening | 23 | 7 | 23-7 | 7. Expulsion fuse replacement: branch line protection strategy (SH-4) | 2021 | 1153.7059 | 0 | 1153.7059 | 421 | 2.7404 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.017856 | 16.019 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.7. | Expulsion fuse replacement
Grid design and system hardening | 23 | 7 | 23-7 | 7. Expulsion fuse replacement: branch line protection strategy (SH-4) | 2022 | 1333.6069 | 0 | 1333.6069 | 481 | 2.7726 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.019809 | 15.5497 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.7. | Expulsion fuse replacement
Grid design and system hardening | 23 | 7 | 23-7 | 7. Expulsion fuse replacement: branch line protection strategy (SH-4) | 2020-2022 plan total | 19285.9 | 9053.603 | 10232.297 | 3927 | 4.9111 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.1699 | 9.0958 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.7. | Expulsion fuse replacement
Grid design and system hardening | 23 | 8.1 | 23-8.1 | 8.1. Grid topology improvements to mitigate or reduce PSPS events: PSPS driven grid hardening work (SH-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | No Forecast | #N/A | TBD
Grid design and system hardening | 23 | 8.1 | 23-8.1 | 8.1. Grid topology improvements to mitigate or reduce PSPS events: PSPS driven grid hardening work (SH-7) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 9, Table 23. | WMP Program | No Forecast | #N/A | TBD
Grid design and system hardening | 23 | 8.1 | 23-8.1 | 8.1. Grid topology improvements to mitigate or reduce PSPS events: PSPS driven grid hardening work (SH-7) | 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 2.8417 | 57.5051 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | No Forecast | #N/A | TBD
Grid design and system hardening | 23 | 8.1 | 23-8.1 | 8.1. Grid topology improvements to mitigate or reduce PSPS events: PSPS driven grid hardening work (SH-7) | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 2.7589 | 61.7133 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | No Forecast | #N/A | TBD
Grid design and system hardening | 23 | 8.1 | 23-8.1 | 8.1. Grid topology improvements to mitigate or reduce PSPS events: PSPS driven grid hardening work (SH-7) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 2.6786 | 65.3369 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | No Forecast | #N/A | TBD
Grid design and system hardening | 23 | 8.1 | 23-8.1 | 8.1. Grid topology improvements to mitigate or reduce PSPS events: PSPS driven grid hardening work (SH-7) | 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 8.2792 | 61.2737 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5. | WMP Program | No Forecast
Grid design and system hardening | 23 | 8.2 | 23-8.2 | 8.2. Grid topology improvements to mitigate or reduce PSPS events: microgrid assessment (PSPS-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | No Forecast | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events
Grid design and system hardening | 23 | 8.2 | 23-8.2 | 8.2. Grid topology improvements to mitigate or reduce PSPS events: microgrid assessment (PSPS-8) | 2019 actual | NA | NA | NA | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | UNKNOWN | NA | NA | In 2019, SCE performed an assessment of Microgrids and the scope will be finalized in the Microgrids OIR filing in February 2020. The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to perform the assessment are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events
Grid design and system hardening | 23 | 8.2 | 23-8.2 | 8.2. Grid topology improvements to mitigate or reduce PSPS events: microgrid assessment (PSPS-8) | 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020. | WMP Program | No Forecast | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events
Grid design and system hardening | 23 | 8.2 | 23-8.2 | 8.2. Grid topology improvements to mitigate or reduce PSPS events: microgrid assessment (PSPS-8) | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020. | WMP Program | No Forecast | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events
Grid design and system hardening | 23 | 8.2 | 23-8.2 | 8.2. Grid topology improvements to mitigate or reduce PSPS events: microgrid assessment (PSPS-8) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020. | WMP Program | No Forecast | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events
Grid design and system hardening | 23 | 8.2 | 23-8.2 | 8.2. Grid topology improvements to mitigate or reduce PSPS events: microgrid assessment (PSPS-8) | 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020. | WMP Program | No Forecast | 7.3.3.8.2 | Grid topology improvements to mitigate or reduce PSPS events
Grid design and system hardening | 23 | 9 | 23-9 | 9. Installation of system automation equipment: installation of system automation equipment - remote controlled automatic reclosers settings update (SH-5) | 2019 plan | 4880.5935 | 4880.5935 | 0 | 50 | 97.6119 | NA | 0.0084341 | 1.7281 | NA | New | NA | GSRPMA, FHPMA | NA | NA | Instead of "Line miles to be treated", number of devices is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.9. | Installation of system automation equipment
Grid design and system hardening | 23 | 9 | 23-9 | 9. Installation of system automation equipment: installation of system automation equipment - remote controlled automatic reclosers settings update (SH-5) | 2019 actual | 11110.4579 | 11110.4579 | 0 | 76 | 146.1902 | NA | 0.01282 | 1.1539 | NA | New | NA | GSRPMA, FHPMA | NA | NA | Instead of "Line miles to be treated", number of devices is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.9. | Installation of system automation equipment
Grid design and system hardening | 23 | 9 | 23-9 | 9. Installation of system automation equipment: installation of system automation equipment - remote controlled automatic reclosers settings update (SH-5) | 2020 | 8639.9018 | 8480.5953 | 159.3066 | 98 | 88.1623 | NA | 0.016049 | 1.929 | NA | New | NA | GSRPMA, FHPMA | NA | NA | The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.9. | Installation of system automation equipment
Grid design and system hardening | 23 | 9 | 23-9 | 9. Installation of system automation equipment: installation of system automation equipment - remote controlled automatic reclosers settings update (SH-5) | 2021 | 0 | 0 | 0 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | UNKNOWN | NA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because there is no sectionalizing device specific program beyond what was defined in GSRP | WMP Program | HFRA | 7.3.3.9. | Installation of system automation equipment
Grid design and system hardening | 23 | 9 | 23-9 | 9. Installation of system automation equipment: installation of system automation equipment - remote controlled automatic reclosers settings update (SH-5) | 2022 | 0 | 0 | 0 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | UNKNOWN | NA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because there is no sectionalizing device specific program beyond what was defined in GSRP | WMP Program | HFRA | 7.3.3.9. | Installation of system automation equipment
Grid design and system hardening | 23 | 9 | 23-9 | 9. Installation of system automation equipment: installation of system automation equipment - remote controlled automatic reclosers settings update (SH-5) | 2020-2022 plan total | 8639.9018 | 8480.5953 | 159.3066 | 98 | 88.1623 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA, FHPMA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because there is no sectionalizing device specific program beyond what was defined in GSRP | WMP Program | HFRA | 7.3.3.9. | Installation of system automation equipment
Grid design and system hardening | 23 | 10 | 23-10 | 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2019 plan | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 10 | 23-10 | 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2019 actual | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 10 | 23-10 | 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2020 | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 10 | 23-10 | 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2021 | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 10 | 23-10 | 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2022 | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 10 | 23-10 | 10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2020-2022 plan total | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 11 | 23-11 | 11. Mitigation of impact on customers and other residents affected during PSPS event | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 11 | 23-11 | 11. Mitigation of impact on customers and other residents affected during PSPS event | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 11 | 23-11 | 11. Mitigation of impact on customers and other residents affected during PSPS event | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 11 | 23-11 | 11. Mitigation of impact on customers and other residents affected during PSPS event | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 11 | 23-11 | 11. Mitigation of impact on customers and other residents affected during PSPS event | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 11 | 23-11 | 11. Mitigation of impact on customers and other residents affected during PSPS event | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 12 | 23-12 | 12. Other corrective action | 2019 plan | NA | NA | NA | 29067 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 12 | 23-12 | 12. Other corrective action | 2019 actual | NA | NA | NA | 36180 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 12 | 23-12 | 12. Other corrective action | 2020 | NA | NA | NA | 5001 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 12 | 23-12 | 12. Other corrective action | 2021 | NA | NA | NA | 275 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 12 | 23-12 | 12. Other corrective action | 2022 | NA | NA | NA | 4972 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 12 | 23-12 | 12. Other corrective action | 2020-2022 plan total | NA | NA | NA | 10248 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 12.1 | 23-12.1 | 12.1. Other corrective action: distribution remediations (SH-12.1) | 2019 plan | 191737.288 | 102808.058 | 88929.23 | NA | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 51.3005 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.1 | 23-12.1 | 12.1. Other corrective action: distribution remediations (SH-12.1) | 2019 actual | 394728.731 | 229991.525 | 164737.206 | 49783 | 7.929 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 26.9372 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.1 | 23-12.1 | 12.1. Other corrective action: distribution remediations (SH-12.1) | 2020 | 327535.32 | 147130.025 | 180405.295 | 58617 | 5.5877 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1309 | 13.8328 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.1 | 23-12.1 | 12.1. Other corrective action: distribution remediations (SH-12.1) | 2021 | 125039.955 | 46436.115 | 78603.84 | 28225 | 4.4301 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5837 | 30.5076 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.1 | 23-12.1 | 12.1. Other corrective action: distribution remediations (SH-12.1) | 2022 | 85021.209 | 29742.715 | 55278.494 | 17793 | 4.7784 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1013 | 25.7553 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.1 | 23-12.1 | 12.1. Other corrective action: distribution remediations (SH-12.1) | 2020-2022 plan total | 537596.484 | 223308.855 | 314287.629 | 104635 | 5.1378 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 6.8159 | 21.2781 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1 | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.2 | 23-12.2 | 12.2. Other corrective action: transmission remediations (SH-12.2) | 2019 plan | 28947.348 | 9911.729 | 19035.619 | NA | NA | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.11797 | 3.3835 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1 | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Grid design and system hardening | 23 | 12.2 | 23-12.2 | 12.2. Other corrective action: transmission remediations (SH-12.2) | 2019 actual | 83879.5404 | 54146.98 | 29732.5604 | 10000 | 8.388 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 1.5237 | 13.5585 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1 | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Grid design and system hardening | 23 | 12.2 | 23-12.2 | 12.2. Other corrective action: transmission remediations (SH-12.2) | 2020 | 71320.128 | 64895.987 | 6424.141 | 5222 | 13.6576 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.031263 | 0.53918 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1 | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Grid design and system hardening | 23 | 12.2 | 23-12.2 | 12.2. Other corrective action: transmission remediations (SH-12.2) | 2021 | 12413.696 | 8838.793 | 3574.903 | 2026.1685 | 6.1267 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.030243 | 2.9172 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1 | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Grid design and system hardening | 23 | 12.2 | 23-12.2 | 12.2. Other corrective action: transmission remediations (SH-12.2) | 2022 | 10246.413 | 7262.283 | 2984.13 | 1833.7685 | 5.5876 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.025122 | 3.0555 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1 | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Grid design and system hardening | 23 | 12.2 | 23-12.2 | 12.2. Other corrective action: transmission remediations (SH-12.2) | 2020-2022 plan total | 93980.237 | 80997.063 | 12983.174 | 9081.9371 | 10.348 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.086627 | 1.1313 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1 | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Grid design and system hardening | 23 | 12.3 | 23-12.3 | 12.3. Other corrective action: generation remediations (SH-12.3) | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because inspections started in March 2019 and did not plan for remediations. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.3 | 23-12.3 | 12.3. Other corrective action: generation remediations (SH-12.3) | 2019 actual | 387.907 | 0 | 387.907 | UNKNOWN | NA | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure. The number of notifications in the HFRA is unavailable for 2019. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.3 | 23-12.3 | 12.3. Other corrective action: generation remediations (SH-12.3) | 2020 | 200 | 40 | 160 | 200 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.3 | 23-12.3 | 12.3. Other corrective action: generation remediations (SH-12.3) | 2021 | 200 | 40 | 160 | 200 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.3 | 23-12.3 | 12.3. Other corrective action: generation remediations (SH-12.3) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 12.3 | 23-12.3 | 12.3. Other corrective action: generation remediations (SH-12.3) | 2020-2022 plan total | 400 | 80 | 320 | 400 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Grid design and system hardening | 23 | 13 | 23-13 | 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend", "Line miles to be treated" and "Spend/ treated line mile" columns are "NA" because SCE did not forecast specific HFRA pole loading program poles in 2019. | Non-WMP Program | No Forecast | 7.3.3.13. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid design and system hardening | 23 | 13 | 23-13 | 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2019 actual | 89444.1 | 89444.1 | 0 | 4506 | 19.85 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure. | Non-WMP Program | HFRA | 7.3.3.13. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid design and system hardening | 23 | 13 | 23-13 | 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2020 | 45097.094 | 45097.094 | 0 | 2588 | 17.4255 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure. | Non-WMP Program | HFRA | 7.3.3.13. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid design and system hardening | 23 | 13 | 23-13 | 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2021 | 15475.673 | 15475.673 | 0 | 874 | 17.7067 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure. | Non-WMP Program | HFRA | 7.3.3.13. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid design and system hardening | 23 | 13 | 23-13 | 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2022 | 29344.168 | 29344.168 | 0 | 1612 | 18.2036 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure. | Non-WMP Program | HFRA | 7.3.3.13. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Vegetation management and inspections | 25 | 13 | 25-13 | 13. Quality assurance / quality control of inspections: quality control (VM-5) | 2020-2022 plan total | 14000 | 0 | 14000 | 24300 | 0.57613 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | Combined | 7.3.5.13. | Quality assurance / quality control of vegetation inspections
Grid design and system hardening | 23 | 14 | 23-14 | 14. Transformers maintenance and replacement | 2019 plan | 2733.0178 | 2678.3574 | 54.6604 | 1503 | 1.8184 | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.14. | Transformers maintenance and replacement
Grid design and system hardening | 23 | 14 | 23-14 | 14. Transformers maintenance and replacement | 2019 actual | NA | NA | NA | 1737 | NA | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.14. | Transformers maintenance and replacement
Grid design and system hardening | 23 | 14 | 23-14 | 14. Transformers maintenance and replacement | 2020 | 2598.0201 | 2546.0597 | 51.9604 | 1885 | 1.3783 | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.14. | Transformers maintenance and replacement
Grid design and system hardening | 23 | 14 | 23-14 | 14. Transformers maintenance and replacement | 2021 | 2466.8506 | 2417.5136 | 49.337 | UNKNOWN | UNKNOWN | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Line miles to be treated" and "Spend/treated line mile" columns for 2021 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.14. | Transformers maintenance and replacement
Grid design and system hardening | 23 | 14 | 23-14 | 14. Transformers maintenance and replacement | 2022 | 2504.398 | 2454.31 | 50.088 | UNKNOWN | UNKNOWN | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Line miles to be treated" and "Spend/treated line mile" columns for 2022 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.14. | Transformers maintenance and replacement
Vegetation management and inspections | 25 | 19 | 25-19 | 19. Vegetation inventory system | 2020-2022 plan total | 7771 | 5911 | 1860 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.19. | Vegetation inventory system
Grid design and system hardening | 23 | 15 | 23-15 | 15. Transmission tower maintenance and replacement | 2019 plan | 5658 | 0 | 5658 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.15. | Transmission tower maintenance and replacement
Grid design and system hardening | 23 | 15 | 23-15 | 15. Transmission tower maintenance and replacement | 2019 actual | 3978 | 0 | 3978 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.15. | Transmission tower maintenance and replacement
Grid design and system hardening | 23 | 15 | 23-15 | 15. Transmission tower maintenance and replacement | 2020 | 5558 | 0 | 5558 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.15. | Transmission tower maintenance and replacement
Grid design and system hardening | 23 | 15 | 23-15 | 15. Transmission tower maintenance and replacement | 2021 | 5679.1644 | 0 | 5679.1644 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.15. | Transmission tower maintenance and replacement
Grid design and system hardening | 23 | 15 | 23-15 | 15. Transmission tower maintenance and replacement | 2022 | 5838.181 | 0 | 5838.181 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.15. | Transmission tower maintenance and replacement
Grid operations and protocols | 26 | 5.8 | 26-5.8 | 5.8. PSPS events and mitigation of PSPS impacts: SGIP resiliency | 2020-2022 plan total | 139840 | NA | NA | 7345 | 19.0388 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.6.1.4.2.3
Grid design and system hardening | 23 | 16 | 23-16 | 16. Undergrounding of electric lines and/or equipment: undergrounding overhead conductor (SH-2) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.3.16. | Undergrounding of electric lines and/or equipment
Grid design and system hardening | 23 | 16 | 23-16 | 16. Undergrounding of electric lines and/or equipment: undergrounding overhead conductor (SH-2) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Columns are "NA" because undergrounding to start in 2021. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.16. | Undergrounding of electric lines and/or equipment
Grid design and system hardening | 23 | 16 | 23-16 | 16. Undergrounding of electric lines and/or equipment: undergrounding overhead conductor (SH-2) | 2020 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | New | NA | WMPMA | NA | NA | Columns are "NA" because undergrounding to start in 2021. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.16. | Undergrounding of electric lines and/or equipment
Grid design and system hardening | 23 | 16 | 23-16 | 16. Undergrounding of electric lines and/or equipment: undergrounding overhead conductor (SH-2) | 2021 | 22507.486 | 22507.486 | 0 | 6 | 3751.2477 | CFO: All EFF: All | 0.1017 | 4.8431 | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.16. | Undergrounding of electric lines and/or equipment
Grid design and system hardening | 23 | 16 | 23-16 | 16. Undergrounding of electric lines and/or equipment: undergrounding overhead conductor (SH-2) | 2022 | 42457.2637 | 42457.2637 | 0 | 11 | 3859.7512 | CFO: All EFF: All | 0.18097 | 4.7005 | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.16. | Undergrounding of electric lines and/or equipment
Grid design and system hardening | 23 | 16 | 23-16 | 16. Undergrounding of electric lines and/or equipment: undergrounding overhead conductor (SH-2) | 2020-2022 plan total | 64964.7496 | 64964.7496 | 0 | 17 | 3821.4559 | CFO: All EFF: All | 0.28267 | 4.7508 | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.16. | Undergrounding of electric lines and/or equipment
Grid design and system hardening | 23 | 17 | 23-17 | 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2019 plan | 46122.0545 | 46122.0545 | 0 | 7511 | 6.1406 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 2.2463 | 48.7041 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 17 | 23-17 | 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2019 actual | 70549.876 | 70292.689 | 257.187 | 7765 | 9.0856 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 2.2809 | 32.3308 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 17 | 23-17 | 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 17 | 23-17 | 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 17 | 23-17 | 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 17 | 23-17 | 17. Updates to grid topology to minimize risk of ignition in HFTDs | 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Grid design and system hardening | 23 | 18 | 23-18 | 18. Transmission overhead (TOH) review (SH-9) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | No Forecast | #N/A | N/A
Grid design and system hardening | 23 | 18 | 23-18 | 18. Transmission overhead (TOH) review (SH-9) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | No Forecast | #N/A | N/A
Grid design and system hardening | 23 | 18 | 23-18 | 18. Transmission overhead (TOH) review (SH-9) | 2020 | NA | NA | NA | 4352 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is blank because the cost will hit overhead, so there will be no memo account treatment The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid design and system hardening | 23 | 18 | 23-18 | 18. Transmission overhead (TOH) review (SH-9) | 2021 | NA | NA | NA | 4352 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid design and system hardening | 23 | 18 | 23-18 | 18. Transmission overhead (TOH) review (SH-9) | 2022 | NA | NA | NA | 4352 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is blank because the cost will hit overhead, so there will be no memo account treatment The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid design and system hardening | 23 | 18 | 23-18 | 18. Transmission overhead (TOH) review (SH-9) | 2020-2022 plan total | NA | NA | NA | 13056 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is blank because the cost will hit overhead, so there will be no memo account treatment The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast
Grid design and system hardening | 23 | 19 | 23-19 | 19. Legacy facilities (SH-11) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs
Grid design and system hardening | 23 | 19 | 23-19 | 19. Legacy facilities (SH-11) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs
Grid design and system hardening | 23 | 19 | 23-19 | 19. Legacy facilities (SH-11) | 2020 | 2173.733 | 1304.24 | 869.493 | 3 | 724.5775 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs
Grid design and system hardening | 23 | 19 | 23-19 | 19. Legacy facilities (SH-11) | 2021 | 4912.135 | 4686.226 | 225.909 | 6 | 818.6892 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs
Grid design and system hardening | 23 | 19 | 23-19 | 19. Legacy facilities (SH-11) | 2022 | 4177.642 | 3985.513 | 192.129 | 6 | 696.2737 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs
Grid design and system hardening | 23 | 19 | 23-19 | 19. Legacy facilities (SH-11) | 2020-2022 plan total | 11263.51 | 9975.979 | 1287.531 | 15 | 750.9007 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. . The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.3.17.2 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset management and inspections | 24 | 1 | 24-1 | 1. Detailed inspections of distribution electric lines and equipment: distribution HFRA detailed inspections (previously ODI) | 2019 plan | 814.286 | 0 | 814.286 | 54551 | 0.014927 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.1. | Detailed inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 1 | 24-1 | 1. Detailed inspections of distribution electric lines and equipment: distribution HFRA detailed inspections (previously ODI) | 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile columns are "NA" as those are included in Initiative 9.1, Table 24 | Non-WMP Program | HFRA | 7.3.4.1. | Detailed inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 1 | 24-1 | 1. Detailed inspections of distribution electric lines and equipment: distribution HFRA detailed inspections (previously ODI) | 2020 | 2276.0632 | 0 | 2276.0632 | 54959 | 0.041414 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.1. | Detailed inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 1 | 24-1 | 1. Detailed inspections of distribution electric lines and equipment: distribution HFRA detailed inspections (previously ODI) | 2021 | 2983.4434 | 0 | 2983.4434 | 69743 | 0.042778 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.1. | Detailed inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 1 | 24-1 | 1. Detailed inspections of distribution electric lines and equipment: distribution HFRA detailed inspections (previously ODI) | 2022 | 2631.2872 | 0 | 2631.2872 | 59681 | 0.044089 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.1. | Detailed inspections of distribution electric lines and equipment
Data governance | 27 | 1 | 27-1 | 1. Centralized repository for data | 2020-2022 plan total | 38791.243 | 36083.284 | 2707.959 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed. | Non-WMP Program | HFRA | 7.3.7.1. | Centralized repository for data
Asset management and inspections | 24 | 2 | 24-2 | 2. Detailed inspections of Transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile columns are "NA" as those are included in Initiative 10.1, Table 24 | Non-WMP Program | HFRA | 7.3.4.2. | Detailed inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 2 | 24-2 | 2. Detailed inspections of Transmission electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile columns are "NA" as those are included in Initiative 10.1, Table 24 | Non-WMP Program | HFRA | 7.3.4.2. | Detailed inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 2 | 24-2 | 2. Detailed inspections of Transmission electric lines and equipment | 2020 | 1149.8967 | 0 | 1149.8967 | 12011 | 0.095737 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.2. | Detailed inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 2 | 24-2 | 2. Detailed inspections of Transmission electric lines and equipment | 2021 | 1192.2138 | 0 | 1192.2138 | 13935 | 0.085555 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.2. | Detailed inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 2 | 24-2 | 2. Detailed inspections of Transmission electric lines and equipment | 2022 | 1059.1106 | 0 | 1059.1106 | 12011 | 0.088178 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.2. | Detailed inspections of transmission electric lines and equipment
Situational awareness and forecasting | 22 | 3 | 22-3 | 3. Fault indicators for detecting faults on electric lines and equipment | 2020-2022 plan total | 6694.794 | 6694.794 | 0 | 414 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | Combined | 7.3.2.3. | Fault indicators for detecting faults on electric lines and equipment
Asset management and inspections | 24 | 3 | 24-3 | 3. Improvement of Inspections | 2019 plan | 467.825 | 0 | 467.825 | 5681 | 0.082349 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets. | Non-WMP Program | HFRA | 7.3.4.3. | Improvement of inspections
Asset management and inspections | 24 | 3 | 24-3 | 3. Improvement of Inspections | 2019 actual | 467.825 | 0 | 467.825 | 5681 | 0.082349 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets. | Non-WMP Program | HFRA | 7.3.4.3. | Improvement of inspections
Asset management and inspections | 24 | 3 | 24-3 | 3. Improvement of Inspections | 2020 | 382.576 | 0 | 382.576 | 5681 | 0.067343 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets. | Non-WMP Program | HFRA | 7.3.4.3. | Improvement of inspections
Asset management and inspections | 24 | 3 | 24-3 | 3. Improvement of Inspections | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | 5681 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | The "Total per-initiative spend" is "UNKNOWN" as the scope for 2021 is still to be determined. Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets. | Non-WMP Program | HFRA | 7.3.4.3. | Improvement of inspections
Asset management and inspections | 24 | 3 | 24-3 | 3. Improvement of Inspections | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | 5681 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | The "Total per-initiative spend" is "UNKNOWN" as the scope for 2022 is still to be determined. Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets. | Non-WMP Program | HFRA | 7.3.4.3. | Improvement of inspections
Grid design and system hardening | 23 | 1 | 23-1 | 1. Capacitor maintenance and replacement program | 2020-2022 plan total | 12490.624 | 12240.812 | 249.812 | 58 | NA | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.1. | Capacitor maintenance and replacement program
Asset management and inspections | 24 | 4 | 24-4 | 4. Infrared inspections of distribution electric lines and equipment: infrared inspection of energized overhead distribution facilities and equipment (IN-3) | 2019 plan | 465.807 | 0 | 465.807 | 4911.9535 | 0.094831 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0046894 | 10.0673 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.4.4. | Infrared inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 4 | 24-4 | 4. Infrared inspections of distribution electric lines and equipment: infrared inspection of energized overhead distribution facilities and equipment (IN-3) | 2019 actual | NA | NA | NA | NA | NA | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0046894 | 0 | NA | NA | NA | NA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The "Total per initiative spend" column is "NA" because the 2019 actuals are included in initiative 9.1, table 24 The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.4.4. | Infrared inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 4 | 24-4 | 4. Infrared inspections of distribution electric lines and equipment: infrared inspection of energized overhead distribution facilities and equipment (IN-3) | 2020 | 400.752 | 0 | 400.752 | 4058 | 0.098756 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0018798 | 4.796 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.4.4. | Infrared inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 4 | 24-4 | 4. Infrared inspections of distribution electric lines and equipment: infrared inspection of energized overhead distribution facilities and equipment (IN-3) | 2021 | 405.6813 | 0 | 405.6813 | 4510 | 0.089952 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0020282 | 5.1747 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.4.4. | Infrared inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 4 | 24-4 | 4. Infrared inspections of distribution electric lines and equipment: infrared inspection of energized overhead distribution facilities and equipment (IN-3) | 2022 | 410.3229 | 0 | 410.3229 | 4510 | 0.090981 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0019691 | 5.0238 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.4.4. | Infrared inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 4 | 24-4 | 4. Infrared inspections of distribution electric lines and equipment: infrared inspection of energized overhead distribution facilities and equipment (IN-3) | 2020-2022 plan total | 1216.7561 | 0 | 1216.7561 | 13078 | 0.093038 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0058771 | 4.9982 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.4.4. | Infrared inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 5 | 24-5 | 5. Infrared inspections of transmission electric lines and equipment: infrared inspection, corona scanning, and high definition imagery of energized overhead transmission facilities and equipment (IN-4) | 2019 plan | 5669.26 | 0 | 5669.26 | 1000 | 5.6693 | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | NA | WMP Program | HFRA | 7.3.4.5. | Infrared inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 5 | 24-5 | 5. Infrared inspections of transmission electric lines and equipment: infrared inspection, corona scanning, and high definition imagery of energized overhead transmission facilities and equipment (IN-4) | 2019 actual | NA | NA | NA | NA | NA | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | NA | NA | NA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The "Total per initiative spend" column is "NA" because the 2019 actuals are included in initiative 10.1, table 24 | WMP Program | HFRA | 7.3.4.5. | Infrared inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 5 | 24-5 | 5. Infrared inspections of transmission electric lines and equipment: infrared inspection, corona scanning, and high definition imagery of energized overhead transmission facilities and equipment (IN-4) | 2020 | 3503.6115 | 0 | 3503.6115 | 1000 | 3.5036 | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | NA | WMP Program | HFRA | 7.3.4.5. | Infrared inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 5 | 24-5 | 5. Infrared inspections of transmission electric lines and equipment: infrared inspection, corona scanning, and high definition imagery of energized overhead transmission facilities and equipment (IN-4) | 2021 | 3533.6033 | 0 | 3533.6033 | UNKNOWN | UNKNOWN | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Line miles to be treated” and "Spend/treated line mile" columns are "UNKNOWN" for 2021 because there are no miles estimated at this time | WMP Program | HFRA | 7.3.4.5. | Infrared inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 5 | 24-5 | 5. Infrared inspections of transmission electric lines and equipment: infrared inspection, corona scanning, and high definition imagery of energized overhead transmission facilities and equipment (IN-4) | 2022 | 3564.017 | 0 | 3564.017 | UNKNOWN | UNKNOWN | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Line miles to be treated” and "Spend/treated line mile" columns are "UNKNOWN" for 2022 because there are no miles estimated at this time | WMP Program | HFRA | 7.3.4.5. | Infrared inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 5 | 24-5 | 5. Infrared inspections of transmission electric lines and equipment: infrared inspection, corona scanning, and high definition imagery of energized overhead transmission facilities and equipment (IN-4) | 2020-2022 plan total | 10601.2319 | 0 | 10601.2319 | NA | NA | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2021 and 2022 because there are no miles estimated at this time | WMP Program | HFRA | 7.3.4.5. | Infrared inspections of transmission electric lines and equipment
Asset management and inspections | 24 | 6 | 24-6 | 6. Intrusive pole inspections (IPI) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as there was no 2019 plan for this initiative | Non-WMP Program | HFRA | 7.3.4.6. | Intrusive pole inspections
Asset management and inspections | 24 | 6 | 24-6 | 6. Intrusive pole inspections (IPI) | 2019 actual | 892.687 | 0 | 892.687 | 21464 | 0.04159 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years. | Non-WMP Program | HFRA | 7.3.4.6. | Intrusive pole inspections
Asset management and inspections | 24 | 6 | 24-6 | 6. Intrusive pole inspections (IPI) | 2020 | 1302 | 0 | 1302 | 30156 | 0.043175 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years. | Non-WMP Program | HFRA | 7.3.4.6. | Intrusive pole inspections
Asset management and inspections | 24 | 6 | 24-6 | 6. Intrusive pole inspections (IPI) | 2021 | 1320 | 0 | 1320 | 30156 | 0.043772 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years. | Non-WMP Program | HFRA | 7.3.4.6. | Intrusive pole inspections
Asset management and inspections | 24 | 6 | 24-6 | 6. Intrusive pole inspections (IPI) | 2022 | 1342 | 0 | 1342 | 30156 | 0.044502 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years. | Non-WMP Program | HFRA | 7.3.4.6. | Intrusive pole inspections
Grid design and system hardening | 23 | 2.6 | 23-2.6 | 2.6. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker installs/ replacements | 2020-2022 plan total | 9574.8815 | 9574.8815 | 0 | 66 | 145.074 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Asset management and inspections | 24 | 7 | 24-7 | 7. LiDAR inspections of distribution electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 7 | 24-7 | 7. LiDAR inspections of distribution electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 7 | 24-7 | 7. LiDAR inspections of distribution electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 7 | 24-7 | 7. LiDAR inspections of distribution electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 7 | 24-7 | 7. LiDAR inspections of distribution electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 7 | 24-7 | 7. LiDAR inspections of distribution electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 8 | 24-8 | 8. LiDAR inspections of transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 8 | 24-8 | 8. LiDAR inspections of transmission electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 8 | 24-8 | 8. LiDAR inspections of transmission electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 8 | 24-8 | 8. LiDAR inspections of transmission electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 8 | 24-8 | 8. LiDAR inspections of transmission electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 8 | 24-8 | 8. LiDAR inspections of transmission electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 9.1 | 24-9.1 | 9.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: distribution high fire risk-informed inspections (IN-1.1) | 2019 plan | 53897.2487 | 0 | 53897.2487 | 380000 | 0.14183 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 51.3005 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.1 | 24-9.1 | 9.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: distribution high fire risk-informed inspections (IN-1.1) | 2019 actual | 72644.5017 | 0 | 72644.5017 | 380000 | 0.19117 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 26.9372 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The spend for 2019 includes both ground and aerial inspections (Initiative 9.2, Table 24). Instead of "Line miles to be treated", number of assets is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.1 | 24-9.1 | 9.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: distribution high fire risk-informed inspections (IN-1.1) | 2020 | 2276.0632 | 0 | 2276.0632 | 54959 | 0.041414 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1309 | 13.8328 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.1 | 24-9.1 | 9.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: distribution high fire risk-informed inspections (IN-1.1) | 2021 | 2983.4434 | 0 | 2983.4434 | 69743 | 0.042778 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5837 | 30.5076 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.1 | 24-9.1 | 9.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: distribution high fire risk-informed inspections (IN-1.1) | 2022 | 2631.2872 | 0 | 2631.2872 | 59681 | 0.044089 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1013 | 25.7553 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.1 | 24-9.1 | 9.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: distribution high fire risk-informed inspections (IN-1.1) | 2020-2022 plan total | 7890.7938 | 0 | 7890.7938 | 184383 | 0.042796 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 6.8159 | 21.2781 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.1.1 | 24-9.1.1 | 9.1.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: asset defect detection using machine learning object detection (AT-5) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.1.1 | 24-9.1.1 | 9.1.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: asset defect detection using machine learning object detection (AT-5) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.1.1 | 24-9.1.1 | 9.1.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: asset defect detection using machine learning object detection (AT-5) | 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.1.1 | 24-9.1.1 | 9.1.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: asset defect detection using machine learning object detection (AT-5) | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.1.1 | 24-9.1.1 | 9.1.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: asset defect detection using machine learning object detection (AT-5) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.1.1 | 24-9.1.1 | 9.1.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: asset defect detection using machine learning object detection (AT-5) | 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.2 | 24-9.2 | 9.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections (IN-6.1) | 2019 plan | NA | NA | NA | NA | NA | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5664 | 35.629 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 9.1, Table 24. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.2 | 24-9.2 | 9.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections (IN-6.1) | 2019 actual | NA | NA | NA | NA | NA | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5664 | 0 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 9.1, Table 24. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.2 | 24-9.2 | 9.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections (IN-6.1) | 2020 | 40059.1628 | 0 | 40059.1628 | 255000 | 0.15709 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1668 | 10.5529 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.2 | 24-9.2 | 9.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections (IN-6.1) | 2021 | 26193.2359 | 0 | 26193.2359 | 165000 | 0.15875 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 1.3221 | 21.1049 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.2 | 24-9.2 | 9.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections (IN-6.1) | 2022 | 26492.925 | 0 | 26492.925 | 165000 | 0.16056 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 1.2618 | 49.8605 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.2 | 24-9.2 | 9.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections (IN-6.1) | 2020-2022 plan total | 92745.3238 | 0 | 92745.3238 | 585000 | 0.15854 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 4.7506 | 16.1986 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure. | WMP Program | HFRA | 7.3.4.9.1 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 9.2.1 | 24-9.2.1 | 9.2.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: unmanned aerial vehicles (UAV) (AT-2.2) | 2019 plan | 461.3691 | 0 | 461.3691 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. Instead of ""Line miles to be treated"", all T&D overhead circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.2.1 | 24-9.2.1 | 9.2.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: unmanned aerial vehicles (UAV) (AT-2.2) | 2019 actual | 1.0479 | 0 | 1.0479 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Total per initiative spend" column is not final due to work performed in 2019 and not yet billed. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.2.1 | 24-9.2.1 | 9.2.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: unmanned aerial vehicles (UAV) (AT-2.2) | 2020 | 413.0213 | 0 | 413.0213 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.2.1 | 24-9.2.1 | 9.2.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: unmanned aerial vehicles (UAV) (AT-2.2) | 2021 | 358.4573 | 0 | 358.4573 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.2.1 | 24-9.2.1 | 9.2.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: unmanned aerial vehicles (UAV) (AT-2.2) | 2022 | 335.6847 | 0 | 335.6847 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.2.1 | 24-9.2.1 | 9.2.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: unmanned aerial vehicles (UAV) (AT-2.2) | 2020-2022 plan total | 1107.1633 | 0 | 1107.1633 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 9.2.2 | 24-9.2.2 | 9.2.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: UAS operations training (OP-3) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Asset management and inspections | 24 | 9.2.2 | 24-9.2.2 | 9.2.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: UAS operations training (OP-3) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Asset management and inspections | 24 | 9.2.2 | 24-9.2.2 | 9.2.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: UAS operations training (OP-3) | 2020 | 271.0301 | 0 | 271.0301 | 50 | 5.4206 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Asset management and inspections | 24 | 9.2.2 | 24-9.2.2 | 9.2.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: UAS operations training (OP-3) | 2021 | 840.7872 | 0 | 840.7872 | 80 | 10.5098 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Asset management and inspections | 24 | 9.2.2 | 24-9.2.2 | 9.2.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: UAS operations training (OP-3) | 2022 | 245.4147 | 0 | 245.4147 | 50 | 4.9083 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Asset management and inspections | 24 | 9.2.2 | 24-9.2.2 | 9.2.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: UAS operations training (OP-3) | 2020-2022 plan total | 1357.232 | 0 | 1357.232 | 180 | 7.5402 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Asset management and inspections | 24 | 10.1 | 24-10.1 | 10.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: transmission risk-informed inspections in HFRA (IN-1.2) | 2019 plan | 5917.957 | 0 | 5917.957 | 51179 | 0.11563 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.11797 | 3.3835 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.1 | 24-10.1 | 10.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: transmission risk-informed inspections in HFRA (IN-1.2) | 2019 actual | 28499.1157 | 0 | 28499.1157 | 41952 | 0.67933 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 1.5237 | 13.5585 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The spend for 2019 includes both ground and aerial inspections (Initiative 10.2, Table 24). Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.1 | 24-10.1 | 10.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: transmission risk-informed inspections in HFRA (IN-1.2) | 2020 | 1149.8967 | 0 | 1149.8967 | 10489 | 0.10963 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.031263 | 0.53918 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.1 | 24-10.1 | 10.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: transmission risk-informed inspections in HFRA (IN-1.2) | 2021 | 1192.2138 | 0 | 1192.2138 | 13935 | 0.085555 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.030243 | 2.9172 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.1 | 24-10.1 | 10.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: transmission risk-informed inspections in HFRA (IN-1.2) | 2022 | 1059.1106 | 0 | 1059.1106 | 12011 | 0.088178 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.025122 | 3.0555 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.1 | 24-10.1 | 10.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: transmission risk-informed inspections in HFRA (IN-1.2) | 2020-2022 plan total | 3401.2211 | 0 | 3401.2211 | 36435 | 0.09335 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.086627 | 1.1313 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.2 | 24-10.2 | 10.2. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections - transmission (IN-6.2) | 2019 plan | NA | NA | NA | NA | NA | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | NA | NA | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 10.1, Table 24. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.2 | 24-10.2 | 10.2. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections - transmission (IN-6.2) | 2019 actual | NA | NA | NA | NA | NA | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | NA | NA | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 10.1, Table 24. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.2 | 24-10.2 | 10.2. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections - transmission (IN-6.2) | 2020 | 11868.6198 | 0 | 11868.6198 | 33500 | 0.35429 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.020154 | 0.83127 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.2 | 24-10.2 | 10.2. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections - transmission (IN-6.2) | 2021 | 11970.218 | 0 | 11970.218 | 33500 | 0.35732 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.019434 | 1.3588 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.2 | 24-10.2 | 10.2. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections - transmission (IN-6.2) | 2022 | 12073.2458 | 0 | 12073.2458 | 33500 | 0.3604 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.018739 | 1.3326 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.2 | 24-10.2 | 10.2. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections - transmission (IN-6.2) | 2020-2022 plan total | 35912.0836 | 0 | 35912.0836 | 100500 | 0.35733 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.058327 | 1.1087 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure. | WMP Program | HFRA | 7.3.4.10. | Other discretionary inspection of transmission electric lines and
Asset management and inspections | 24 | 10.2.1 | 24-10.2.1 | 10.2.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: assessment of partial discharge for transmission facilities (AT-6) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 10.2.1 | 24-10.2.1 | 10.2.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: assessment of partial discharge for transmission facilities (AT-6) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 10.2.1 | 24-10.2.1 | 10.2.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: assessment of partial discharge for transmission facilities (AT-6) | 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 10.2.1 | 24-10.2.1 | 10.2.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: assessment of partial discharge for transmission facilities (AT-6) | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 10.2.1 | 24-10.2.1 | 10.2.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: assessment of partial discharge for transmission facilities (AT-6) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 10.2.1 | 24-10.2.1 | 10.2.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: assessment of partial discharge for transmission facilities (AT-6) | 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time. | WMP Program | No Forecast | 7.1.D | Alternative Technologies
Asset management and inspections | 24 | 11 | 24-11 | 11. Patrol inspections of distribution electric lines and equipment | 2019 plan | 0 | 0 | 0 | 7352 | 0 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.11. | Patrol inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 11 | 24-11 | 11. Patrol inspections of distribution electric lines and equipment | 2019 actual | 0 | 0 | 0 | 7352 | 0 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.11. | Patrol inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 11 | 24-11 | 11. Patrol inspections of distribution electric lines and equipment | 2020 | 1200 | 0 | 1200 | 7352 | 0.16322 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.11. | Patrol inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 11 | 24-11 | 11. Patrol inspections of distribution electric lines and equipment | 2021 | 1012 | 0 | 1012 | 7352 | 0.13765 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.11. | Patrol inspections of distribution electric lines and equipment
Asset management and inspections | 24 | 11 | 24-11 | 11. Patrol inspections of distribution electric lines and equipment | 2022 | 1039 | 0 | 1039 | 7352 | 0.14132 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.11. | Patrol inspections of distribution electric lines and equipment
Grid design and system hardening | 23 | 6.2 | 23-6.2 | 6.2. Distribution pole replacement and reinforcement, including with composite poles: deteriorated pole | 2020-2022 plan total | 111442.923 | 111442.923 | 0 | 6328 | 17.6111 | EFF: Other Equipment Types | 0.067452 | 3.4425 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.6. | Distribution pole replacement and reinforcement, including with composite poles
Asset management and inspections | 24 | 12 | 24-12 | 12. Patrol inspections of transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 12 | 24-12 | 12. Patrol inspections of transmission electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 12 | 24-12 | 12. Patrol inspections of transmission electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 12 | 24-12 | 12. Patrol inspections of transmission electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 12 | 24-12 | 12. Patrol inspections of transmission electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 12 | 24-12 | 12. Patrol inspections of transmission electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 13 | 24-13 | 13. Pole loading assessment program to determine safety factor | 2019 plan | 2159.394 | 0 | 2159.394 | 18271 | 0.11819 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.4.13. | Pole loading assessment program to determine safety factor
Asset management and inspections | 24 | 13 | 24-13 | 13. Pole loading assessment program to determine safety factor | 2019 actual | 1879.409 | 0 | 1879.409 | 15902 | 0.11819 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.4.13. | Pole loading assessment program to determine safety factor
Asset management and inspections | 24 | 13 | 24-13 | 13. Pole loading assessment program to determine safety factor | 2020 | 287.988 | 0 | 287.988 | 2369 | 0.12157 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.4.13. | Pole loading assessment program to determine safety factor
Asset management and inspections | 24 | 13 | 24-13 | 13. Pole loading assessment program to determine safety factor | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2018 GRC | NA | NA | NA | All columns are "NA" as this initiative is to be completed in 2020 | Non-WMP Program | HFRA | 7.3.4.13. | Pole loading assessment program to determine safety factor
Asset management and inspections | 24 | 13 | 24-13 | 13. Pole loading assessment program to determine safety factor | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2018 GRC | NA | NA | NA | All columns are "NA" as this initiative is to be completed in 2020 | Non-WMP Program | HFRA | 7.3.4.13. | Pole loading assessment program to determine safety factor
Grid design and system hardening | 23 | 13 | 23-13 | 13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2020-2022 plan total | 89916.935 | 89916.935 | 0 | 5074 | 17.7211 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure. | Non-WMP Program | HFRA | 7.3.3.13. | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Asset management and inspections | 24 | 14 | 24-14 | 14. Quality assurance / quality control of inspections: Quality Oversight / Quality Control (IN-2) | 2019 plan | NA | NA | NA | 7500 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 14 | 24-14 | 14. Quality assurance / quality control of inspections: Quality Oversight / Quality Control (IN-2) | 2019 actual | NA | NA | NA | 17109 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 14 | 24-14 | 14. Quality assurance / quality control of inspections: Quality Oversight / Quality Control (IN-2) | 2020 | NA | NA | NA | 15000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 14 | 24-14 | 14. Quality assurance / quality control of inspections: Quality Oversight / Quality Control (IN-2) | 2021 | NA | NA | NA | 15000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 14 | 24-14 | 14. Quality assurance / quality control of inspections: Quality Oversight / Quality Control (IN-2) | 2022 | NA | NA | NA | 15000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 14 | 24-14 | 14. Quality assurance / quality control of inspections: Quality Oversight / Quality Control (IN-2) | 2020-2022 plan total | NA | NA | NA | 45000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 15 | 24-15 | 15. Substation inspections | 2019 plan | 18015.009 | 0 | 18015.009 | 5500 | 3.2755 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure. | Non-WMP Program | HFRA | 7.3.4.15. | Substation inspections
Asset management and inspections | 24 | 15 | 24-15 | 15. Substation inspections | 2019 actual | 19214.171 | 0 | 19214.171 | 5591 | 3.4366 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure. | Non-WMP Program | HFRA | 7.3.4.15. | Substation inspections
Asset management and inspections | 24 | 15 | 24-15 | 15. Substation inspections | 2020 | 18943.038 | 0 | 18943.038 | 5500 | 3.4442 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure. | Non-WMP Program | HFRA | 7.3.4.15. | Substation inspections
Asset management and inspections | 24 | 15 | 24-15 | 15. Substation inspections | 2021 | 19259.712 | 0 | 19259.712 | 5500 | 3.5018 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure. | Non-WMP Program | HFRA | 7.3.4.15. | Substation inspections
Asset management and inspections | 24 | 15 | 24-15 | 15. Substation inspections | 2022 | 20473.074 | 0 | 20473.074 | 5500 | 3.7224 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure. | Non-WMP Program | HFRA | 7.3.4.15. | Substation inspections
Grid design and system hardening | 23 | 14 | 23-14 | 14. Transformers maintenance and replacement | 2020-2022 plan total | 7569.268 | 7417.883 | 151.385 | NA | NA | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.3.14. | Transformers maintenance and replacement
Asset management and inspections | 24 | 15.1 | 24-15.1 | 15.1 Failure Modes and Effects Analysis (FMEA) (IN-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 15.1 | 24-15.1 | 15.1 Failure Modes and Effects Analysis (FMEA) (IN-7) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 15.1 | 24-15.1 | 15.1 Failure Modes and Effects Analysis (FMEA) (IN-7) | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 15.1 | 24-15.1 | 15.1 Failure Modes and Effects Analysis (FMEA) (IN-7) | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 15.1 | 24-15.1 | 15.1 Failure Modes and Effects Analysis (FMEA) (IN-7) | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 15.1 | 24-15.1 | 15.1 Failure Modes and Effects Analysis (FMEA) (IN-7) | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Asset management and inspections | 24 | 16 | 24-16 | 16. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: generation risk-informed inspections in HFRA (IN-5) | 2019 plan | 400 | 0 | 400 | 400 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 16 | 24-16 | 16. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: generation risk-informed inspections in HFRA (IN-5) | 2019 actual | 252.9923 | 0 | 252.9923 | 449 | 0.56346 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 16 | 24-16 | 16. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: generation risk-informed inspections in HFRA (IN-5) | 2020 | 157.8599 | 0 | 157.8599 | 200 | 0.7893 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure. 50% of applicable assets per year | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 16 | 24-16 | 16. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: generation risk-informed inspections in HFRA (IN-5) | 2021 | 162.2616 | 0 | 162.2616 | 200 | 0.81131 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure. 50% of applicable assets per year | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 16 | 24-16 | 16. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: generation risk-informed inspections in HFRA (IN-5) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile" columns are UNKNOWN because the need for 2022 inspections will be evaluated after analysis of all assets in 2020-2021 is completed. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset management and inspections | 24 | 16 | 24-16 | 16. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: generation risk-informed inspections in HFRA (IN-5) | 2020-2022 plan total | 320.1216 | 0 | 320.1216 | 400 | 0.8003 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure. | WMP Program | HFRA | 7.3.4.9.2 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Vegetation management and inspections | 25 | 1 | 25-1 | 1. Additional efforts to manage community and environmental impacts | 2019 plan | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 1 | 25-1 | 1. Additional efforts to manage community and environmental impacts | 2019 actual | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 1 | 25-1 | 1. Additional efforts to manage community and environmental impacts | 2020 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 1 | 25-1 | 1. Additional efforts to manage community and environmental impacts | 2021 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 1 | 25-1 | 1. Additional efforts to manage community and environmental impacts | 2022 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 1 | 25-1 | 1. Additional efforts to manage community and environmental impacts | 2020-2022 plan total | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 2 | 25-2 | 2. Detailed inspections of vegetation around distribution electric lines and equipment | 2019 plan | 11378.9144 | 0 | 11378.9144 | 9827 | 1.1579 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.2. | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 2 | 25-2 | 2. Detailed inspections of vegetation around distribution electric lines and equipment | 2019 actual | 5944.3773 | 0 | 5944.3773 | 9827 | 0.6049 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.2. | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 2 | 25-2 | 2. Detailed inspections of vegetation around distribution electric lines and equipment | 2020 | 11385.882 | 0 | 11385.882 | 9827 | 1.1586 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.2. | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 2 | 25-2 | 2. Detailed inspections of vegetation around distribution electric lines and equipment | 2021 | 11396.674 | 0 | 11396.674 | 9827 | 1.1597 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.2. | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 2 | 25-2 | 2. Detailed inspections of vegetation around distribution electric lines and equipment | 2022 | 11407.062 | 0 | 11407.062 | 9827 | 1.1608 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.2. | Detailed inspections of vegetation around distribution electric lines and equipment
Asset management and inspections | 24 | 6 | 24-6 | 6. Intrusive pole inspections (IPI) | 2020-2022 plan total | 3964 | 0 | 3964 | 90468 | 0.043817 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years. | Non-WMP Program | HFRA | 7.3.4.6. | Intrusive pole inspections
Vegetation management and inspections | 25 | 3 | 25-3 | 3. Detailed inspections of vegetation around transmission electric lines and equipment | 2019 plan | 508.2339 | 0 | 508.2339 | 4352 | 0.11678 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.3. | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 3 | 25-3 | 3. Detailed inspections of vegetation around transmission electric lines and equipment | 2019 actual | 1868.0634 | 0 | 1868.0634 | 4352 | 0.42924 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.3. | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 3 | 25-3 | 3. Detailed inspections of vegetation around transmission electric lines and equipment | 2020 | 508.727 | 0 | 508.727 | 4352 | 0.11689 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.3. | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 3 | 25-3 | 3. Detailed inspections of vegetation around transmission electric lines and equipment | 2021 | 509.029 | 0 | 509.029 | 4352 | 0.11696 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.3. | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 3 | 25-3 | 3. Detailed inspections of vegetation around transmission electric lines and equipment | 2022 | 509.339 | 0 | 509.339 | 4352 | 0.11704 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.3. | Detailed inspections of vegetation around transmission electric lines and equipment
Asset management and inspections | 24 | 11 | 24-11 | 11. Patrol inspections of distribution electric lines and equipment | 2020-2022 plan total | 3251 | 0 | 3251 | 22056 | 0.1474 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure. | Non-WMP Program | HFRA | 7.3.4.11. | Patrol inspections of distribution electric lines and equipment
Vegetation management and inspections | 25 | 4 | 25-4 | 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2019 plan | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 4 | 25-4 | 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2019 actual | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 4 | 25-4 | 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2020 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 4 | 25-4 | 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2021 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 4 | 25-4 | 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2022 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 4 | 25-4 | 4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2020-2022 plan total | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 5 | 25-5 | 5. Fuel management and reduction of “slash” from vegetation management activities | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 5 | 25-5 | 5. Fuel management and reduction of “slash” from vegetation management activities | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 5 | 25-5 | 5. Fuel management and reduction of “slash” from vegetation management activities | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 5 | 25-5 | 5. Fuel management and reduction of “slash” from vegetation management activities | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 5 | 25-5 | 5. Fuel management and reduction of “slash” from vegetation management activities | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 5 | 25-5 | 5. Fuel management and reduction of “slash” from vegetation management activities | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 5.1 | 25-5.1 | 5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing (VM-2) | 2019 plan | 909.4192 | 0 | 909.4192 | 98913 | 0.0091941 | EFF: Capacitor Bank Crossarm Insulator | 0.020923 | 89.306 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.1 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.1 | 25-5.1 | 5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing (VM-2) | 2019 actual | 1646.0911 | 0 | 1646.0911 | 163149 | 0.010089 | EFF: Capacitor Bank Crossarm Insulator | 0.13339 | 83.1545 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.1 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.1 | 25-5.1 | 5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing (VM-2) | 2020 | 4156.9252 | 0 | 4156.9252 | 300000 | 0.013856 | EFF: Capacitor Bank Crossarm Insulator | 0.24498 | 60.2554 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.1 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.1 | 25-5.1 | 5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing (VM-2) | 2021 | 4208.0555 | 0 | 4208.0555 | 300000 | 0.014027 | EFF: Capacitor Bank Crossarm Insulator | 0.23784 | 58.5004 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.1 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.1 | 25-5.1 | 5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing (VM-2) | 2022 | 4256.2018 | 0 | 4256.2018 | 300000 | 0.014187 | EFF: Capacitor Bank Crossarm Insulator | 0.23091 | 56.7965 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.1 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.1 | 25-5.1 | 5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing (VM-2) | 2020-2022 plan total | 12621.1826 | 0 | 12621.1826 | 900000 | 0.014024 | EFF: Capacitor Bank Crossarm Insulator | 0.71373 | 58.5174 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.1 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.2 | 25-5.2 | 5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities (VM-3) | 2019 plan | NA | NA | NA | NA | NA | NA | Insufficient data to model risk | Insufficient data to model risk | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.3.5.5.2 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.2 | 25-5.2 | 5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities (VM-3) | 2019 actual | NA | NA | NA | NA | NA | NA | Insufficient data to model risk | Insufficient data to model risk | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative. | WMP Program | HFRA | 7.3.5.5.2 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.2 | 25-5.2 | 5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities (VM-3) | 2020 | 1217.4395 | 0 | 1217.4395 | 80 | 15.218 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.2 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.2 | 25-5.2 | 5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities (VM-3) | 2021 | 1055.9668 | 0 | 1055.9668 | 32 | 32.999 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.2 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.2 | 25-5.2 | 5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities (VM-3) | 2022 | 1088.7505 | 0 | 1088.7505 | 24 | 45.3646 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.2 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 5.2 | 25-5.2 | 5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities (VM-3) | 2020-2022 plan total | 3362.1568 | 0 | 3362.1568 | 136 | 24.7217 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.5.2 | Fuel management and reduction of “slash” from vegetation management activities
Vegetation management and inspections | 25 | 6 | 25-6 | 6. Improvement of inspections | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 6 | 25-6 | 6. Improvement of inspections | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 6 | 25-6 | 6. Improvement of inspections | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 6 | 25-6 | 6. Improvement of inspections | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 6 | 25-6 | 6. Improvement of inspections | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 6 | 25-6 | 6. Improvement of inspections | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 7 | 25-7 | 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 7 | 25-7 | 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 7 | 25-7 | 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 7 | 25-7 | 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 7 | 25-7 | 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 7 | 25-7 | 7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 8 | 25-8 | 8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2019 plan | 3721.8542 | 0 | 3721.8542 | 3658 | 1.0175 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.8. | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 8 | 25-8 | 8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2019 actual | 4516.581 | 0 | 4516.581 | 1559 | 2.8971 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.8. | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 8 | 25-8 | 8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2020 | 1467.4411 | 0 | 1467.4411 | 1227 | 1.196 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.8. | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 8 | 25-8 | 8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2021 | 1485.4906 | 0 | 1485.4906 | 1227 | 1.2107 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.8. | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 8 | 25-8 | 8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2022 | 1502.4868 | 0 | 1502.4868 | 1227 | 1.2245 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.8. | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 8 | 25-8 | 8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2020-2022 plan total | 4455.4185 | 0 | 4455.4185 | 3681 | 1.2104 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.8. | LiDAR inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 9 | 25-9 | 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 9 | 25-9 | 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 9 | 25-9 | 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 9 | 25-9 | 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 9 | 25-9 | 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 9 | 25-9 | 9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 10 | 25-10 | 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 10 | 25-10 | 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 10 | 25-10 | 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 10 | 25-10 | 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 10 | 25-10 | 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 10 | 25-10 | 10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 11 | 25-11 | 11. Patrol inspections of vegetation around distribution electric lines and equipment | 2019 plan | 7255.4223 | 0 | 7255.4223 | 96 | 75.5773 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.11. | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 11 | 25-11 | 11. Patrol inspections of vegetation around distribution electric lines and equipment | 2019 actual | 15072.089 | 0 | 15072.089 | 96 | 157.0009 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.11. | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 11 | 25-11 | 11. Patrol inspections of vegetation around distribution electric lines and equipment | 2020 | 5060.603 | 0 | 5060.603 | 96 | 52.7146 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.11. | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 11 | 25-11 | 11. Patrol inspections of vegetation around distribution electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #20, Table 25 | Non-WMP Program | HFRA | 7.3.5.11. | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 11 | 25-11 | 11. Patrol inspections of vegetation around distribution electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #20, Table 25 | Non-WMP Program | HFRA | 7.3.5.11. | Patrol inspections of vegetation around distribution electric lines and equipment
Asset management and inspections | 24 | 13 | 24-13 | 13. Pole loading assessment program to determine safety factor | 2020-2022 plan total | 287.988 | 0 | 287.988 | 2369 | 0.12157 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.4.13. | Pole loading assessment program to determine safety factor
Vegetation management and inspections | 25 | 12 | 25-12 | 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25 | Non-WMP Program | HFRA | 7.3.5.12. | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 12 | 25-12 | 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25 | Non-WMP Program | HFRA | 7.3.5.12. | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 12 | 25-12 | 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2020 | 2177.009 | 0 | 2177.009 | 96 | 22.6772 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.12. | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 12 | 25-12 | 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25 | Non-WMP Program | HFRA | 7.3.5.12. | Patrol inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 12 | 25-12 | 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25 | Non-WMP Program | HFRA | 7.3.5.12. | Patrol inspections of vegetation around transmission electric lines and equipment
Asset management and inspections | 24 | 15 | 24-15 | 15. Substation inspections | 2020-2022 plan total | 58675.824 | 0 | 58675.824 | 16500 | 3.5561 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure. | Non-WMP Program | HFRA | 7.3.4.15. | Substation inspections
Vegetation management and inspections | 25 | 13 | 25-13 | 13. Quality assurance / quality control of inspections: quality control (VM-5) | 2019 plan | 0 | 0 | 0 | 4700 | 0 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | Combined | 7.3.5.13. | Quality assurance / quality control of vegetation inspections
Vegetation management and inspections | 25 | 13 | 25-13 | 13. Quality assurance / quality control of inspections: quality control (VM-5) | 2019 actual | 985.2004 | 0 | 985.2004 | 4700 | 0.20962 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | Combined | 7.3.5.13. | Quality assurance / quality control of vegetation inspections
Vegetation management and inspections | 25 | 13 | 25-13 | 13. Quality assurance / quality control of inspections: quality control (VM-5) | 2020 | 4000 | 0 | 4000 | 8100 | 0.49383 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | Combined | 7.3.5.13. | Quality assurance / quality control of vegetation inspections
Vegetation management and inspections | 25 | 13 | 25-13 | 13. Quality assurance / quality control of inspections: quality control (VM-5) | 2021 | 5000 | 0 | 5000 | 8100 | 0.61728 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | Combined | 7.3.5.13. | Quality assurance / quality control of vegetation inspections
Vegetation management and inspections | 25 | 13 | 25-13 | 13. Quality assurance / quality control of inspections: quality control (VM-5) | 2022 | 5000 | 0 | 5000 | 8100 | 0.61728 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | Combined | 7.3.5.13. | Quality assurance / quality control of vegetation inspections
Vegetation management and inspections | 25 | 2 | 25-2 | 2. Detailed inspections of vegetation around distribution electric lines and equipment | 2020-2022 plan total | 34189.618 | 0 | 34189.618 | 29481 | 1.1597 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.2. | Detailed inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 14 | 25-14 | 14. Recruiting and training of vegetation management personnel | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 14 | 25-14 | 14. Recruiting and training of vegetation management personnel | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 14 | 25-14 | 14. Recruiting and training of vegetation management personnel | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 14 | 25-14 | 14. Recruiting and training of vegetation management personnel | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 14 | 25-14 | 14. Recruiting and training of vegetation management personnel | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 14 | 25-14 | 14. Recruiting and training of vegetation management personnel | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 15 | 25-15 | 15. Remediation of at-risk species | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 15 | 25-15 | 15. Remediation of at-risk species | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 15 | 25-15 | 15. Remediation of at-risk species | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 15 | 25-15 | 15. Remediation of at-risk species | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 15 | 25-15 | 15. Remediation of at-risk species | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 15 | 25-15 | 15. Remediation of at-risk species | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 16 | 25-16 | 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 16 | 25-16 | 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 16 | 25-16 | 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 16 | 25-16 | 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 16 | 25-16 | 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 16 | 25-16 | 16. Removal and remediation of trees with strike potential to electric lines and equipment | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 16.1 | 25-16.1 | 16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 2019 plan | 56894.7409 | 0 | 56894.7409 | 125000 | 0.45516 | CFO: Vegetation | 0.34135 | 5.9998 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.1 | 25-16.1 | 16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 2019 actual | 15209.6163 | 0 | 15209.6163 | 129485 | 0.11746 | CFO: Vegetation | 0.44888 | 29.5129 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.1 | 25-16.1 | 16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 2020 | 54097.2977 | 0 | 54097.2977 | 75000 | 0.7213 | CFO: Vegetation | 1.3234 | 25.0199 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.1 | 25-16.1 | 16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 2021 | 59475.8515 | 0 | 59475.8515 | 75000 | 0.79301 | CFO: Vegetation | 1.4138 | 24.6199 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.1 | 25-16.1 | 16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 2022 | 72035.267 | 0 | 72035.267 | 75000 | 0.96047 | CFO: Vegetation | 1.6975 | 24.6914 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.1 | 25-16.1 | 16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 2020-2022 plan total | 185608.4163 | 0 | 185608.4163 | 225000 | 0.82493 | CFO: Vegetation | 4.4347 | 24.7655 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | WMP Program | HFRA | 7.3.5.16.1 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.2 | 25-16.2 | 16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 2019 plan | 41481.9813 | 0 | 41481.9813 | 14179 | 2.9256 | CFO: Vegetation | 1.1914 | 28.7203 | NA | New | NA | CEMA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.2 | 25-16.2 | 16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 2019 actual | 32598.997 | 0 | 32598.997 | 14179 | 2.2991 | CFO: Vegetation | 1.1914 | 36.5463 | NA | New | NA | CEMA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.2 | 25-16.2 | 16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 2020 | 36470.011 | 0 | 36470.011 | 14179 | 2.5721 | CFO: Vegetation | 1.1567 | 31.7157 | NA | New | NA | CEMA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.2 | 25-16.2 | 16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 2021 | 36973.531 | 0 | 36973.531 | 14179 | 2.6076 | CFO: Vegetation | 1.123 | 30.3726 | NA | New | NA | UNKNOWN | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The "If new: Memorandum account" column is "UNKNOWN" because it is pending 2021 GRC decision The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 16.2 | 25-16.2 | 16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 2022 | 37564.933 | 0 | 37564.933 | 14179 | 2.6493 | CFO: Vegetation | 1.0903 | 29.0238 | NA | New | NA | UNKNOWN | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The "If new: Memorandum account" column is "UNKNOWN" because it is pending 2021 GRC decision The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment
Vegetation management and inspections | 25 | 3 | 25-3 | 3. Detailed inspections of vegetation around transmission electric lines and equipment | 2020-2022 plan total | 1527.095 | 0 | 1527.095 | 13056 | 0.11696 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | HFRA | 7.3.5.3. | Detailed inspections of vegetation around transmission electric lines and equipment
Vegetation management and inspections | 25 | 17 | 25-17 | 17. Substation inspections | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 17 | 25-17 | 17. Substation inspections | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 17 | 25-17 | 17. Substation inspections | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 17 | 25-17 | 17. Substation inspections | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 17 | 25-17 | 17. Substation inspections | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 17 | 25-17 | 17. Substation inspections | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24 | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 18 | 25-18 | 18. Substation vegetation management | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 18 | 25-18 | 18. Substation vegetation management | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 18 | 25-18 | 18. Substation vegetation management | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 18 | 25-18 | 18. Substation vegetation management | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 18 | 25-18 | 18. Substation vegetation management | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 18 | 25-18 | 18. Substation vegetation management | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program. | Non-WMP Program | No Forecast
Vegetation management and inspections | 25 | 19 | 25-19 | 19. Vegetation inventory system | 2019 plan | 421 | 0 | 421 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.19. | Vegetation inventory system
Vegetation management and inspections | 25 | 19 | 25-19 | 19. Vegetation inventory system | 2019 actual | 5381 | 4960 | 421 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.19. | Vegetation inventory system
Vegetation management and inspections | 25 | 19 | 25-19 | 19. Vegetation inventory system | 2020 | 3771 | 2111 | 1660 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.19. | Vegetation inventory system
Vegetation management and inspections | 25 | 19 | 25-19 | 19. Vegetation inventory system | 2021 | 3000 | 2850 | 150 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.19. | Vegetation inventory system
Vegetation management and inspections | 25 | 19 | 25-19 | 19. Vegetation inventory system | 2022 | 1000 | 950 | 50 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.19. | Vegetation inventory system
Vegetation management and inspections | 25 | 11 | 25-11 | 11. Patrol inspections of vegetation around distribution electric lines and equipment | 2020-2022 plan total | 5060.603 | 0 | 5060.603 | 96 | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.11. | Patrol inspections of vegetation around distribution electric lines and equipment
Vegetation management and inspections | 25 | 20 | 25-20 | 20. Vegetation management to achieve clearances around electric lines and equipment | 2019 plan | 76281.452 | 0 | 76281.452 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | Please note that the forecast plan costs include line clearance work in HFRA and non-HFRA. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates. | WMP Program | HFRA | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment
Vegetation management and inspections | 25 | 20 | 25-20 | 20. Vegetation management to achieve clearances around electric lines and equipment | 2019 actual | 247104.99 | 0 | 247104.99 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | Please note that the recorded costs include line clearance work in HFRA and non-HFRA and therefore on a different basis than the forecasts included in the 2019 WMP. We are unable to separate the recorded costs for wildfire mitigation and HFRA line clearance costs at this time for 2019. SCE is modifying its business practices to track wildfire mitigation and HFRA line clearance costs separately going forward. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates. | WMP Program | HFRA | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment
Vegetation management and inspections | 25 | 20 | 25-20 | 20. Vegetation management to achieve clearances around electric lines and equipment | 2020 | 76281.452 | 0 | 76281.452 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2020 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates. | WMP Program | HFRA | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment
Vegetation management and inspections | 25 | 20 | 25-20 | 20. Vegetation management to achieve clearances around electric lines and equipment | 2021 | 64169.652 | 0 | 64169.652 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2021 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates. | WMP Program | HFRA | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment
Vegetation management and inspections | 25 | 20 | 25-20 | 20. Vegetation management to achieve clearances around electric lines and equipment | 2022 | 60868.687 | 0 | 60868.687 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2022 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates. | WMP Program | HFRA | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment
Vegetation management and inspections | 25 | 20 | 25-20 | 20. Vegetation management to achieve clearances around electric lines and equipment | 2020-2022 plan total | 201319.791 | 0 | 201319.791 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2020-2022 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates. | WMP Program | HFRA | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment
Grid operations and protocols | 26 | 1 | 26-1 | 1. Automatic recloser operations | 2019 plan | 284.8915 | 0 | 284.8915 | 150 | 1.8993 | NA | 0.010796 | 2.212 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid operations and protocols | 26 | 1 | 26-1 | 1. Automatic recloser operations | 2019 actual | 418.265 | 0 | 418.265 | NA | NA | NA | 0.015181 | 1.3664 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid operations and protocols | 26 | 1 | 26-1 | 1. Automatic recloser operations | 2020 | NA | NA | NA | NA | NA | NA | 0.016049 | 1.929 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid operations and protocols | 26 | 1 | 26-1 | 1. Automatic recloser operations | 2021 | NA | NA | NA | NA | NA | NA | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid operations and protocols | 26 | 1 | 26-1 | 1. Automatic recloser operations | 2022 | NA | NA | NA | NA | NA | NA | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid operations and protocols | 26 | 1 | 26-1 | 1. Automatic recloser operations | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | 0.016049 | 1.929 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | 7.3.3.2. | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid operations and protocols | 26 | 1.1 | 26-1.1 | 1.1. Annual SOB 322 review (OP-1) | 2019 plan | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid operations and protocols | 26 | 1.1 | 26-1.1 | 1.1. Annual SOB 322 review (OP-1) | 2019 actual | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid operations and protocols | 26 | 1.1 | 26-1.1 | 1.1. Annual SOB 322 review (OP-1) | 2020 | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid operations and protocols | 26 | 1.1 | 26-1.1 | 1.1. Annual SOB 322 review (OP-1) | 2021 | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid operations and protocols | 26 | 1.1 | 26-1.1 | 1.1. Annual SOB 322 review (OP-1) | 2022 | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast | #N/A | N/A
Grid operations and protocols | 26 | 1.1 | 26-1.1 | 1.1. Annual SOB 322 review (OP-1) | 2020-2022 plan total | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | No Forecast
Grid operations and protocols | 26 | 2 | 26-2 | 2. Crew-accompanying ignition prevention and suppression resources and services | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 2 | 26-2 | 2. Crew-accompanying ignition prevention and suppression resources and services | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 2 | 26-2 | 2. Crew-accompanying ignition prevention and suppression resources and services | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 2 | 26-2 | 2. Crew-accompanying ignition prevention and suppression resources and services | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 2 | 26-2 | 2. Crew-accompanying ignition prevention and suppression resources and services | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 2 | 26-2 | 2. Crew-accompanying ignition prevention and suppression resources and services | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 3 | 26-3 | 3. Personnel work procedures and training in conditions of elevated fire risk | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 3 | 26-3 | 3. Personnel work procedures and training in conditions of elevated fire risk | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 3 | 26-3 | 3. Personnel work procedures and training in conditions of elevated fire risk | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 3 | 26-3 | 3. Personnel work procedures and training in conditions of elevated fire risk | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 3 | 26-3 | 3. Personnel work procedures and training in conditions of elevated fire risk | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 3 | 26-3 | 3. Personnel work procedures and training in conditions of elevated fire risk | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 4 | 26-4 | 4. Protocols for PSPS re-energization | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 4 | 26-4 | 4. Protocols for PSPS re-energization | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 4 | 26-4 | 4. Protocols for PSPS re-energization | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 4 | 26-4 | 4. Protocols for PSPS re-energization | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 4 | 26-4 | 4. Protocols for PSPS re-energization | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 4 | 26-4 | 4. Protocols for PSPS re-energization | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26 | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 5 | 26-5 | 5. PSPS events and mitigation of PSPS impacts | 2019 plan | 1044.3883 | 0 | 1044.3883 | NA | NA | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5 | 26-5 | 5. PSPS events and mitigation of PSPS impacts | 2019 actual | 4216.9108 | 0 | 4216.9108 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5 | 26-5 | 5. PSPS events and mitigation of PSPS impacts | 2020 | 7258.891 | 787.908 | 6470.983 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5 | 26-5 | 5. PSPS events and mitigation of PSPS impacts | 2021 | 7442.645 | 812.974 | 6629.671 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5 | 26-5 | 5. PSPS events and mitigation of PSPS impacts | 2022 | 7667.501 | 836.489 | 6831.012 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5 | 26-5 | 5. PSPS events and mitigation of PSPS impacts | 2020-2022 plan total | 22369.037 | 2437.371 | 19931.666 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.1 | 26-5.1 | 5.1. PSPS events and mitigation of PSPS impacts: community resource centers (PSPS-2) | 2019 plan | 783.15 | 0 | 783.15 | 13 | 60.2423 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.1 | 26-5.1 | 5.1. PSPS events and mitigation of PSPS impacts: community resource centers (PSPS-2) | 2019 actual | 45.7336 | 0 | 45.7336 | 13 | 3.518 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.1 | 26-5.1 | 5.1. PSPS events and mitigation of PSPS impacts: community resource centers (PSPS-2) | 2020 | 2274.806 | 1212.013 | 1062.793 | 36 | 63.189 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.1 | 26-5.1 | 5.1. PSPS events and mitigation of PSPS impacts: community resource centers (PSPS-2) | 2021 | 2107.708 | 737.864 | 1369.844 | 50 | 42.1542 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.1 | 26-5.1 | 5.1. PSPS events and mitigation of PSPS impacts: community resource centers (PSPS-2) | 2022 | 1368.88 | 0 | 1368.88 | 50 | 27.3776 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.1 | 26-5.1 | 5.1. PSPS events and mitigation of PSPS impacts: community resource centers (PSPS-2) | 2020-2022 plan total | 5751.394 | 1949.877 | 3801.517 | 136 | 42.2897 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.2 | 26-5.2 | 5.2. PSPS events and mitigation of PSPS impacts: customer resiliency equipment incentives (PSPS-3) | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | NA | NA | Refer to Initiative 5, Table 26 | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.2 | 26-5.2 | 5.2. PSPS events and mitigation of PSPS impacts: customer resiliency equipment incentives (PSPS-3) | 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | SCE is currently in the process of setting up a pilot for this Initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.2 | 26-5.2 | 5.2. PSPS events and mitigation of PSPS impacts: customer resiliency equipment incentives (PSPS-3) | 2020 | UNKNOWN | UNKNOWN | UNKNOWN | 1 | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | SCE is currently in the process of setting up a pilot for this Initiative. The costs for 2020 are still to be determined. Instead of "Line miles to be treated", number of customers in the program is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.2 | 26-5.2 | 5.2. PSPS events and mitigation of PSPS impacts: customer resiliency equipment incentives (PSPS-3) | 2021 | 3685.0947 | 0 | 3685.0947 | UNKNOWN | UNKNOWN | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", number of customers in the program is the unit of measure. The scope for 2021 is still to be determined. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.2 | 26-5.2 | 5.2. PSPS events and mitigation of PSPS impacts: customer resiliency equipment incentives (PSPS-3) | 2022 | 3758.5213 | 0 | 3758.5213 | UNKNOWN | UNKNOWN | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", number of customers in the program is the unit of measure. The scope for 2022 is still to be determined. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.2 | 26-5.2 | 5.2. PSPS events and mitigation of PSPS impacts: customer resiliency equipment incentives (PSPS-3) | 2020-2022 plan total | 7443.616 | 0 | 7443.616 | UNKNOWN | UNKNOWN | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", number of customers in the program is the unit of measure. SCE has forecasted a rollout of this Initiative based on the successful completion of the pilot done in 2020. The number of customers for 2021-2022 are still to be determined. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.3 | 26-5.3 | 5.3. PSPS events and mitigation of PSPS impacts: income qualified critical care (IQCC) customer battery backup incentive program (PSPS-4) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.3 | 26-5.3 | 5.3. PSPS events and mitigation of PSPS impacts: income qualified critical care (IQCC) customer battery backup incentive program (PSPS-4) | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 actual as this initiative did not begin until 2020. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.3 | 26-5.3 | 5.3. PSPS events and mitigation of PSPS impacts: income qualified critical care (IQCC) customer battery backup incentive program (PSPS-4) | 2020 | 9240.9856 | 0 | 9240.9856 | 2500 | 3.6964 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.3 | 26-5.3 | 5.3. PSPS events and mitigation of PSPS impacts: income qualified critical care (IQCC) customer battery backup incentive program (PSPS-4) | 2021 | 1431.7112 | 0 | 1431.7112 | 408 | 3.5091 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.3 | 26-5.3 | 5.3. PSPS events and mitigation of PSPS impacts: income qualified critical care (IQCC) customer battery backup incentive program (PSPS-4) | 2022 | 1462.642 | 0 | 1462.642 | 408 | 3.5849 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.3 | 26-5.3 | 5.3. PSPS events and mitigation of PSPS impacts: income qualified critical care (IQCC) customer battery backup incentive program (PSPS-4) | 2020-2022 plan total | 12135.3387 | 0 | 12135.3387 | 3316 | 3.6596 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.4 | 26-5.4 | 5.4. PSPS events and mitigation of PSPS impacts: MICOP partnership (PSPS-5) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.4 | 26-5.4 | 5.4. PSPS events and mitigation of PSPS impacts: MICOP partnership (PSPS-5) | 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | The MICOP partnership began in Q4 of 2019, the majority of deliverables will be executed in 2020. 2019 spend is "NA" because the MICOP grant partnership was funded through corporate philanthropy shareholder budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.4 | 26-5.4 | 5.4. PSPS events and mitigation of PSPS impacts: MICOP partnership (PSPS-5) | 2020 | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2020 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.4 | 26-5.4 | 5.4. PSPS events and mitigation of PSPS impacts: MICOP partnership (PSPS-5) | 2021 | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2021 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.4 | 26-5.4 | 5.4. PSPS events and mitigation of PSPS impacts: MICOP partnership (PSPS-5) | 2022 | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2022 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.4 | 26-5.4 | 5.4. PSPS events and mitigation of PSPS impacts: MICOP partnership (PSPS-5) | 2020-2022 plan total | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2021-2022 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.5 | 26-5.5 | 5.5. PSPS events and mitigation of PSPS impacts: independent living centers partnership (PSPS-6) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.5 | 26-5.5 | 5.5. PSPS events and mitigation of PSPS impacts: independent living centers partnership (PSPS-6) | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | PSPS Decision, 2019 WMP Decision | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because this initiative was funded through corporate philanthropy shareholder budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.5 | 26-5.5 | 5.5. PSPS events and mitigation of PSPS impacts: independent living centers partnership (PSPS-6) | 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2020 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.5 | 26-5.5 | 5.5. PSPS events and mitigation of PSPS impacts: independent living centers partnership (PSPS-6) | 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2021 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.5 | 26-5.5 | 5.5. PSPS events and mitigation of PSPS impacts: independent living centers partnership (PSPS-6) | 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2022 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.5 | 26-5.5 | 5.5. PSPS events and mitigation of PSPS impacts: independent living centers partnership (PSPS-6) | 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In compliance | PSPS Decision, 2019 WMP Decision | 2020-2022 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | No Forecast | 7.3.10.1.1 | Community engagement
Grid operations and protocols | 26 | 5.6 | 26-5.6 | 5.6. PSPS events and mitigation of PSPS impacts: community outreach (PSPS-7) | 2019 plan | 1123.6182 | 0 | 1123.6182 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.6 | 26-5.6 | 5.6. PSPS events and mitigation of PSPS impacts: community outreach (PSPS-7) | 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Total per-initiative spend" is "NA" as the 2019 actuals for this initiative are included with Initiative 2, Table 29. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.6 | 26-5.6 | 5.6. PSPS events and mitigation of PSPS impacts: community outreach (PSPS-7) | 2020 | 439.6565 | 0 | 439.6565 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.6 | 26-5.6 | 5.6. PSPS events and mitigation of PSPS impacts: community outreach (PSPS-7) | 2021 | 362.2616 | 0 | 362.2616 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.6 | 26-5.6 | 5.6. PSPS events and mitigation of PSPS impacts: community outreach (PSPS-7) | 2022 | 303.5939 | 0 | 303.5939 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.6 | 26-5.6 | 5.6. PSPS events and mitigation of PSPS impacts: community outreach (PSPS-7) | 2020-2022 plan total | 1105.512 | 0 | 1105.512 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.7 | 26-5.7 | 5.7. PSPS events and mitigation of PSPS impacts: wildfire infrastructure protection team additional staffing (OP-2) | 2019 plan | 493 | 0 | 493 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.7 | 26-5.7 | 5.7. PSPS events and mitigation of PSPS impacts: wildfire infrastructure protection team additional staffing (OP-2) | 2019 actual | 1372.9081 | 0 | 1372.9081 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.7 | 26-5.7 | 5.7. PSPS events and mitigation of PSPS impacts: wildfire infrastructure protection team additional staffing (OP-2) | 2020 | 1817.4655 | 0 | 1817.4655 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.7 | 26-5.7 | 5.7. PSPS events and mitigation of PSPS impacts: wildfire infrastructure protection team additional staffing (OP-2) | 2021 | 1817.9094 | 0 | 1817.9094 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.7 | 26-5.7 | 5.7. PSPS events and mitigation of PSPS impacts: wildfire infrastructure protection team additional staffing (OP-2) | 2022 | 1818.3709 | 0 | 1818.3709 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.7 | 26-5.7 | 5.7. PSPS events and mitigation of PSPS impacts: wildfire infrastructure protection team additional staffing (OP-2) | 2020-2022 plan total | 5453.7457 | 0 | 5453.7457 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 5.8 | 26-5.8 | 5.8. PSPS events and mitigation of PSPS impacts: SGIP resiliency | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020. | Non-WMP Program | HFRA | 7.3.6.1.4.2.3
Grid operations and protocols | 26 | 5.8 | 26-5.8 | 5.8. PSPS events and mitigation of PSPS impacts: SGIP resiliency | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 actuals as this initiative did not begin until 2020. | Non-WMP Program | HFRA | 7.3.6.1.4.2.3
Grid operations and protocols | 26 | 5.8 | 26-5.8 | 5.8. PSPS events and mitigation of PSPS impacts: SGIP resiliency | 2020 | 69280 | NA | NA | 3675 | 18.8517 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.6.1.4.2.3
Grid operations and protocols | 26 | 5.8 | 26-5.8 | 5.8. PSPS events and mitigation of PSPS impacts: SGIP resiliency | 2021 | 35280 | NA | NA | 1835 | 19.2262 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.6.1.4.2.3
Grid operations and protocols | 26 | 5.8 | 26-5.8 | 5.8. PSPS events and mitigation of PSPS impacts: SGIP resiliency | 2022 | 35280 | NA | NA | 1835 | 19.2262 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | HFRA | 7.3.6.1.4.2.3
Vegetation management and inspections | 25 | 12 | 25-12 | 12. Patrol inspections of vegetation around transmission electric lines and equipment | 2020-2022 plan total | 2177.009 | 0 | 2177.009 | 96 | 22.6772 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.12. | Patrol inspections of vegetation around transmission electric lines and equipment
Grid operations and protocols | 26 | 6 | 26-6 | 6. Stationed and on-call ignition prevention and suppression resources and services | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 6 | 26-6 | 6. Stationed and on-call ignition prevention and suppression resources and services | 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 6 | 26-6 | 6. Stationed and on-call ignition prevention and suppression resources and services | 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 6 | 26-6 | 6. Stationed and on-call ignition prevention and suppression resources and services | 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 6 | 26-6 | 6. Stationed and on-call ignition prevention and suppression resources and services | 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 6 | 26-6 | 6. Stationed and on-call ignition prevention and suppression resources and services | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services. | Non-WMP Program | No Forecast
Grid operations and protocols | 26 | 7 | 26-7 | 7. De-energization notifications (PSPS-1) | 2019 plan | 1275.7816 | 0 | 1275.7816 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 7 | 26-7 | 7. De-energization notifications (PSPS-1) | 2019 actual | 1556.7495 | 0 | 1556.7495 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 7 | 26-7 | 7. De-energization notifications (PSPS-1) | 2020 | 1415.2887 | 0 | 1415.2887 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 7 | 26-7 | 7. De-energization notifications (PSPS-1) | 2021 | 1445.3183 | 0 | 1445.3183 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 7 | 26-7 | 7. De-energization notifications (PSPS-1) | 2022 | 1476.5431 | 0 | 1476.5431 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Grid operations and protocols | 26 | 7 | 26-7 | 7. De-energization notifications (PSPS-1) | 2020-2022 plan total | 4337.1502 | 0 | 4337.1502 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. | WMP Program | HFRA | 7.3.6.5. | PSPS events and mitigation of PSPS impacts
Data governance | 27 | 1 | 27-1 | 1. Centralized repository for data | 2019 plan | 3400 | 2700 | 700 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed. | Non-WMP Program | HFRA | 7.3.7.1. | Centralized repository for data
Data governance | 27 | 1 | 27-1 | 1. Centralized repository for data | 2019 actual | 2377.4 | 2071.4 | 306 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed. | Non-WMP Program | HFRA | 7.3.7.1. | Centralized repository for data
Data governance | 27 | 1 | 27-1 | 1. Centralized repository for data | 2020 | 11688.6 | 11132 | 556.6 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed. | Non-WMP Program | HFRA | 7.3.7.1. | Centralized repository for data
Data governance | 27 | 1 | 27-1 | 1. Centralized repository for data | 2021 | 18021.683 | 16843.284 | 1178.399 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed. | Non-WMP Program | HFRA | 7.3.7.1. | Centralized repository for data
Data governance | 27 | 1 | 27-1 | 1. Centralized repository for data | 2022 | 9080.96 | 8108 | 972.96 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed. | Non-WMP Program | HFRA | 7.3.7.1. | Centralized repository for data
Vegetation management and inspections | 25 | 16.2 | 25-16.2 | 16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 2020-2022 plan total | 111008.475 | 0 | 111008.475 | 42537 | 2.6097 | CFO: Vegetation | 3.3699 | 30.3574 | NA | New | NA | UNKNOWN | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The "If new: Memorandum account" column is "UNKNOWN" because it is pending 2021 GRC decision The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | HFRA | 7.3.5.16.2 | Removal and remediation of trees with strike potential to electric lines and equipment
Data governance | 27 | 2 | 27-2 | 2. Collaborative research on utility ignition and/or wildfire | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 2 | 27-2 | 2. Collaborative research on utility ignition and/or wildfire | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 2 | 27-2 | 2. Collaborative research on utility ignition and/or wildfire | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 2 | 27-2 | 2. Collaborative research on utility ignition and/or wildfire | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 2 | 27-2 | 2. Collaborative research on utility ignition and/or wildfire | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 2 | 27-2 | 2. Collaborative research on utility ignition and/or wildfire | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 3 | 27-3 | 3. Documentation and disclosure of wildfire-related data and algorithms | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 3 | 27-3 | 3. Documentation and disclosure of wildfire-related data and algorithms | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 3 | 27-3 | 3. Documentation and disclosure of wildfire-related data and algorithms | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 3 | 27-3 | 3. Documentation and disclosure of wildfire-related data and algorithms | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 3 | 27-3 | 3. Documentation and disclosure of wildfire-related data and algorithms | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 3 | 27-3 | 3. Documentation and disclosure of wildfire-related data and algorithms | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Data governance | 27 | 4 | 27-4 | 4. Tracking and analysis of near miss data | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7. | Non-WMP Program | No Forecast
Data governance | 27 | 4 | 27-4 | 4. Tracking and analysis of near miss data | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7. | Non-WMP Program | No Forecast
Data governance | 27 | 4 | 27-4 | 4. Tracking and analysis of near miss data | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7. | Non-WMP Program | No Forecast
Data governance | 27 | 4 | 27-4 | 4. Tracking and analysis of near miss data | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7. | Non-WMP Program | No Forecast
Data governance | 27 | 4 | 27-4 | 4. Tracking and analysis of near miss data | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7. | Non-WMP Program | No Forecast
Data governance | 27 | 4 | 27-4 | 4. Tracking and analysis of near miss data | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 1 | 28-1 | 1. Allocation methodology development and application | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 1 | 28-1 | 1. Allocation methodology development and application | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 1 | 28-1 | 1. Allocation methodology development and application | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 1 | 28-1 | 1. Allocation methodology development and application | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 1 | 28-1 | 1. Allocation methodology development and application | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 1 | 28-1 | 1. Allocation methodology development and application | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 2 | 28-2 | 2. Risk reduction scenario development and analysis | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 2 | 28-2 | 2. Risk reduction scenario development and analysis | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 2 | 28-2 | 2. Risk reduction scenario development and analysis | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 2 | 28-2 | 2. Risk reduction scenario development and analysis | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 2 | 28-2 | 2. Risk reduction scenario development and analysis | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 2 | 28-2 | 2. Risk reduction scenario development and analysis | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 3 | 28-3 | 3. Risk spend efficiency analysis | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 3 | 28-3 | 3. Risk spend efficiency analysis | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 3 | 28-3 | 3. Risk spend efficiency analysis | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 3 | 28-3 | 3. Risk spend efficiency analysis | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 3 | 28-3 | 3. Risk spend efficiency analysis | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 3 | 28-3 | 3. Risk spend efficiency analysis | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Resource allocation methodology | 28 | 4 | 28-4 | 4. Organizational Support - PMO, OCM, and wildfire-related IT support | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed. | WMP Program | HFRA | 7.3.8.1. | Allocation methodology development and application
Resource allocation methodology | 28 | 4 | 28-4 | 4. Organizational Support - PMO, OCM, and wildfire-related IT support | 2019 actual | 61614.6 | 18790.871 | 42823.729 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.8.1. | Allocation methodology development and application
Resource allocation methodology | 28 | 4 | 28-4 | 4. Organizational Support - PMO, OCM, and wildfire-related IT support | 2020 | 78518.986 | 32117.396 | 46401.59 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.8.1. | Allocation methodology development and application
Resource allocation methodology | 28 | 4 | 28-4 | 4. Organizational Support - PMO, OCM, and wildfire-related IT support | 2021 | 31314.893 | 6555.037 | 24759.856 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.8.1. | Allocation methodology development and application
Resource allocation methodology | 28 | 4 | 28-4 | 4. Organizational Support - PMO, OCM, and wildfire-related IT support | 2022 | 23495.035 | 2434.952 | 21060.083 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.8.1. | Allocation methodology development and application
Resource allocation methodology | 28 | 4 | 28-4 | 4. Organizational Support - PMO, OCM, and wildfire-related IT support | 2020-2022 plan total | 133328.914 | 41107.385 | 92221.529 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.8.1. | Allocation methodology development and application
Emergency planning and preparedness | 29 | 1 | 29-1 | 1. Adequate and trained workforce for service restoration (DEP-2) | 2019 plan | 2610.1046 | 0 | 2610.1046 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Emergency planning and preparedness | 29 | 1 | 29-1 | 1. Adequate and trained workforce for service restoration (DEP-2) | 2019 actual | 1440.7269 | 0 | 1440.7269 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Emergency planning and preparedness | 29 | 1 | 29-1 | 1. Adequate and trained workforce for service restoration (DEP-2) | 2020 | 1721.6811 | 0 | 1721.6811 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Emergency planning and preparedness | 29 | 1 | 29-1 | 1. Adequate and trained workforce for service restoration (DEP-2) | 2021 | 1758.2118 | 0 | 1758.2118 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Emergency planning and preparedness | 29 | 1 | 29-1 | 1. Adequate and trained workforce for service restoration (DEP-2) | 2022 | 1796.1963 | 0 | 1796.1963 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Emergency planning and preparedness | 29 | 1 | 29-1 | 1. Adequate and trained workforce for service restoration (DEP-2) | 2020-2022 plan total | 5276.0892 | 0 | 5276.0892 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.1. | Adequate and trained workforce for service restoration
Emergency planning and preparedness | 29 | 2 | 29-2 | 2. Community outreach, public awareness, and communications efforts (DEP-1.1 - DEP-1.3, DEP-3) | 2019 plan | 1423.242 | 0 | 1423.242 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.10.1.3 | Community engagement
Emergency planning and preparedness | 29 | 2 | 29-2 | 2. Community outreach, public awareness, and communications efforts (DEP-1.1 - DEP-1.3, DEP-3) | 2019 Actual | 6449.956 | 0 | 6449.956 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.10.1.3 | Community engagement
Emergency planning and preparedness | 29 | 2 | 29-2 | 2. Community outreach, public awareness, and communications efforts (DEP-1.1 - DEP-1.3, DEP-3) | 2020 | 9109.5679 | 0 | 9109.5679 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.10.1.3 | Community engagement
Emergency planning and preparedness | 29 | 2 | 29-2 | 2. Community outreach, public awareness, and communications efforts (DEP-1.1 - DEP-1.3, DEP-3) | 2021 | 9302.8547 | 0 | 9302.8547 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.10.1.3 | Community engagement
Emergency planning and preparedness | 29 | 2 | 29-2 | 2. Community outreach, public awareness, and communications efforts (DEP-1.1 - DEP-1.3, DEP-3) | 2022 | 9503.8344 | 0 | 9503.8344 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.10.1.3 | Community engagement
Emergency planning and preparedness | 29 | 2 | 29-2 | 2. Community outreach, public awareness, and communications efforts (DEP-1.1 - DEP-1.3, DEP-3) | 2020-2022 plan total | 27916.257 | 0 | 27916.257 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | D. 19-017-015 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | WMP Program | HFRA | 7.3.10.1.3 | Community engagement
Emergency planning and preparedness | 29 | 3 | 29-3 | 3. Customer support in emergencies | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 3 | 29-3 | 3. Customer support in emergencies | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 3 | 29-3 | 3. Customer support in emergencies | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 3 | 29-3 | 3. Customer support in emergencies | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 3 | 29-3 | 3. Customer support in emergencies | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 3 | 29-3 | 3. Customer support in emergencies | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 4 | 29-4 | 4. Disaster and emergency preparedness plan | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 4 | 29-4 | 4. Disaster and emergency preparedness plan | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 4 | 29-4 | 4. Disaster and emergency preparedness plan | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 4 | 29-4 | 4. Disaster and emergency preparedness plan | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 4 | 29-4 | 4. Disaster and emergency preparedness plan | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 4 | 29-4 | 4. Disaster and emergency preparedness plan | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 5 | 29-5 | 5. Preparedness and planning for service restoration | 2019 plan | 2153.4085 | 0 | 2153.4085 | 4 | 538.3521 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.5. | Preparedness and planning for service restoration
Emergency planning and preparedness | 29 | 5 | 29-5 | 5. Preparedness and planning for service restoration | 2019 actual | 9994.986 | 585.423 | 9409.563 | 16 | 624.6866 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.5. | Preparedness and planning for service restoration
Emergency planning and preparedness | 29 | 5 | 29-5 | 5. Preparedness and planning for service restoration | 2020 | 11230.867 | 0 | 11230.867 | 30 | 374.3622 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.5. | Preparedness and planning for service restoration
Emergency planning and preparedness | 29 | 5 | 29-5 | 5. Preparedness and planning for service restoration | 2021 | 11600.721 | 0 | 11600.721 | 30 | 386.6907 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.5. | Preparedness and planning for service restoration
Emergency planning and preparedness | 29 | 5 | 29-5 | 5. Preparedness and planning for service restoration | 2022 | 11956.387 | 0 | 11956.387 | 30 | 398.5462 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.5. | Preparedness and planning for service restoration
Emergency planning and preparedness | 29 | 5 | 29-5 | 5. Preparedness and planning for service restoration | 2020-2022 plan total | 34787.975 | 0 | 34787.975 | 90 | 386.5331 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.9.5. | Preparedness and planning for service restoration
Emergency planning and preparedness | 29 | 6 | 29-6 | 6. Protocols in place to learn from wildfire events | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 6 | 29-6 | 6. Protocols in place to learn from wildfire events | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 6 | 29-6 | 6. Protocols in place to learn from wildfire events | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 6 | 29-6 | 6. Protocols in place to learn from wildfire events | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 6 | 29-6 | 6. Protocols in place to learn from wildfire events | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 6 | 29-6 | 6. Protocols in place to learn from wildfire events | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Emergency planning and preparedness | 29 | 7 | 29-7 | 7. Customer research and education (DEP-4) | 2019 plan | 919.05 | 0 | 919.05 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.10.1.4 | Community engagement
Emergency planning and preparedness | 29 | 7 | 29-7 | 7. Customer research and education (DEP-4) | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as they are covered in Initiative 2, Table 29. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.10.1.4 | Community engagement
Emergency planning and preparedness | 29 | 7 | 29-7 | 7. Customer research and education (DEP-4) | 2020 | 1409.4079 | 0 | 1409.4079 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.10.1.4 | Community engagement
Emergency planning and preparedness | 29 | 7 | 29-7 | 7. Customer research and education (DEP-4) | 2021 | 1434.0904 | 0 | 1434.0904 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.10.1.4 | Community engagement
Emergency planning and preparedness | 29 | 7 | 29-7 | 7. Customer research and education (DEP-4) | 2022 | 1465.0726 | 0 | 1465.0726 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.10.1.4 | Community engagement
Emergency planning and preparedness | 29 | 7 | 29-7 | 7. Customer research and education (DEP-4) | 2020-2022 plan total | 4308.571 | 0 | 4308.571 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | WMP Program | HFRA | 7.3.10.1.4 | Community engagement
Stakeholder cooperation and community engagement | 30 | 1 | 30-1 | 1. Community engagement | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE met with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and held regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 1 | 30-1 | 1. Community engagement | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE met with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and held regular updates with local emergency officials. In 2019, SCE met with 145 local governments and tribes in HFRA, participated in approximately 80 other meetings and presentations with stakeholders, and held regular updates with County Operational Areas. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 1 | 30-1 | 1. Community engagement | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 1 | 30-1 | 1. Community engagement | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 1 | 30-1 | 1. Community engagement | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 1 | 30-1 | 1. Community engagement | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 2 | 30-2 | 2. Cooperation and best practice sharing with agencies outside CA | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 2 | 30-2 | 2. Cooperation and best practice sharing with agencies outside CA | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 2 | 30-2 | 2. Cooperation and best practice sharing with agencies outside CA | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 2 | 30-2 | 2. Cooperation and best practice sharing with agencies outside CA | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 2 | 30-2 | 2. Cooperation and best practice sharing with agencies outside CA | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 2 | 30-2 | 2. Cooperation and best practice sharing with agencies outside CA | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events per year (2020-2022) with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 3 | 30-3 | 3. Cooperation with suppression agencies | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 3 | 30-3 | 3. Cooperation with suppression agencies | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | Exceeding Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 3 | 30-3 | 3. Cooperation with suppression agencies | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 3 | 30-3 | 3. Cooperation with suppression agencies | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 3 | 30-3 | 3. Cooperation with suppression agencies | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 3 | 30-3 | 3. Cooperation with suppression agencies | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 4 | 30-4 | 4. Forest service and fuel reduction cooperation and joint roadmap | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 4 | 30-4 | 4. Forest service and fuel reduction cooperation and joint roadmap | 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 4 | 30-4 | 4. Forest service and fuel reduction cooperation and joint roadmap | 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 4 | 30-4 | 4. Forest service and fuel reduction cooperation and joint roadmap | 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 4 | 30-4 | 4. Forest service and fuel reduction cooperation and joint roadmap | 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast
Stakeholder cooperation and community engagement | 30 | 4 | 30-4 | 4. Forest service and fuel reduction cooperation and joint roadmap | 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. | Non-WMP Program | No Forecast

## Table 21
Table 21: Risk assessment and mapping
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2. Climate-driven risk map and modelling based on various relevant weather scenarios | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
3. Ignition probability mapping showing the probability of ignition along the electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
4. Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
5. Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
6. Weather-driven risk map and modelling based on various relevant weather scenarios | 2019 plan | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.

## Table 22
Table 22: Situational awareness and forecasting
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Advanced weather monitoring and weather stations (SA-1) | 2019 plan | 6031.067 | 5389.254 | 641.813 | 315 | 19.1462 | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2019 actual | 5520.099 | 4282.182 | 1237.917 | 357 | 15.4625 | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020 | 6832.771 | 5535.885 | 1296.886 | 475 | 14.3848 | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | 5766.528 | 4203.504 | 1563.024 | 475 | 12.1401 | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | 5800.296 | 4203.504 | 1596.792 | 475 | 12.2111 | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | 18399.595 | 13942.893 | 4456.702 | 1425 | 12.912 | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of weather station installations is the unit of measure. Advanced weather monitoring will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
2.1. Continuous monitoring sensors: Distribution Fault Anticipation (DFA) (AT-2.1) | 2019 plan | 69.205 | 0 | 69.205 | 10 | 6.9205 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 2485.151 | 0 | 2485.151 | 24 | 103.548 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | In 2019, SCE developed a plan to engineer, design, and construct 60 DFA units. 54 were constructed. Of those 54, 24 were fully commissioned. The costs for the 2019 work includes the engineering, design, construction of all DFAs and the commissioning of 24 units of the 60 units. The remaining will DFA units will be completed in 2020. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 251.524 | 0 | 251.524 | 36 | 6.9868 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | In the first quarter of 2020, the remaining 36 DFAs will be commissioned and monitored. In 2020 engineering will monitor the DFA pilot installations to assess the success of the pilot. No other DFAs will be deployed until the assessment in 2020 is complete. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 9900.683 | 9646.065 | 254.618 | 150 | 66.0046 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 19850.149 | 19850.149 | 0 | 300 | 66.1672 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 30002.356 | 29496.214 | 506.142 | 486 | 61.7332 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA, WMPMA | NA | NA | Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.2. Continuous monitoring sensors: Early Fault Detection (EFD) evaluation (AT-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020.
| 2020 | 511.228 | 0 | 511.228 | 25 | 20.4491 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Monitor DFA during 2020; Estimated 2.5 miles per sensor install. The mileage values are estimated total miles covered and may include HFRA, non-HFRA, and Underground circuitry. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 2587.583 | 0 | 2587.583 | 225 | 11.5004 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Monitor DFA during 2021; Estimated 2.5 miles per sensor install. The mileage values are estimated total miles covered and may include HFRA, non-HFRA, and Underground circuitry. Continuous monitoring sensors will not directly reduce risk drivers, but instead provides awareness for potential situations which may be able to identified and remediated to avoid related consequences. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns for 2022 for this Initiative are "UNKNOWN" as the scope and strategy are yet to be determined for 2022. This determination will be made after careful study and review of the 2020-2021 work.
| 2020-2022 plan total | 3098.811 | 0 | 3098.811 | 250 | 12.3952 | CFO: Vegetation EFF: All Equipment Failures | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.3. Continuous monitoring sensors: transmission open phase detection (SH-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 actual. This initiative was successfully piloted in 2109 and cost were charged to internal overhead.
| 2020 | 295.0149 | 0 | 295.0149 | 323.5 | 0.91195 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | Instead of "Line miles to be treated", select circuit miles within the HFRA is the unit of measure. The “Other risk drivers addressed” columns “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | 288.0542 | 0 | 288.0542 | 315.8671 | 0.91195 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | The "Line miles to be treated" and "Spend/ treated line mile" columns are "UNKNOWN" because the expansion of deployment is based on the success/fail criteria in 2020. The “Other risk drivers addressed” column is “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | 281.891 | 0 | 281.891 | 315.8671 | 0.89244 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | The "Line miles to be treated" and "Spend/ treated line mile" columns are "UNKNOWN" because the expansion of deployment is based on the success/fail criteria in 2020. The “Other risk drivers addressed” column is “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | 864.96 | 0 | 864.96 | 955.2343 | 0.90572 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | In Compliance | SB901 OIR | Instead of "Line miles to be treated", select circuit miles within the HFRA is the unit of measure. The “Other risk drivers addressed” columns “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
3. Fault indicators for detecting faults on electric lines and equipment | 2019 plan | 4285.315 | 4285.315 | 0 | 265 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 2134.572 | 2134.572 | 0 | 132 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 1649.442 | 1649.442 | 0 | 102 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 2522.676 | 2522.676 | 0 | 156 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 2522.676 | 2522.676 | 0 | 156 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 6694.794 | 6694.794 | 0 | 414 | 16.171 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Line miles to be treated" columns are system-wide numbers that include HFRA applications. Fault indicators will not directly reduce risk drivers, but inform areas where additional situational awareness is beneficial. The "Ignition probability drivers targeted" column is “NA” as this activity doesn't target specific ignition probability drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
4.1 .Forecast of a fire risk index, fire potential index, or similar: Fire Potential Index phase II (SA-2) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 6, Table 22
4.2. Forecast of a fire risk index, fire potential index, or similar: fuel sampling program (SA-5) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA | NA | NA | The "Total per initiative spend" for 2019 actual is "NA" as this initiative is covered in Initiative 4.3, Table 22. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020 | 631.824 | 0 | 631.824 | 6500 | 0.097204 | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | 645.23 | 0 | 645.23 | 6500 | 0.099266 | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | 659.17 | 0 | 659.17 | 6500 | 0.10141 | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | 1936.224 | 0 | 1936.224 | 19500 | 0.099294 | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA | NA | NA | Instead of "Line miles to be treated", HFRA square miles is the unit of measure with SCE's Fuel Sampling to cover a sample population of 4,500 square miles within the HFRA. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
4.3. Forecast of a fire risk index, fire potential index, or similar: surface & canopy fuels mapping (SA-6) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this was not a 2019 activity.
| 2019 actual | 92.814 | 0 | 92.814 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020 | 1380.72 | 0 | 1380.72 | 14179 | 0.097378 | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | 208.891 | 0 | 208.891 | 14179 | 0.014732 | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | 213.404 | 0 | 213.404 | 14179 | 0.015051 | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | 1803.015 | 0 | 1803.015 | 42537 | 0.042387 | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA | NA | NA | Surface and canopy vegetation mapping allows for better fire spread calculations which will allow for more accurate assessment of risk. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Surface & Canopy Fuels Mapping will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
4.4. Forecast of a fire risk index, fire potential index, or similar: remote sensing / satellite fuel moisture (SA-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | 0 | 0 | 0 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020 | 1534.133 | 0 | 1534.133 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | 1827.798 | 0 | 1827.798 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | 0 | 0 | 0 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | 3361.931 | 0 | 3361.931 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Remote Sensing will improve wildfire modeling capabilities but will not directly reduce risk drivers. This wildfire modeling will improve PSPS decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
4.5. Forecast of a fire risk index, fire potential index, or similar: fire science enhancements (SA-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | 773.444 | 0 | 773.444 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020 | 1534.133 | 0 | 1534.133 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | 1566.684 | 0 | 1566.684 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | 1600.531 | 0 | 1600.531 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | 4701.348 | 0 | 4701.348 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. This mitigation is focused on improving overall understanding of environmental factors (weather and fuels) and their relationship with ignition drivers for utility caused wildfires. These models will be used to inform wildfire mitigation activities and real-time decision making for PSPS events. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
5. Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | 2019 plan | 4900.349 | 2283.22 | 2617.129 | NA | NA | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2019 actual | 1436.1416 | 969.552 | 466.5895 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020 | 1844.2773 | 219.8177 | 1624.4596 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | 1763.6359 | 0 | 1763.6359 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | 1801.7376 | 0 | 1801.7376 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | 5409.6508 | 219.8177 | 5189.833 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
6. Weather forecasting and estimating impacts on electric lines and equipment (SA-3) | 2019 plan | 4495.8845 | 3759.22 | 736.6645 | NA | NA | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2019 actual | 7006.235 | 5678.791 | 1327.444 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020 | 2456.619 | 799.555 | 1657.064 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | 2899.377 | 1102.466 | 1796.911 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | 1835.925 | 0 | 1835.925 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | 7191.921 | 1902.021 | 5289.9 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. Weather modeling and forecast of fire ignition and spread will not directly reduce risk drivers, but informs the primary inputs into the PSPS decision that reduce wildfire risk. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
7. Develop Asset & Reliability & Risk Analytics Capability (RA-1, SA-4) | 2019 plan | 509.798 | 509.798 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 857.51 | 857.51 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 6692.174 | 6692.174 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 6692.174 | 6692.174 | 0 | NA | NA | CFO: Vegetation Wire to Wire EFF: All | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement. Asset risk and fire consequence modeling will not directly reduce risk drivers, but inform prioritization and mitigation deployment decisions. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.

## Table 23
Table 23: Grid design and system hardening
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Capacitor maintenance and replacement program | 2019 plan | 10300 | 10094 | 206 | 116 | 88.7931 | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 9700 | 9506 | 194 | 111 | 87.3874 | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 4994.914 | 4895.016 | 99.898 | 58 | 86.1192 | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 3694.425 | 3620.537 | 73.888 | UNKNOWN | UNKNOWN | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. The "Line miles to be treated" and "Spend/treated line mile" columns for 2021 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 3801.285 | 3725.259 | 76.026 | UNKNOWN | UNKNOWN | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. The "Line miles to be treated" and "Spend/treated line mile" columns for 2022 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 12490.624 | 12240.812 | 249.812 | 58 | NA | EFF: Capacitor Bank Failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" column reflects Capacitor Replacement costs only. Maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. Instead of "Line miles to be treated", notification count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
2.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: maintenance | 2019 plan | 208.228 | 0 | 208.228 | 138 | 1.5089 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 208.228 | 0 | 208.228 | 138 | 1.5089 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 200 | 0 | 200 | 138 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 200 | 0 | 200 | 138 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 200 | 0 | 200 | 138 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 600 | 0 | 600 | 414 | 1.4493 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - meter alarm down energized conductor (MADEC) (AT-1) | 2019 plan | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | 107088 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | 321264 | NA | EFF: Conductor Splice | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because the costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", all T&D overhead circuit miles is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.3.1. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - ground fault neutralizer (GFN) (AT-3.1) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 2586.8161 | 0 | 2586.8161 | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 3684.7183 | 0 | 3684.7183 | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile" columns are "NA" because the pilot is currently only scheduled for 2020 and 2021. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 6271.5344 | 0 | 6271.5344 | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this pilot. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.3.2. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - arc suppression coil (AT-3.2) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 511.2285 | 0 | 511.2285 | 1 | 511.2285 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", units is the unit of measure. The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 724.5233 | 0 | 724.5233 | 1 | 724.5233 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", units is the unit of measure. The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation.
| 2020-2022 plan total | 1235.7517 | 0 | 1235.7517 | 2 | 617.8759 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", units is the unit of measure. The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.3.3. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - rapid earth current fault limiter - isolation transformer (AT-3.3) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" column is "NA" because costs to implement this initiative are part of normal O&M and are not incremental wildfire-related costs. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this activity. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 408.9828 | 0 | 408.9828 | 1 | 408.9828 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", the number of pilot locations is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 1035.0332 | 0 | 1035.0332 | 1 | 1035.0332 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", the number of pilot locations is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | NA | WMPMA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation
| 2020-2022 plan total | 1444.016 | 0 | 1444.016 | 2 | 722.008 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", the number of pilot locations is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.4. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - distribution open phase detection (AT-3.4) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2020 | 511.2285 | 0 | 511.2285 | 5 | 102.2457 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit locations is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2021/2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because 2021/2022 scope will be determined by success/fail criteria of pilot; There is no identified plan/spend at this point for the evaluation
| 2020-2022 plan total | 511.2285 | 0 | 511.2285 | 5 | 102.2457 | EFF: Conductor Splice/Clamp/Connector | Under assessment/pilot | UNKNOWN | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit locations is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.5. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: alternative technology evaluations - high impedance relay evaluations (AT-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2020 | 306.7371 | 0 | 306.7371 | 2 | 153.3685 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", protection relay setting counts are the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the 2021 scope and strategy for this initiative are not known at this time.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the 2022 scope and strategy for this initiative are not known at this time.
| 2020-2022 plan total | 306.7371 | 0 | 306.7371 | 2 | 153.3685 | CFO: All EFF: All | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", protection relay setting counts are the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.6. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker installs/ replacements | 2019 plan | 1094.6142 | 1094.6142 | 0 | 8 | 136.8268 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 1094.6142 | 1094.6142 | 0 | 8 | 136.8268 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 2479.5502 | 2479.5502 | 0 | 16 | 154.9719 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 3506.1286 | 3506.1286 | 0 | 26 | 134.8511 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 3589.2027 | 3589.2027 | 0 | 24 | 149.5501 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 9574.8815 | 9574.8815 | 0 | 66 | 145.074 | CFO: All EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", circuit breaker count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2.7. Circuit breaker maintenance and installation to de-energize lines upon detecting a fault: circuit breaker relay hardware for fast curve (SH-6) | 2019 plan | 9052.155 | 9052.155 | 0 | 189 | 47.895 | CFO: All EFF: All | 0.20024 | 22.1207 | NA | New | NA | GSRPMA | NA | NA | The original budget allocated in 2019 under the GS&RP consisted of relays actually being replaced in 2019. However, given resource, outage, procurement constraints, no relays were able to be replaced in 2019. Subsequent decision was to instead focus on developing a full deployment plan for relay replacements in years 2020, 2021 and 2022. This goal to develop a full execution plan was achieved by YE2019. Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 838.6407 | 838.6407 | 0 | NA | NA | CFO: All EFF: All | NA | NA | NA | New | NA | GSRPMA | NA | NA | The "Line Miles to Be Treated", "Spend/treated line mile", "Risk reduction", and "Risk-spend efficiency" columns are "NA" because all 2019 spend was for project scoping and engineering/design charges for work to be done in 2020. No relays were replaced in 2019. Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 5170.0123 | 5170.0123 | 0 | 55 | 94.0002 | CFO: All EFF: All | 0.05653 | 11.3578 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 11091.9206 | 11091.9206 | 0 | 81 | 136.9373 | CFO: All EFF: All | 0.080815 | 7.8089 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 10492.3202 | 10492.3202 | 0 | 74 | 141.7881 | CFO: All EFF: All | 0.07166 | 7.5317 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 26754.2531 | 26754.2531 | 0 | 210 | 127.4012 | CFO: All EFF: All | 0.209 | 8.4138 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", relay count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
3.1. Covered conductor installation: covered conductor (SH-1) | 2019 plan | 42231.377 | 42231.377 | 0 | 95.7026 | 441.2773 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 1.1417 | 27.0351 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure.
| 2019 actual | 239911.075 | 239911.075 | 0 | 372 | 644.9222 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 5.6187 | 22.5382 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure. The 372 miles includes some overhead conductor program and 4 kV cutover work. Costs also include design, engineering, and pre-construction for 2020 work.
| 2020 | 454368.671 | 454368.671 | 0 | 1000 | 454.3687 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 11.5251 | 25.9579 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure.
| 2021 | 656352.963 | 656352.963 | 0 | 1400 | 468.8235 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 14.8451 | 23.8746 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure.
| 2022 | 771814.5744 | 771814.5744 | 0 | 1600 | 482.3841 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 15.1985 | 21.3876 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure.
| 2020-2022 plan total | 1882536.2084 | 1882536.2084 | 0 | 4000 | 470.6341 | CFO: Vegetation Balloon Animal EFF: Wire to wire | 41.5686 | 23.4004 | Covered Conductor provides ancillary benefits to EFF and wire to wire contact, in addition to CFO (primary benefit). | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", miles of covered conductor installed is the unit of measure.
3.2. Covered conductor installation: tree attachment remediation (SH-10) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin as a stand-alone initiative until after the 2019 WMP had been filed.
| 2019 actual | 9383.4546 | 9383.4546 | 0 | 101 | 92.9055 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 15182.9007 | 15182.9007 | 0 | 481.244 | 31.5493 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 24 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 22431.7113 | 22431.7113 | 0 | 689.0836 | 32.553 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 25 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 26377.7612 | 26377.7612 | 0 | 787.5241 | 33.4945 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 63992.3731 | 63992.3731 | 0 | 1957.8517 | 32.685 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 23 | Refer to Initiative 3.1, Table 27 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", tree attachments to be remediated is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
3.3. Covered conductor installation: alternative technology implementation - vibration dampers (AT-4) | 2019 plan | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | EFF: Conductor | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Updates to vibration damper standards do not address risk drivers, the standards are used to inform construction requirements. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
4. Covered conductor maintenance | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as activity is covered in Initiative 12.1, Table 23
5. Crossarm maintenance, repair, and replacement | 2019 plan | NA | NA | NA | 4714 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 51.3005 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2019 actual | NA | NA | NA | 6575 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 26.9372 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2020 | NA | NA | NA | 3570 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1309 | 13.8328 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2021 | NA | NA | NA | 21 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5837 | 30.5076 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2022 | NA | NA | NA | 79 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1013 | 25.7553 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. The numbers in future years are expected to increase as new work is identified from SCE's inspection programs. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2020-2022 plan total | NA | NA | NA | 3670 | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 6.8159 | 21.2781 | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because maintenance costs are at the work order level, and grouped with other maintenance efforts, and are thus are not possible to be separated. SCE does not track/unitize B-materials. Instead of "Line miles to be treated", notifications in HFTD is the unit of measure. The numbers in future years are expected to increase as new work is identified from SCE's inspection programs. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
6.1. Distribution pole replacement and reinforcement, including with composite poles: composite poles and crossarms (SH-3) | 2019 plan | 5136.4128 | 5136.4128 | 0 | 1100 | 4.6695 | EFF: Other Equipment Types | 0.020945 | 4.0778 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | NA | NA | NA | 1421 | NA | EFF: Other Equipment Types | 0.027057 | 3.6015 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/ treated line mile" columns are "NA" as the activity is covered in Initiative 3.1, Table 23. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 56832.5745 | 56832.5745 | 0 | 17304.48 | 3.2843 | EFF: Other Equipment Types | 0.20902 | 3.901 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. WCCP scope is 11,700 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 64010.258 | 64010.258 | 0 | 18952.672 | 3.3774 | EFF: Other Equipment Types | 0.21875 | 3.7275 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. WCCP scope is 16,381 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 73642.7252 | 73642.7252 | 0 | 21238.768 | 3.4674 | EFF: Other Equipment Types | 0.23398 | 3.558 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. WCCP scope is 18,721 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 194485.5577 | 194485.5577 | 0 | 57495.92 | 3.3826 | EFF: Other Equipment Types | 0.66175 | 3.7171 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.1 | The total spend includes incremental costs for all composite pole replacements in HFRA. 2020-2022 WCCP scope is 46,802 poles. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
6.2. Distribution pole replacement and reinforcement, including with composite poles: deteriorated pole | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because SCE did not forecast deteriorated poles in 2019 in the HFRA specifically.
| 2019 actual | 78010.5 | 78010.5 | 0 | 3930 | 19.85 | EFF: Other Equipment Types | 0.069761 | 3.3574 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 64895.818 | 64895.818 | 0 | 3724 | 17.4264 | EFF: Other Equipment Types | 0.040377 | 3.5016 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 30041.011 | 30041.011 | 0 | 1698 | 17.692 | EFF: Other Equipment Types | 0.017841 | 3.3933 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 16506.094 | 16506.094 | 0 | 906 | 18.2186 | EFF: Other Equipment Types | 0.0092342 | 3.2916 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 111442.923 | 111442.923 | 0 | 6328 | 17.6111 | EFF: Other Equipment Types | 0.067452 | 3.4425 | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The total spend for this initiative includes cost for traditional scope of program. Instead of "Line miles to be treated", pole count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
6.3. Distribution pole replacement and reinforcement, including with composite poles: poles identified during inspections | 2019 plan | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | EFF: Other Equipment Types | NA | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 9.1, Table 24. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
7. Expulsion fuse replacement: branch line protection strategy (SH-4) | 2019 plan | NA | NA | NA | NA | NA | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 17, Table 23. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as this initiative is covered in Initiative 17, Table 23 Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 16798.587 | 9053.603 | 7744.984 | 3025 | 5.5533 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.13224 | 8.1174 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 1153.7059 | 0 | 1153.7059 | 421 | 2.7404 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.017856 | 16.019 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 1333.6069 | 0 | 1333.6069 | 481 | 2.7726 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.019809 | 15.5497 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 19285.9 | 9053.603 | 10232.297 | 3927 | 4.9111 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 0.1699 | 9.0958 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
8.1. Grid topology improvements to mitigate or reduce PSPS events: PSPS driven grid hardening work (SH-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 9, Table 23.
| 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 2.8417 | 57.5051 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 2.7589 | 61.7133 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 2.6786 | 65.3369 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
| 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | CFO: All EFF: All | 8.2792 | 61.2737 | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend", and "Spend/ treated line mile" columns are "UNKNOWN" because this analysis won't be available until after the 2020 WMP filing. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative. Values in columns H-K are repeated from the risk columns in Table 26, Initiative 5.
8.2. Grid topology improvements to mitigate or reduce PSPS events: microgrid assessment (PSPS-8) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | UNKNOWN | NA | NA | In 2019, SCE performed an assessment of Microgrids and the scope will be finalized in the Microgrids OIR filing in February 2020. The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to perform the assessment are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020.
| 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" for this Initiative because the strategy for Microgrids will be finalized in Microgrids OIR filing in February 2020.
9. Installation of system automation equipment: installation of system automation equipment - remote controlled automatic reclosers settings update (SH-5) | 2019 plan | 4880.5935 | 4880.5935 | 0 | 50 | 97.6119 | NA | 0.0084341 | 1.7281 | NA | New | NA | GSRPMA, FHPMA | NA | NA | Instead of "Line miles to be treated", number of devices is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2019 actual | 11110.4579 | 11110.4579 | 0 | 76 | 146.1902 | NA | 0.01282 | 1.1539 | NA | New | NA | GSRPMA, FHPMA | NA | NA | Instead of "Line miles to be treated", number of devices is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2020 | 8639.9018 | 8480.5953 | 159.3066 | 98 | 88.1623 | NA | 0.016049 | 1.929 | NA | New | NA | GSRPMA, FHPMA | NA | NA | The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2021 | 0 | 0 | 0 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | UNKNOWN | NA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because there is no sectionalizing device specific program beyond what was defined in GSRP
| 2022 | 0 | 0 | 0 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | UNKNOWN | NA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because there is no sectionalizing device specific program beyond what was defined in GSRP
| 2020-2022 plan total | 8639.9018 | 8480.5953 | 159.3066 | 98 | 88.1623 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA, FHPMA | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" because there is no sectionalizing device specific program beyond what was defined in GSRP
10. Maintenance, repair, and replacement of connectors, including hotline clamps | 2019 plan | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure.
| 2019 actual | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure.
| 2020 | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure.
| 2021 | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure.
| 2022 | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure.
| 2020-2022 plan total | NA | NA | NA | NA | NA | EFF: Splice/Clamp/Connector | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. The "Line miles to be treated" column is "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Connector failures may result in conductor failure.
11. Mitigation of impact on customers and other residents affected during PSPS event | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
12. Other corrective action | 2019 plan | NA | NA | NA | 29067 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | NA | NA | NA | 36180 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | NA | NA | NA | 5001 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | NA | NA | NA | 275 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | NA | NA | NA | 4972 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | NA | NA | NA | 10248 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
12.1. Other corrective action: distribution remediations (SH-12.1) | 2019 plan | 191737.288 | 102808.058 | 88929.23 | NA | NA | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 51.3005 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2019 actual | 394728.731 | 229991.525 | 164737.206 | 49783 | 7.929 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 26.9372 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2020 | 327535.32 | 147130.025 | 180405.295 | 58617 | 5.5877 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1309 | 13.8328 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2021 | 125039.955 | 46436.115 | 78603.84 | 28225 | 4.4301 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5837 | 30.5076 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2022 | 85021.209 | 29742.715 | 55278.494 | 17793 | 4.7784 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1013 | 25.7553 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
| 2020-2022 plan total | 537596.484 | 223308.855 | 314287.629 | 104635 | 5.1378 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 6.8159 | 21.2781 | Some types of object contact, primarily veg. | New | NA | WMPMA | In compliance | GO 95 | Instead of "Line miles to be treated", notifications is the unit of measure. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 9.1
12.2. Other corrective action: transmission remediations (SH-12.2) | 2019 plan | 28947.348 | 9911.729 | 19035.619 | NA | NA | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.11797 | 3.3835 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1
| 2019 actual | 83879.5404 | 54146.98 | 29732.5604 | 10000 | 8.388 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 1.5237 | 13.5585 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1
| 2020 | 71320.128 | 64895.987 | 6424.141 | 5222 | 13.6576 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.031263 | 0.53918 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1
| 2021 | 12413.696 | 8838.793 | 3574.903 | 2026.1685 | 6.1267 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.030243 | 2.9172 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1
| 2022 | 10246.413 | 7262.283 | 2984.13 | 1833.7685 | 5.5876 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.025122 | 3.0555 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1
| 2020-2022 plan total | 93980.237 | 80997.063 | 12983.174 | 9081.9371 | 10.348 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.086627 | 1.1313 | NA | New | NA | WMPMA | In compliance | GO 95 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because SCE did not plan for remediations Instead of "Line miles to be treated", notifications is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Values in columns H-K are repeated from the risk columns in Table 24, Initiative 10.1
12.3. Other corrective action: generation remediations (SH-12.3) | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because inspections started in March 2019 and did not plan for remediations.
| 2019 actual | 387.907 | 0 | 387.907 | UNKNOWN | NA | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure. The number of notifications in the HFRA is unavailable for 2019.
| 2020 | 200 | 40 | 160 | 200 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure.
| 2021 | 200 | 40 | 160 | 200 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure.
| 2020-2022 plan total | 400 | 80 | 320 | 400 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 | Instead of "Line miles to be treated", projected notifications is the unit of measure.
13. Pole loading infrastructure hardening and replacement program based on pole loading assessment program | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Total per initiative spend", "Line miles to be treated" and "Spend/ treated line mile" columns are "NA" because SCE did not forecast specific HFRA pole loading program poles in 2019.
| 2019 actual | 89444.1 | 89444.1 | 0 | 4506 | 19.85 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure.
| 2020 | 45097.094 | 45097.094 | 0 | 2588 | 17.4255 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure.
| 2021 | 15475.673 | 15475.673 | 0 | 874 | 17.7067 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure.
| 2022 | 29344.168 | 29344.168 | 0 | 1612 | 18.2036 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure.
| 2020-2022 plan total | 89916.935 | 89916.935 | 0 | 5074 | 17.7211 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Refer to Initiative 6, Table 23 | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", number of poles are the unit of measure.
14. Transformers maintenance and replacement | 2019 plan | 2733.0178 | 2678.3574 | 54.6604 | 1503 | 1.8184 | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | NA | NA | NA | 1737 | NA | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 2598.0201 | 2546.0597 | 51.9604 | 1885 | 1.3783 | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 2466.8506 | 2417.5136 | 49.337 | UNKNOWN | UNKNOWN | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Line miles to be treated" and "Spend/treated line mile" columns for 2021 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 2504.398 | 2454.31 | 50.088 | UNKNOWN | UNKNOWN | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | The "Line miles to be treated" and "Spend/treated line mile" columns for 2022 for this Initiative are "UNKNOWN" as the scope is yet to be determined. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 7569.268 | 7417.883 | 151.385 | NA | NA | EFF: Transformer failure | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 31.1 | Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
15. Transmission tower maintenance and replacement | 2019 plan | 5658 | 0 | 5658 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 3978 | 0 | 3978 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 5558 | 0 | 5558 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 5679.1644 | 0 | 5679.1644 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 5838.181 | 0 | 5838.181 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 17075.3454 | 0 | 17075.3454 | NA | NA | EFF: Other Equipment Types | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, Rule 44.3 | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because SCE does not track/utilize B-materials. Instead of "Line miles to be treated", notifications are the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
16. Undergrounding of electric lines and/or equipment: undergrounding overhead conductor (SH-2) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" column is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Columns are "NA" because undergrounding to start in 2021. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | New | NA | WMPMA | NA | NA | Columns are "NA" because undergrounding to start in 2021. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 22507.486 | 22507.486 | 0 | 6 | 3751.2477 | CFO: All EFF: All | 0.1017 | 4.8431 | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 42457.2637 | 42457.2637 | 0 | 11 | 3859.7512 | CFO: All EFF: All | 0.18097 | 4.7005 | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 64964.7496 | 64964.7496 | 0 | 17 | 3821.4559 | CFO: All EFF: All | 0.28267 | 4.7508 | NA | New | NA | WMPMA | NA | NA | The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
17. Updates to grid topology to minimize risk of ignition in HFTDs | 2019 plan | 46122.0545 | 46122.0545 | 0 | 7511 | 6.1406 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 2.2463 | 48.7041 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 70549.876 | 70292.689 | 257.187 | 7765 | 9.0856 | CFO: All EFF: Conductor failure, fuse failure, arrester failure, switch failure Wire-to-wire contact | 2.2809 | 32.3308 | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", location count is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | New | NA | GSRPMA | NA | NA | The "Total per initiative spend", "Line miles to be treated", "Spend/treated line mile", "Ignition probability drivers targeted", "Risk reduction", "Risk-spend efficiency", and "Other risk drivers addressed" columns are "UNKNOWN" because the program scope is yet to be targeted for 2020, 2021 and 2022. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
18. Transmission overhead (TOH) review (SH-9) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2020 | NA | NA | NA | 4352 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is blank because the cost will hit overhead, so there will be no memo account treatment The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | 4352 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | 4352 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is blank because the cost will hit overhead, so there will be no memo account treatment The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | 13056 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | NA | NA | NA | NA | NA | The "Total per-initiative spend" and "Spend/ treated line mile" columns are "NA" because costs are expected to be labor only for this internal assessment using existing resources. Instead of "Line miles to be treated", total HFRA Transmission miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is blank because the cost will hit overhead, so there will be no memo account treatment The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
19. Legacy facilities (SH-11) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2020 | 2173.733 | 1304.24 | 869.493 | 3 | 724.5775 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 4912.135 | 4686.226 | 225.909 | 6 | 818.6892 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 4177.642 | 3985.513 | 192.129 | 6 | 696.2737 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 11263.51 | 9975.979 | 1287.531 | 15 | 750.9007 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. . The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.

## Table 24
Table 24: Asset management and inspections
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Detailed inspections of distribution electric lines and equipment: distribution HFRA detailed inspections (previously ODI) | 2019 plan | 814.286 | 0 | 814.286 | 54551 | 0.014927 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile columns are "NA" as those are included in Initiative 9.1, Table 24
| 2020 | 2276.0632 | 0 | 2276.0632 | 54959 | 0.041414 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2021 | 2983.4434 | 0 | 2983.4434 | 69743 | 0.042778 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2022 | 2631.2872 | 0 | 2631.2872 | 59681 | 0.044089 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2020-2022 plan total | 7890.7938 | 0 | 7890.7938 | 184383 | 0.042796 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
2. Detailed inspections of Transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile columns are "NA" as those are included in Initiative 10.1, Table 24
| 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile columns are "NA" as those are included in Initiative 10.1, Table 24
| 2020 | 1149.8967 | 0 | 1149.8967 | 12011 | 0.095737 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2021 | 1192.2138 | 0 | 1192.2138 | 13935 | 0.085555 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2022 | 1059.1106 | 0 | 1059.1106 | 12011 | 0.088178 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2020-2022 plan total | 3401.2211 | 0 | 3401.2211 | 37957 | 0.089607 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Refer to Initiative 10.1, Table 24 | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
3. Improvement of Inspections | 2019 plan | 467.825 | 0 | 467.825 | 5681 | 0.082349 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets.
| 2019 actual | 467.825 | 0 | 467.825 | 5681 | 0.082349 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets.
| 2020 | 382.576 | 0 | 382.576 | 5681 | 0.067343 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | 5681 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | The "Total per-initiative spend" is "UNKNOWN" as the scope for 2021 is still to be determined. Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | 5681 | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | The "Total per-initiative spend" is "UNKNOWN" as the scope for 2022 is still to be determined. Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets.
| 2020-2022 plan total | 382.576 | 0 | 382.576 | 5681 | 0.067343 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | GO 165 | Instead of "Line miles to be treated", HFRA circuit miles is the unit of measure. For distribution SCE assumes 37% of HFRA line miles (3,636 miles) will be inspected per year; for transmission SCE assumes 47% of HFRA line miles (2,045 miles) will be inspected per year. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The "If new: Memorandum account" column is "NA" because costs are part of existing training budgets.
4. Infrared inspections of distribution electric lines and equipment: infrared inspection of energized overhead distribution facilities and equipment (IN-3) | 2019 plan | 465.807 | 0 | 465.807 | 4911.9535 | 0.094831 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0046894 | 10.0673 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | NA | NA | NA | NA | NA | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0046894 | 0 | NA | NA | NA | NA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The "Total per initiative spend" column is "NA" because the 2019 actuals are included in initiative 9.1, table 24 The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 400.752 | 0 | 400.752 | 4058 | 0.098756 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0018798 | 4.796 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 405.6813 | 0 | 405.6813 | 4510 | 0.089952 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0020282 | 5.1747 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 410.3229 | 0 | 410.3229 | 4510 | 0.090981 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0019691 | 5.0238 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 1216.7561 | 0 | 1216.7561 | 13078 | 0.093038 | EFF: Cap Bank Conductor Fuse Splice/Clamp/Connector Transformer Lightning arrestor Switch | 0.0058771 | 4.9982 | NA | New | NA | GSRPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
5. Infrared inspections of transmission electric lines and equipment: infrared inspection, corona scanning, and high definition imagery of energized overhead transmission facilities and equipment (IN-4) | 2019 plan | 5669.26 | 0 | 5669.26 | 1000 | 5.6693 | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | NA
| 2019 actual | NA | NA | NA | NA | NA | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | NA | NA | NA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The "Total per initiative spend" column is "NA" because the 2019 actuals are included in initiative 10.1, table 24
| 2020 | 3503.6115 | 0 | 3503.6115 | 1000 | 3.5036 | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | NA
| 2021 | 3533.6033 | 0 | 3533.6033 | UNKNOWN | UNKNOWN | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Line miles to be treated” and "Spend/treated line mile" columns are "UNKNOWN" for 2021 because there are no miles estimated at this time
| 2022 | 3564.017 | 0 | 3564.017 | UNKNOWN | UNKNOWN | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Line miles to be treated” and "Spend/treated line mile" columns are "UNKNOWN" for 2022 because there are no miles estimated at this time
| 2020-2022 plan total | 10601.2319 | 0 | 10601.2319 | NA | NA | EFF: Conductor Crossarm Insulator Splice/Clamp/Connector | 0 | 0 | All types of object contact Contamination | New | NA | WMPMA | In Compliance | GO 95, Rule 31.2 GO 95, Rule 31.1 | The “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2021 and 2022 because there are no miles estimated at this time
6. Intrusive pole inspections (IPI) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as there was no 2019 plan for this initiative
| 2019 actual | 892.687 | 0 | 892.687 | 21464 | 0.04159 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years.
| 2020 | 1302 | 0 | 1302 | 30156 | 0.043175 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years.
| 2021 | 1320 | 0 | 1320 | 30156 | 0.043772 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years.
| 2022 | 1342 | 0 | 1342 | 30156 | 0.044502 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years.
| 2020-2022 plan total | 3964 | 0 | 3964 | 90468 | 0.043817 | EFF: Other Equipment | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | Exceeding Compliance | GO 165 | Instead of "Line miles to be treated", number of poles to be inspected is the unit of measure. As a compliance program, intrusive inspections were not included in the risk modeling. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. IPI ‘exceeds’ compliance because GO165 requires an IPI every 20 years and SCE does one every 10 years.
7. LiDAR inspections of distribution electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24.
8. LiDAR inspections of transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #10.2, Table 24.
9.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: distribution high fire risk-informed inspections (IN-1.1) | 2019 plan | 53897.2487 | 0 | 53897.2487 | 380000 | 0.14183 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 51.3005 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure.
| 2019 actual | 72644.5017 | 0 | 72644.5017 | 380000 | 0.19117 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 12.5897 | 26.9372 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The spend for 2019 includes both ground and aerial inspections (Initiative 9.2, Table 24). Instead of "Line miles to be treated", number of assets is the unit of measure.
| 2020 | 2276.0632 | 0 | 2276.0632 | 54959 | 0.041414 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1309 | 13.8328 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure.
| 2021 | 2983.4434 | 0 | 2983.4434 | 69743 | 0.042778 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5837 | 30.5076 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure.
| 2022 | 2631.2872 | 0 | 2631.2872 | 59681 | 0.044089 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1013 | 25.7553 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure.
| 2020-2022 plan total | 7890.7938 | 0 | 7890.7938 | 184383 | 0.042796 | EFF: Capacitor bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 6.8159 | 21.2781 | Some types of object contact, primarily veg. | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", number of assets is the unit of measure.
9.1.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: asset defect detection using machine learning object detection (AT-5) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
| 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
9.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections (IN-6.1) | 2019 plan | NA | NA | NA | NA | NA | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5664 | 35.629 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 9.1, Table 24.
| 2019 actual | NA | NA | NA | NA | NA | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.5664 | 0 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 9.1, Table 24.
| 2020 | 40059.1628 | 0 | 40059.1628 | 255000 | 0.15709 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 2.1668 | 10.5529 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure.
| 2021 | 26193.2359 | 0 | 26193.2359 | 165000 | 0.15875 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 1.3221 | 21.1049 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure.
| 2022 | 26492.925 | 0 | 26492.925 | 165000 | 0.16056 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 1.2618 | 49.8605 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure.
| 2020-2022 plan total | 92745.3238 | 0 | 92745.3238 | 585000 | 0.15854 | CFO: Animal Vegetation EFF: Capacitor Bank Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor Switch | 4.7506 | 16.1986 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count is the unit of measure.
9.2.1. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: unmanned aerial vehicles (UAV) (AT-2.2) | 2019 plan | 461.3691 | 0 | 461.3691 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. Instead of ""Line miles to be treated"", all T&D overhead circuit miles is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 1.0479 | 0 | 1.0479 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Total per initiative spend" column is not final due to work performed in 2019 and not yet billed. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 413.0213 | 0 | 413.0213 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 358.4573 | 0 | 358.4573 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 335.6847 | 0 | 335.6847 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 1107.1633 | 0 | 1107.1633 | NA | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" while activity is in pilot/research phase. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
9.2.2. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: UAS operations training (OP-3) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2020 | 271.0301 | 0 | 271.0301 | 50 | 5.4206 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 840.7872 | 0 | 840.7872 | 80 | 10.5098 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 245.4147 | 0 | 245.4147 | 50 | 4.9083 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 1357.232 | 0 | 1357.232 | 180 | 7.5402 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated" , operator count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
10.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: transmission risk-informed inspections in HFRA (IN-1.2) | 2019 plan | 5917.957 | 0 | 5917.957 | 51179 | 0.11563 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.11797 | 3.3835 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure.
| 2019 actual | 28499.1157 | 0 | 28499.1157 | 41952 | 0.67933 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 1.5237 | 13.5585 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The spend for 2019 includes both ground and aerial inspections (Initiative 10.2, Table 24). Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure.
| 2020 | 1149.8967 | 0 | 1149.8967 | 10489 | 0.10963 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.031263 | 0.53918 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets
| 2021 | 1192.2138 | 0 | 1192.2138 | 13935 | 0.085555 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.030243 | 2.9172 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets
| 2022 | 1059.1106 | 0 | 1059.1106 | 12011 | 0.088178 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.025122 | 3.0555 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets
| 2020-2022 plan total | 3401.2211 | 0 | 3401.2211 | 36435 | 0.09335 | CFO: Animal Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.086627 | 1.1313 | NA | New | NA | WMPMA | Exceeding Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", the number of structures inspected in HFRA is the unit of measure. SCE modified the inspection cycles for some of its transmission overhead inspection assets to exceed compliance requirements such that, in 2020 and beyond, SCE plans to annually inspect approximately 47% of its high fire transmission assets
10.2. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: aerial inspections - transmission (IN-6.2) | 2019 plan | NA | NA | NA | NA | NA | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | NA | NA | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 10.1, Table 24.
| 2019 actual | NA | NA | NA | NA | NA | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | NA | NA | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" for 2019 because this initiative's costs and scope are included in Initiative 10.1, Table 24.
| 2020 | 11868.6198 | 0 | 11868.6198 | 33500 | 0.35429 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.020154 | 0.83127 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2021 | 11970.218 | 0 | 11970.218 | 33500 | 0.35732 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.019434 | 1.3588 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2022 | 12073.2458 | 0 | 12073.2458 | 33500 | 0.3604 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.018739 | 1.3326 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2020-2022 plan total | 35912.0836 | 0 | 35912.0836 | 100500 | 0.35733 | CFO: Vegetation EFF: Conductor Crossarm Insulator Splice/Clamp/Connector Transformer Lightning Arrestor | 0.058327 | 1.1087 | NA | New | NA | WMPMA | In Compliance | GO 95 Rules 31.1 and 31.2 | Instead of "Line miles to be treated", structure count the unit of measure.
10.2.1. Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations: assessment of partial discharge for transmission facilities (AT-6) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because this initiative was not an active 2019 initiative.
| 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
| 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | All columns are "UNKNOWN" as the scope and strategy for this initiative are not known at this time.
11. Patrol inspections of distribution electric lines and equipment | 2019 plan | 0 | 0 | 0 | 7352 | 0 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2019 actual | 0 | 0 | 0 | 7352 | 0 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2020 | 1200 | 0 | 1200 | 7352 | 0.16322 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2021 | 1012 | 0 | 1012 | 7352 | 0.13765 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2022 | 1039 | 0 | 1039 | 7352 | 0.14132 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
| 2020-2022 plan total | 3251 | 0 | 3251 | 22056 | 0.1474 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 165 | Instead of "Line miles to be treated", structure count the unit of measure.
12. Patrol inspections of transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 2, Table 24.
13. Pole loading assessment program to determine safety factor | 2019 plan | 2159.394 | 0 | 2159.394 | 18271 | 0.11819 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2019 actual | 1879.409 | 0 | 1879.409 | 15902 | 0.11819 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020 | 287.988 | 0 | 287.988 | 2369 | 0.12157 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2018 GRC | NA | NA | NA | All columns are "NA" as this initiative is to be completed in 2020
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2018 GRC | NA | NA | NA | All columns are "NA" as this initiative is to be completed in 2020
| 2020-2022 plan total | 287.988 | 0 | 287.988 | 2369 | 0.12157 | NA | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95 | Instead of "Line miles to be treated", pole count is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
14. Quality assurance / quality control of inspections: Quality Oversight / Quality Control (IN-2) | 2019 plan | NA | NA | NA | 7500 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | 17109 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | 15000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | 15000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | 15000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | 45000 | NA | CFO: Vegetation EFF: All | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. Instead of "Line miles to be treated", structure count is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
15. Substation inspections | 2019 plan | 18015.009 | 0 | 18015.009 | 5500 | 3.2755 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure.
| 2019 actual | 19214.171 | 0 | 19214.171 | 5591 | 3.4366 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure.
| 2020 | 18943.038 | 0 | 18943.038 | 5500 | 3.4442 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure.
| 2021 | 19259.712 | 0 | 19259.712 | 5500 | 3.5018 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure.
| 2022 | 20473.074 | 0 | 20473.074 | 5500 | 3.7224 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure.
| 2020-2022 plan total | 58675.824 | 0 | 58675.824 | 16500 | 3.5561 | EFF: All | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | Some types of object contact, primarily veg. | Existing | 2018 GRC | NA | In Compliance | ISO WECC GO 174 | Instead of "Line miles to be treated", count of substation inspections is the unit of measure.
15.1 Failure Modes and Effects Analysis (FMEA) (IN-7) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile", and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
16. Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations: generation risk-informed inspections in HFRA (IN-5) | 2019 plan | 400 | 0 | 400 | 400 | 1 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure.
| 2019 actual | 252.9923 | 0 | 252.9923 | 449 | 0.56346 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure.
| 2020 | 157.8599 | 0 | 157.8599 | 200 | 0.7893 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure. 50% of applicable assets per year
| 2021 | 162.2616 | 0 | 162.2616 | 200 | 0.81131 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure. 50% of applicable assets per year
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | The "Total per initiative spend", "Line miles to be treated", and "Spend/treated line mile" columns are UNKNOWN because the need for 2022 inspections will be evaluated after analysis of all assets in 2020-2021 is completed.
| 2020-2022 plan total | 320.1216 | 0 | 320.1216 | 400 | 0.8003 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | Refer to Initiative 9.1, Table 24 | New | NA | WMPMA | Exceeding Compliance | GO 95 Rule 31.2 | Instead of "Line miles to be treated", asset count is the unit of measure.

## Table 25
Table 25: Vegetation management and inspections
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Additional efforts to manage community and environmental impacts | 2019 plan | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and the expense is absorbed in budget for communications, and it is not broken out by Wild Fire group today. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2. Detailed inspections of vegetation around distribution electric lines and equipment | 2019 plan | 11378.9144 | 0 | 11378.9144 | 9827 | 1.1579 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 5944.3773 | 0 | 5944.3773 | 9827 | 0.6049 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 11385.882 | 0 | 11385.882 | 9827 | 1.1586 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 11396.674 | 0 | 11396.674 | 9827 | 1.1597 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 11407.062 | 0 | 11407.062 | 9827 | 1.1608 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 34189.618 | 0 | 34189.618 | 29481 | 1.1597 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
3. Detailed inspections of vegetation around transmission electric lines and equipment | 2019 plan | 508.2339 | 0 | 508.2339 | 4352 | 0.11678 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 1868.0634 | 0 | 1868.0634 | 4352 | 0.42924 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 508.727 | 0 | 508.727 | 4352 | 0.11689 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 509.029 | 0 | 509.029 | 4352 | 0.11696 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 509.339 | 0 | 509.339 | 4352 | 0.11704 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 1527.095 | 0 | 1527.095 | 13056 | 0.11696 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
4. Emergency response vegetation management due to red flag warning or other urgent conditions | 2019 plan | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because conditions do not drive additional scope. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
5. Fuel management and reduction of “slash” from vegetation management activities | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because "slash" from vegetation management activities are disposed or recycled by trimming/removal contractors.
5.1. Fuel management and reduction of “slash” from vegetation management activities: expanded pole brushing (VM-2) | 2019 plan | 909.4192 | 0 | 909.4192 | 98913 | 0.0091941 | EFF: Capacitor Bank Crossarm Insulator | 0.020923 | 89.306 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 1646.0911 | 0 | 1646.0911 | 163149 | 0.010089 | EFF: Capacitor Bank Crossarm Insulator | 0.13339 | 83.1545 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 4156.9252 | 0 | 4156.9252 | 300000 | 0.013856 | EFF: Capacitor Bank Crossarm Insulator | 0.24498 | 60.2554 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 4208.0555 | 0 | 4208.0555 | 300000 | 0.014027 | EFF: Capacitor Bank Crossarm Insulator | 0.23784 | 58.5004 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 4256.2018 | 0 | 4256.2018 | 300000 | 0.014187 | EFF: Capacitor Bank Crossarm Insulator | 0.23091 | 56.7965 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 12621.1826 | 0 | 12621.1826 | 900000 | 0.014024 | EFF: Capacitor Bank Crossarm Insulator | 0.71373 | 58.5174 | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4292 | Instead of "Line miles to be treated", number of poles to be brushed is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
5.2. Fuel management and reduction of “slash” from vegetation management activities: expanded clearances for legacy facilities (VM-3) | 2019 plan | NA | NA | NA | NA | NA | NA | Insufficient data to model risk | Insufficient data to model risk | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Insufficient data to model risk | Insufficient data to model risk | NA | NA | NA | NA | NA | NA | All columns are NA because this initiative was not an active 2019 initiative.
| 2020 | 1217.4395 | 0 | 1217.4395 | 80 | 15.218 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 1055.9668 | 0 | 1055.9668 | 32 | 32.999 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 1088.7505 | 0 | 1088.7505 | 24 | 45.3646 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 3362.1568 | 0 | 3362.1568 | 136 | 24.7217 | NA | Insufficient data to model risk | Insufficient data to model risk | NA | New | NA | WMPMA | Exceeding Compliance | PRC 4291 and 4293 | Instead of "Line miles to be treated", number of assets is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
6. Improvement of inspections | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #13, Table 25
7. LiDAR inspections of vegetation around distribution electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #9.2, Table 24
8. LiDAR inspections of vegetation around transmission electric lines and equipment | 2019 plan | 3721.8542 | 0 | 3721.8542 | 3658 | 1.0175 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 4516.581 | 0 | 4516.581 | 1559 | 2.8971 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 1467.4411 | 0 | 1467.4411 | 1227 | 1.196 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 1485.4906 | 0 | 1485.4906 | 1227 | 1.2107 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 1502.4868 | 0 | 1502.4868 | 1227 | 1.2245 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 4455.4185 | 0 | 4455.4185 | 3681 | 1.2104 | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program and not a WMP initiative | NA | New | NA | WMPMA | Exceeding Compliance | FAC-003-4 | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
9. Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
10. Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #16.2, Table 25
11. Patrol inspections of vegetation around distribution electric lines and equipment | 2019 plan | 7255.4223 | 0 | 7255.4223 | 96 | 75.5773 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 15072.089 | 0 | 15072.089 | 96 | 157.0009 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 5060.603 | 0 | 5060.603 | 96 | 52.7146 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #20, Table 25
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #20, Table 25
| 2020-2022 plan total | 5060.603 | 0 | 5060.603 | 96 | NA | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
12. Patrol inspections of vegetation around transmission electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25
| 2020 | 2177.009 | 0 | 2177.009 | 96 | 22.6772 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | Instead of "Line miles to be treated", the canyons patrolled is the unit of measure. Patrols include 3 main activities: Operation Santa Ana, Canyon Patrols and At-Risk Circuit Patrols. These 3 activities occur in 96 canyons that are patrolled annually. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative #11, Table 25
| 2020-2022 plan total | 2177.009 | 0 | 2177.009 | 96 | 22.6772 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
13. Quality assurance / quality control of inspections: quality control (VM-5) | 2019 plan | 0 | 0 | 0 | 4700 | 0 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 985.2004 | 0 | 985.2004 | 4700 | 0.20962 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 4000 | 0 | 4000 | 8100 | 0.49383 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 5000 | 0 | 5000 | 8100 | 0.61728 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 5000 | 0 | 5000 | 8100 | 0.61728 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 14000 | 0 | 14000 | 24300 | 0.57613 | CFO: Vegetation | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | In the "Line miles to be treated" column the number of line miles shown includes both HFRA and non-HFRA line miles. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
14. Recruiting and training of vegetation management personnel | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because recruitment costs are embedded in personnel time, and not broken out
15. Remediation of at-risk species | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" because the team does not track this activity separately.
16. Removal and remediation of trees with strike potential to electric lines and equipment | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 16.1, Table 25
16.1. Removal and remediation of trees with strike potential to electric lines and equipment: hazard tree (VM-1) | 2019 plan | 56894.7409 | 0 | 56894.7409 | 125000 | 0.45516 | CFO: Vegetation | 0.34135 | 5.9998 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | 15209.6163 | 0 | 15209.6163 | 129485 | 0.11746 | CFO: Vegetation | 0.44888 | 29.5129 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | 54097.2977 | 0 | 54097.2977 | 75000 | 0.7213 | CFO: Vegetation | 1.3234 | 25.0199 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | 59475.8515 | 0 | 59475.8515 | 75000 | 0.79301 | CFO: Vegetation | 1.4138 | 24.6199 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | 72035.267 | 0 | 72035.267 | 75000 | 0.96047 | CFO: Vegetation | 1.6975 | 24.6914 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | 185608.4163 | 0 | 185608.4163 | 225000 | 0.82493 | CFO: Vegetation | 4.4347 | 24.7655 | NA | New | NA | GSRPMA | Exceeding Compliance | GO 95 Rule 35; PRC 4293 | Instead of "Line miles to be treated", number of tree assessments is the unit of measure. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
16.2. Removal and remediation of trees with strike potential to electric lines and equipment: DRI quarterly inspections and tree removals (VM-4) | 2019 plan | 41481.9813 | 0 | 41481.9813 | 14179 | 2.9256 | CFO: Vegetation | 1.1914 | 28.7203 | NA | New | NA | CEMA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 32598.997 | 0 | 32598.997 | 14179 | 2.2991 | CFO: Vegetation | 1.1914 | 36.5463 | NA | New | NA | CEMA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 36470.011 | 0 | 36470.011 | 14179 | 2.5721 | CFO: Vegetation | 1.1567 | 31.7157 | NA | New | NA | CEMA | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 36973.531 | 0 | 36973.531 | 14179 | 2.6076 | CFO: Vegetation | 1.123 | 30.3726 | NA | New | NA | UNKNOWN | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The "If new: Memorandum account" column is "UNKNOWN" because it is pending 2021 GRC decision The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 37564.933 | 0 | 37564.933 | 14179 | 2.6493 | CFO: Vegetation | 1.0903 | 29.0238 | NA | New | NA | UNKNOWN | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The "If new: Memorandum account" column is "UNKNOWN" because it is pending 2021 GRC decision The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 111008.475 | 0 | 111008.475 | 42537 | 2.6097 | CFO: Vegetation | 3.3699 | 30.3574 | NA | New | NA | UNKNOWN | NA | NA | The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The "If new: Memorandum account" column is "UNKNOWN" because it is pending 2021 GRC decision The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
17. Substation inspections | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 15, Table 24
18. Substation vegetation management | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this activity is not broken out of the routine compliance program.
19. Vegetation inventory system | 2019 plan | 421 | 0 | 421 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2019 actual | 5381 | 4960 | 421 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2020 | 3771 | 2111 | 1660 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2021 | 3000 | 2850 | 150 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2022 | 1000 | 950 | 50 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
| 2020-2022 plan total | 7771 | 5911 | 1860 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | Existing | 2018 GRC | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because they are not applicable fields of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no compliance targets associated with this initiative.
20. Vegetation management to achieve clearances around electric lines and equipment | 2019 plan | 76281.452 | 0 | 76281.452 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | Please note that the forecast plan costs include line clearance work in HFRA and non-HFRA. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates.
| 2019 actual | 247104.99 | 0 | 247104.99 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | Please note that the recorded costs include line clearance work in HFRA and non-HFRA and therefore on a different basis than the forecasts included in the 2019 WMP. We are unable to separate the recorded costs for wildfire mitigation and HFRA line clearance costs at this time for 2019. SCE is modifying its business practices to track wildfire mitigation and HFRA line clearance costs separately going forward. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates.
| 2020 | 76281.452 | 0 | 76281.452 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2020 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates.
| 2021 | 64169.652 | 0 | 64169.652 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2021 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates.
| 2022 | 60868.687 | 0 | 60868.687 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2022 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates.
| 2020-2022 plan total | 201319.791 | 0 | 201319.791 | NA | NA | CFO: Vegetation | Initiative addressed by Traditional Program | No RSE was calculated as this is already a compliance program | NA | Existing | 2018 GRC | NA | In Compliance | GO 95, PRC 4293, FAC-003-4 | The 2020-2022 spend plan includes vegetation management to achieve clearances in HFRA only. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. Vegetation management activities to maintain clearance distances from transmission and distribution lines and equipment are conducted in HFRA and non-HFRA. In HFRA, this work includes three distinct activities: 1. Expanding clearances, where achievable, to D.17-12-024 recommended distances, 2. Maintaining those expanded clearances, and 3. Maintaining 4 feet clearances per D.17-12-024 minimum requirements where SCE cannot achieve expanded clearances due to operational constraints. All three of these activities in HFRA are for wildfire mitigation and reducing the probability and consequence of potential ignitions. SCE’s line clearance forecasts currently include these three activities in HFRA and line clearance maintenance in non-HFRA. The forecasts included are subject to change as there are considerable uncertainties associated with the scope of work (number of trees trimmed or removed). SCE is also modifying its business practices to record the costs to track wildfire mitigation-related costs separately. Though risk analysis is guiding some line clearance activities, the line clearance scope in HFRA is driven by Commission requirement and recommendations to mitigate wildfire risks and not informed by RSE estimates.

## Table 26
Table 26: Grid operations and protocols
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Automatic recloser operations | 2019 plan | 284.8915 | 0 | 284.8915 | 150 | 1.8993 | NA | 0.010796 | 2.212 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 418.265 | 0 | 418.265 | NA | NA | NA | 0.015181 | 1.3664 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | 0.016049 | 1.929 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | 0 | 0 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | 0.016049 | 1.929 | NA | New | NA | GSRPMA | NA | NA | Costs for installation of system automation equipment are discussed in Initiative 9, Table 23; costs for recloser settings and operations are part of base O&M. This mitigation program allows SCE to remotely change the mode of protection during elevated fire weather threat. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
1.1. Annual SOB 322 review (OP-1) | 2019 plan | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | 14179 | NA | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | WMPMA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2. Crew-accompanying ignition prevention and suppression resources and services | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Entire initiative is "NA" because SCE does not utilize crew-accompanying ignition prevention and suppression resources and services.
3. Personnel work procedures and training in conditions of elevated fire risk | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 8, Table 29
4. Protocols for PSPS re-energization | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" as this initiative is covered in Initiative 5, Table 26
5. PSPS events and mitigation of PSPS impacts | 2019 plan | 1044.3883 | 0 | 1044.3883 | NA | NA | CFO: All EFF: All | 2.927 | 151.3942 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 4216.9108 | 0 | 4216.9108 | NA | NA | CFO: All EFF: All | 2.927 | 77.2542 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 7258.891 | 787.908 | 6470.983 | NA | NA | CFO: All EFF: All | 2.8417 | 57.5051 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 7442.645 | 812.974 | 6629.671 | NA | NA | CFO: All EFF: All | 2.7589 | 61.7133 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 7667.501 | 836.489 | 6831.012 | NA | NA | CFO: All EFF: All | 2.6786 | 65.3369 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 22369.037 | 2437.371 | 19931.666 | NA | NA | CFO: All EFF: All | 8.2792 | 61.2737 | NA | New | NA | FRMMA, GSRPMA | NA | NA | This initiative include PSPS event-related costs only; costs for mitigation of PSPS impacts are discussed in Initiative 5.1 - 5.6 and Initiative 7, Table 26. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. RSE calculation includes costs from all PSPS events and mitigation activities. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
5.1. PSPS events and mitigation of PSPS impacts: community resource centers (PSPS-2) | 2019 plan | 783.15 | 0 | 783.15 | 13 | 60.2423 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 45.7336 | 0 | 45.7336 | 13 | 3.518 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 2274.806 | 1212.013 | 1062.793 | 36 | 63.189 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 2107.708 | 737.864 | 1369.844 | 50 | 42.1542 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 1368.88 | 0 | 1368.88 | 50 | 27.3776 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 5751.394 | 1949.877 | 3801.517 | 136 | 42.2897 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", number of incremental Community Resource Centers is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
5.2. PSPS events and mitigation of PSPS impacts: customer resiliency equipment incentives (PSPS-3) | 2019 plan | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | NA | NA | Refer to Initiative 5, Table 26 | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | SCE is currently in the process of setting up a pilot for this Initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | UNKNOWN | UNKNOWN | UNKNOWN | 1 | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | SCE is currently in the process of setting up a pilot for this Initiative. The costs for 2020 are still to be determined. Instead of "Line miles to be treated", number of customers in the program is the unit of measure. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 3685.0947 | 0 | 3685.0947 | UNKNOWN | UNKNOWN | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", number of customers in the program is the unit of measure. The scope for 2021 is still to be determined. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 3758.5213 | 0 | 3758.5213 | UNKNOWN | UNKNOWN | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", number of customers in the program is the unit of measure. The scope for 2022 is still to be determined. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 7443.616 | 0 | 7443.616 | UNKNOWN | UNKNOWN | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | NA | NA | Instead of "Line miles to be treated", number of customers in the program is the unit of measure. SCE has forecasted a rollout of this Initiative based on the successful completion of the pilot done in 2020. The number of customers for 2021-2022 are still to be determined. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
5.3. PSPS events and mitigation of PSPS impacts: income qualified critical care (IQCC) customer battery backup incentive program (PSPS-4) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 actual as this initiative did not begin until 2020.
| 2020 | 9240.9856 | 0 | 9240.9856 | 2500 | 3.6964 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | 1431.7112 | 0 | 1431.7112 | 408 | 3.5091 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | 1462.642 | 0 | 1462.642 | 408 | 3.5849 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | 12135.3387 | 0 | 12135.3387 | 3316 | 3.6596 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | SB 167 | Instead of "Line miles to be treated", number of customers eligible for the program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
5.4. PSPS events and mitigation of PSPS impacts: MICOP partnership (PSPS-5) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | The MICOP partnership began in Q4 of 2019, the majority of deliverables will be executed in 2020. 2019 spend is "NA" because the MICOP grant partnership was funded through corporate philanthropy shareholder budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019.
| 2020 | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2020 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019.
| 2021 | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2021 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019.
| 2022 | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2022 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019.
| 2020-2022 plan total | UNKNOWN | 0 | UNKNOWN | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2021-2022 spend is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative for work done in 2019.
5.5. PSPS events and mitigation of PSPS impacts: independent living centers partnership (PSPS-6) | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | PSPS Decision, 2019 WMP Decision | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because this initiative was funded through corporate philanthropy shareholder budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2020 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2021 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | In compliance | PSPS Decision, 2019 WMP Decision | 2022 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In compliance | PSPS Decision, 2019 WMP Decision | 2020-2022 spend and scope is "UNKNOWN" because future funding is determined on a yearly basis and evaluated based on program execution and annual Corporate Contributions budget. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
5.6. PSPS events and mitigation of PSPS impacts: community outreach (PSPS-7) | 2019 plan | 1123.6182 | 0 | 1123.6182 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Total per-initiative spend" is "NA" as the 2019 actuals for this initiative are included with Initiative 2, Table 29. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 439.6565 | 0 | 439.6565 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 362.2616 | 0 | 362.2616 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 303.5939 | 0 | 303.5939 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 1105.512 | 0 | 1105.512 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
5.7. PSPS events and mitigation of PSPS impacts: wildfire infrastructure protection team additional staffing (OP-2) | 2019 plan | 493 | 0 | 493 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 1372.9081 | 0 | 1372.9081 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 1817.4655 | 0 | 1817.4655 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 1817.9094 | 0 | 1817.9094 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 1818.3709 | 0 | 1818.3709 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 5453.7457 | 0 | 5453.7457 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
5.8. PSPS events and mitigation of PSPS impacts: SGIP resiliency | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until 2020.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 actuals as this initiative did not begin until 2020.
| 2020 | 69280 | NA | NA | 3675 | 18.8517 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | 35280 | NA | NA | 1835 | 19.2262 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | 35280 | NA | NA | 1835 | 19.2262 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | 139840 | NA | NA | 7345 | 19.0388 | NA | Under assessment/pilot | No RSE was calculated as the purpose of the assessment is to learn and assess the effectiveness of the mitigation. | NA | New | NA | California Equity Resiliency Budget (Public Purpose Funds) | In Compliance | D.19-09-027 and D.20-01-021 | The funding for this initiative come from the Public Purpose Funds. Instead of "Line miles to be treated", umber of customers in the SGIP program is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
6. Stationed and on-call ignition prevention and suppression resources and services | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services.
| 2019 actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services.
| 2020 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services.
| 2021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services.
| 2022 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns for this Initiative are "NA" because SCE does not utilize stationed and on-call ignition prevention and suppression resources and services.
7. De-energization notifications (PSPS-1) | 2019 plan | 1275.7816 | 0 | 1275.7816 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative.
| 2019 actual | 1556.7495 | 0 | 1556.7495 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative.
| 2020 | 1415.2887 | 0 | 1415.2887 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative.
| 2021 | 1445.3183 | 0 | 1445.3183 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative.
| 2022 | 1476.5431 | 0 | 1476.5431 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative.
| 2020-2022 plan total | 4337.1502 | 0 | 4337.1502 | NA | NA | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | Refer to Initiative 5, Table 26 | New | NA | WMPMA | In compliance | PSPS OIR | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative.

## Table 27
Table 27: Data governance
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Centralized repository for data | 2019 plan | 3400 | 2700 | 700 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed.
| 2019 actual | 2377.4 | 2071.4 | 306 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed.
| 2020 | 11688.6 | 11132 | 556.6 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed.
| 2021 | 18021.683 | 16843.284 | 1178.399 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed.
| 2022 | 9080.96 | 8108 | 972.96 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed.
| 2020-2022 plan total | 38791.243 | 36083.284 | 2707.959 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. Reporting for the SB901 activities is from a consolidated data repository (SAS VA). There is however no single integrated data store that contains all the data for the WFMP. See Section 5.3.7 for a list of the data sets and how the data is managed.
2. Collaborative research on utility ignition and/or wildfire | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
3. Documentation and disclosure of wildfire-related data and algorithms | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
4. Tracking and analysis of near miss data | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative. There is no single integrated data repository against which the algorithms and models are run. The data sets that are used and how they are managed is captured in the narrative document for Section 5.3.7.

## Table 28
Table 28: Resource allocation methodology
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Allocation methodology development and application | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2. Risk reduction scenario development and analysis | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
3. Risk spend efficiency analysis | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend" and "Spend/treated line mile" columns are "NA" because costs to implement this initiative are used as shared resources and the incremental wildfire-related costs are not tracked at this level. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
4. Organizational Support - PMO, OCM, and wildfire-related IT support | 2019 plan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All columns are "NA" for the 2019 plan as this initiative did not begin until after the 2019 WMP had been filed.
| 2019 actual | 61614.6 | 18790.871 | 42823.729 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 78518.986 | 32117.396 | 46401.59 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 31314.893 | 6555.037 | 24759.856 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 23495.035 | 2434.952 | 21060.083 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 133328.914 | 41107.385 | 92221.529 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, WMPMA, GSRPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.

## Table 29
Table 29: Emergency planning and preparedness
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Adequate and trained workforce for service restoration (DEP-2) | 2019 plan | 2610.1046 | 0 | 2610.1046 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 1440.7269 | 0 | 1440.7269 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 1721.6811 | 0 | 1721.6811 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 1758.2118 | 0 | 1758.2118 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 1796.1963 | 0 | 1796.1963 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 5276.0892 | 0 | 5276.0892 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | WMPMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
2. Community outreach, public awareness, and communications efforts (DEP-1.1 - DEP-1.3, DEP-3) | 2019 plan | 1423.242 | 0 | 1423.242 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2019 Actual | 6449.956 | 0 | 6449.956 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020 | 9109.5679 | 0 | 9109.5679 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | 9302.8547 | 0 | 9302.8547 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | 9503.8344 | 0 | 9503.8344 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | R-1812005 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | 27916.257 | 0 | 27916.257 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA, GSRPMA | In Compliance | D. 19-017-015 | This initiative activity includes costs associated with customer engagement, direct customer mailings, and town hall community meetings. The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
3. Customer support in emergencies | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
4. Disaster and emergency preparedness plan | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
5. Preparedness and planning for service restoration | 2019 plan | 2153.4085 | 0 | 2153.4085 | 4 | 538.3521 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | 9994.986 | 585.423 | 9409.563 | 16 | 624.6866 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 11230.867 | 0 | 11230.867 | 30 | 374.3622 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 11600.721 | 0 | 11600.721 | 30 | 386.6907 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 11956.387 | 0 | 11956.387 | 30 | 398.5462 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 34787.975 | 0 | 34787.975 | 90 | 386.5331 | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | GSRPMA | NA | NA | Instead of "Line miles to be treated", the number of patrols is the unit of measure. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
6. Protocols in place to learn from wildfire events | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | NA | NA | NA | In Compliance | GO 166 | The "Total per initiative spend", "Spend/treated line mile" and "Existing/ new" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not tracked as incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
7. Customer research and education (DEP-4) | 2019 plan | 919.05 | 0 | 919.05 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Total per initiative spend", “Line miles to be treated” and "Spend/treated line mile" columns are "NA" as they are covered in Initiative 2, Table 29. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | 1409.4079 | 0 | 1409.4079 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | 1434.0904 | 0 | 1434.0904 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | 1465.0726 | 0 | 1465.0726 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | 4308.571 | 0 | 4308.571 | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | FRMMA | NA | NA | The "Line miles to be treated" and "Spend/treated line mile" columns are "NA" because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.

## Table 30
Table 30: Stakeholder cooperation and community engagement
Initiative activity | Year | Total per-initiative spend | Subtotal A: Capital expenditure | Subtotal B: Operating expenses | Line miles to be treated | Spend/ treated line mile | Ignition probability drivers targeted | Risk reduction | Risk-spend efficiency | Other risk drivers addressed | Existing/ new | Existing: What proceeding has reviewed program | If new: Memorandum account | In / exceeding compliance with regulations | Cite associated rule | Comments
1. Community engagement | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE met with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and held regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE met with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and held regular updates with local emergency officials. In 2019, SCE met with 145 local governments and tribes in HFRA, participated in approximately 80 other meetings and presentations with stakeholders, and held regular updates with County Operational Areas. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | ESRB 8 D. 19-017-015 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns are "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. The "Line miles to be treated" columns is "NA", instead SCE intends to meet with local government and other stakeholders and tribal officials in SCE's HFRA to review SCE's WMP and PSPS protocols and hold regular updates with local emergency officials. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts.
2. Cooperation and best practice sharing with agencies outside CA | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. Instead SCE intends to present or share wildfire lessons learned at a minimum of 10 events per year (2020-2022) with audiences outside of California. Audiences could be a combination of technical, government agencies, industry associations, utilities or universities outside of California. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
3. Cooperation with suppression agencies | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | Exceeding Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | In Compliance | PRC 4292 and 4293 | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The “Other risk drivers addressed” column is “NA” as there are no secondary risk reduction drivers directly addressed by this initiative.
4. Forest service and fuel reduction cooperation and joint roadmap | 2019 plan | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2019 actual | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2021 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2022 | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.
| 2020-2022 plan total | NA | NA | NA | NA | NA | NA | Supporting activity | No RSE was created as this is an enabling activity that indirectly, rather than directly, reduces risk. | NA | New | NA | NA | NA | NA | The "Total per initiative spend", "Spend/treated line mile" and "If new: Memorandum account" columns is "NA" because costs to implement this initiative are part of normal labor hours and are not incremental wildfire-related costs. In addition, the “Line miles to be treated” column is “NA” because line miles treated is not an applicable field of measurement for this initiative. The "Ignition probability drivers targeted" and “Other risk drivers addressed” columns are “NA” as this initiative doesn't target specific ignition probability or other risk drivers but instead supports SCE's overall wildfire mitigation efforts. The “In / exceeding compliance with regulations” and “Cite associated rule” columns are “NA” because there are no statutory compliance targets associated with this initiative.