## DCR
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
4847 | Devers-Colorado River |  | 22970 | 17800 | 40770
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 1400 | 500 | 1900
| 2 | Engineering and Design | 286 | 150 | 436
| 3 | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  | 1686 | 650 | 2336
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | -1000 | 0 | -1000
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | -1000 | 0 | -1000
Construction
| 1 | Civil and Structural Construction | 13270 | 9300 | 22570
| 2 | Electrical Construction | 394 | 0 | 394
| 3 | Construction Management Services | 720 | 150 | 870
| Total |  | 14384 | 9450 | 23834
Environmental
| 1 | Environmental | 4000 | 7000 | 11000
| Total |  | 4000 | 7000 | 11000
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 3900 | 700 | 4600
| Total |  | 3900 | 700 | 4600
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## TRTP Seg 3B
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7183 | TRTP Segment 3B |  |  |  | 4574 | 7587 | 12161
[8 empty] | 16860 | 6646 | 2884 | 26390
[8 empty] | TL | HW SS | AC Mitigation | Total
| Project Support | [6 empty] | 537 | 167 | 458 | 1162
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 810 | 500 | 1310 | 135 | 142 | 109 | 386
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0 | 377 | 0 | 339 | 716
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0 | 25 | 25 | 10 | 60
| Total |  |  |  | 810 | 500 | 1310
| Materials | [6 empty] | 1053 | 1283 | 0 | 2336
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0 | 200 |  |  | 200
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0 | 100 |  |  | 100
| 3 |  |  | Transformers | 0 | 0 | 0 |  |  |  | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0 | 100 |  |  | 100
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0 |  | 670 |  | 670
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0 | 653 | 613 |  | 1266
| Total |  |  |  | 0 | 0 | 0
| Construction | [6 empty] | 13420 | 4706 | 2350 | 20476
| 1 |  |  | Civil and Structural Construction | 3014 | 5350 | 8364 | 8789 | 3445 | 2350 | 14584
| 2 |  |  | Electrical Construction | 0 | 0 | 0 | 4431 | 1261 |  | 5692
| 3 |  |  | Construction Management Services | 0 | 0 | 0 | 200 |  |  | 200
| Total |  |  |  | 3014 | 5350 | 8364
Environmental
| 1 | 20 |  | Environmental | 347 | 1120 | 1467 | 833 | 755 | 86 | 1674
| Total |  | 0 |  | 347 | 1120 | 1467
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
| Allocated | [6 empty] | 1850 | 490 | 76 | 2416
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 403 | 617 | 1020 | 1850 | 490 | 76 | 2416
| Total |  |  |  | 403 | 617 | 1020
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 3C
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7014 | TRTP Segment 3C |  |  |  | 542 | 0 | 542
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 305 | 0 | 305
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 305 | 0 | 305
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | -108 | 0 | -108
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | -108 | 0 | -108
Construction
| 1 |  |  | Civil and Structural Construction | 324 | 0 | 324
| 2 |  |  | Electrical Construction Inc. Wire Stringing & Testing | 0 | 0 | 0
| 3 |  |  | Transformers Setting & Testing | 0 | 0 | 0
| Total |  |  |  | 324 | 0 | 324
Environmental
| 1 | 20 |  | Environmental | 0 | 0 | 0
| Total |  | 0 |  | 0 | 0 | 0
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
| Allocated |  |  |  | 0 | 0
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 21 | 0 | 21
| Total |  |  |  | 21 | 0 | 21
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 4
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6435 | TRTP Segment 4 |  |  |  | 1105 | 0 | 1105
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 0 | 0 | 0
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Materials
| 1 |  |  | Steel and Hardware (e.g. Yard 28 Relocation and Storage) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Environmental
| 3 | 20 |  | Environmental | 1073 | 0 | 1073
| Total |  |  |  | 1073 | 0 | 1073
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 32 | 0 | 32
| Total |  |  |  | 32 | 0 | 32
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 5
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
5472 | TRTP Segment 5 |  |  |  | 626 | 3652 | 4278
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | -1916 | 0 | -1916
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | -1916 | 0 | -1916
Materials
| 1 |  |  | Steel and Hardware (e.g. Marker Balls) | -7 | 0 | -7
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | -7 | 0 | -7
Construction
| 1 |  |  | Civil and Structural Construction | 657 | 0 | 657
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 657 | 0 | 657
Environmental
| 1 | 20 |  | Environmental | 1749 | 3652 | 5401
| Total |  |  |  | 1749 | 3652 | 5401
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 143 | 0 | 143
| Total |  |  |  | 143 | 0 | 143
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 6
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
5243 | TRTP Segment 6 |  |  |  | 54774 | 5536 | 60310
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 6783 | 0 | 6783
| 2 | 16 |  | Engineering and Design | 0 |  | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 |  | 0
| Total |  |  |  | 6783 | 0 | 6783
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 464 | 0 | 464
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 464 | 0 | 464
Construction
| 1 |  |  | Civil and Structural Construction | 31635 | 0 | 31635
| 2 |  |  | Electrical Construction |  |  | 0
| 3 |  |  | Construction Management Services |  |  | 0
| Total |  |  |  | 31635 | 0 | 31635
Environmental
| 1 | 20 |  | Environmental | 5706 | 4073 | 9779
| Total |  |  |  | 5706 | 4073 | 9779
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 10186 | 1463 | 11649
| Total |  |  |  | 10186 | 1463 | 11649
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 7
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6438 | TRTP Segment 7 |  |  |  | 67551 | 12092 | 79643
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 2470 | 1224 | 3694
| 2 | 16 |  | Engineering and Design | 0 |  | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 |  | 0
| Total |  |  |  | 2470 | 1224 | 3694
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Construction
| 1 |  |  | Civil and Structural Construction | 57309 | 2760 | 60069
| 2 |  |  | Electrical Construction | 0 |  | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 57309 | 2760 | 60069
Environmental
| 1 | 20 |  | Environmental | 2892 | 7800 | 10692
| Total |  |  |  | 2892 | 7800 | 10692
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 4880 | 308 | 5188
| Total |  |  |  | 4880 | 308 | 5188
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 8
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6439 | TRTP Segment 8 |  |  |  | 157037 | 95239 | 252276
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 8695 | 2929 | 11624
| 2 | 16 |  | Engineering and Design | 0 |  | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 |  | 0
| Total |  |  |  | 8695 | 2929 | 11624
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 472 | 0 | 472
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 |  | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 472 | 0 | 472
Construction
| 1 |  |  | Civil and Structural Construction | 129618 | 84008 | 213626
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 129618 | 84008 | 213626
Environmental
| 1 | 20 |  | Environmental | 4213 | 6587 | 10800
| Total |  |  |  | 4213 | 6587 | 10800
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 3091 | 0 | 3091
| Total |  |  |  | 3091 | 0 | 3091
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 10948 | 1715 | 12663
| Total |  |  |  | 10948 | 1715 | 12663
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 8A CHUG
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7553 | Chino Hills Underground |  |  |  | 48048 | 195760 | 243808
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 12241 | 15105 | 27346
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 12241 | 15105 | 27346
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 700 | 28081 | 28781
| Total |  |  |  | 700 | 28081 | 28781
Construction
| 1 |  |  | Civil and Structural Construction | 18560 | 123951 | 142511
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 18560 | 123951 | 142511
Environmental
| 1 | 20 |  | Environmental | 6037 | 13477 | 19514
| Total |  |  |  | 6037 | 13477 | 19514
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 7200 | 4886 | 12086
| Total |  |  |  | 7200 | 4886 | 12086
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 3310 | 10260 | 13570
| Total |  |  |  | 3310 | 10260 | 13570
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 9
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6440 | TRTP Segment 9 |  | 14887.9 | 0 | 14887.9
Project Support
| 1 | Windhub Sub | 263.7 | 0 | 263.7
| 2 | Whirlwind Sub | 2192.4 | 0 | 2192.4
| 3 | Antelope Sub | 12.6 | 0 | 12.6
| 4 | Vincent Sub | 481 | 0 | 481
| 5 | Other Substations | 1276 |  | 1276
| Total |  | 4225.7 | 0 | 4225.7
Materials
| 1 | Windhub Sub | 0 | 0 | 0
| 2 | Whirlwind Sub | 0 | 0 | 0
| 3 | Antelope Sub | 0 | 0 | 0
| 4 | Vincent Sub | 1500 | 0 | 1500
| 5 | Other Substations | 0 | 0 | 0
| Total |  | 1500 | 0 | 1500
Construction
| 1 | Windhub Sub | 0 | 0 | 0
| 2 | Whirlwind Sub | 0 | 0 | 0
| 3 | Antelope Sub | 0 | 0 | 0
| 4 | Vincent Sub | 6905 | 0 | 6905
| 5 | Other Substations | 0 |  | 0
| Total |  | 6905 | 0 | 6905
Environmental
| 1 | Environmental | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Real Properties
| 1 | Corporate Real Estate | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Windhub Sub | 29.3 | 0 | 29.3
| 2 | Whirlwind Sub | 243.6 | 0 | 243.6
| 3 | Antelope Sub | 1.4 | 0 | 1.4
| 4 | Vincent Sub | 1841 | 0 | 1841
| 5 | Other Substations | 141.9 |  | 141.9
| Total |  | 2257.2 | 0 | 2257.2
Contingency
| 1 | Windhub Sub | 0 | 0 | 0
| 2 | Whirlwind Sub | 0 | 0 | 0
| 3 | Antelope Sub | 0 | 0 | 0
| 4 | Vincent Sub | 0 | 0 | 0
| 5 | Other Substations | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## TRTP Seg 10
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6441 | TRTP Segment 10 |  |  |  | -643 | 0 | -643
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 0 | 0 | 0
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles and Anchor Bolts) | 0 | 0 | 0
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Construction
| 1 |  |  | Civil and Structural Construction | 0 | 0 | 0
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Environmental
| 1 | 20 |  | Environmental | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | -643 | 0 | -643
| Total |  |  |  | -643 | 0 | -643
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## TRTP Seg 11
PIN # | Description |  |  |  | Forecast | Forecast
[5 empty] | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6442 | TRTP Segment 11 |  |  |  | 112985 | 45761 | 158746
Project Support
| 1 | 14 |  | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 7709 | 4001 | 11710
| 2 | 16 |  | Engineering and Design | 0 | 0 | 0
| 3 | 26 |  | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  |  |  | 7709 | 4001 | 11710
Materials
| 1 |  |  | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 1403 | 0 | 1403
| 2 |  |  | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 |  |  | Transformers | 0 | 0 | 0
| 4 |  |  | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 |  |  | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 |  |  | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  |  |  | 1403 | 0 | 1403
Construction
| 1 |  |  | Civil and Structural Construction | 85208 | 28145 | 113353
| 2 |  |  | Electrical Construction | 0 | 0 | 0
| 3 |  |  | Construction Management Services | 0 | 0 | 0
| Total |  |  |  | 85208 | 28145 | 113353
Environmental
| 1 | 20 |  | Environmental | 9995 | 8443 | 18438
| Total |  |  |  | 9995 | 8443 | 18438
Real Properties
| 1 | Contingency |  | Real Properties Acquisitions | -5 | 0 | -5
| Total |  |  |  | -5 | 0 | -5
Allocated
| 1 | Contingency |  | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 8675 | 5172 | 13847
| Total |  |  |  | 8675 | 5172 | 13847
AFUDC
Contingency
| 1 | Contingency |  | Contingency | 0 | 0 | 0
| Total |  |  |  | 0 | 0 | 0

## EITP
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6551 | Eldorado-Ivanpah Transmission |  | 3475 | 0 | 3475
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 475 | 0 | 475
| 2 | Engineering and Design | 318 | 0 | 318
| 3 | Regulatory and Licensing | 0 | 0 | 0
| Total |  | 793 | 0 | 793
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | -81 | 0 | -81
| 2 | Conductor and Conductor Hardware | -56 | 0 | -56
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | -137 | 0 | -137
Construction
| 1 | Civil and Structural Construction | 750 | 0 | 750
| 2 | Electrical Construction | 412 | 0 | 412
| 3 | Construction Management Services | 21 | 0 | 21
| Total |  | 1183 | 0 | 1183
Environmental
| 1 | Environmental | 189 | 0 | 189
| Total |  | 189 | 0 | 189
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 1447 | 0 | 1447
| Total |  | 1447 | 0 | 1447
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## Lugo-Pisgah
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7018 | Lugo-Pisgah Transmission |  | 0 | 0 | 0
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 0 | 0 | 0
| 2 | Engineering and Design | 0 | 0 | 0
| 3 | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction | 0 | 0 | 0
| 2 | Electrical Construction | 0 | 0 | 0
| 3 | Construction Management Services | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Environmental
| 1 | Environmental | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## Red Bluff
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6929 | Red Bluff Substation |  | 13574 | 3330 | 16904
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 1650 | 650 | 2300
| 2 | Engineering and Design | 250 | 150 | 400
| 3 | Regulatory and Licensing | 0 | 0 | 0
| Total |  | 1900 | 800 | 2700
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) |  |  | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction | 7924 | 1530 | 9454
| 2 | Electrical Construction | 0 | 0 | 0
| 3 | Construction Management Services | 250 | 100 | 350
| Total |  | 8174 | 1630 | 9804
Environmental
| 1 | Environmental | 2000 | 600 | 2600
| Total |  | 2000 | 600 | 2600
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 1500 | 300 | 1800
| Total |  | 1500 | 300 | 1800
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## CRSE
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7076/ 7061/7062 | Colorado River Substation Expansion |  | 1677 | 10313 | 11990
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 480 | 2730 | 3210
| 2 | Engineering and Design | 200 | 3125 | 3325
| 3 | Regulatory and Licensing | 0 | 0 | 0
| Total |  | 680 | 5855 | 6535
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 75 | 75
| 2 | Conductor and Conductor Hardware | 0 | 100 | 100
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 25 | 25
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 100 | 200 | 300
| 6 | Civil Materials and Misc Hardware | 50 | 50 | 100
| Total |  | 150 | 450 | 600
Construction
| 1 | Civil and Structural Construction | 100 | 300 | 400
| 2 | Electrical Construction | 0 | 543 | 543
| 3 | Construction Management Services | 25 | 150 | 175
| Total |  | 125 | 993 | 1118
Environmental
| 1 | Environmental | 475 | 1260 | 1735
| Total |  | 475 | 1260 | 1735
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 247 | 1755 | 2002
| Total |  | 247 | 1755 | 2002
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## CRSE 7076 (hidden)
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7076/ 7061/7062 | Colorado River Substation Expansion |  | 997 | 8500 | 9497
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 350 | 2650 | 3000
| 2 | Engineering and Design | 50 | 3025 | 3075
| 3 | Regulatory and Licensing | 0 | 0 | 0
| Total |  | 400 | 5675 | 6075
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) |  |  | 0
| 2 | Conductor and Conductor Hardware |  |  | 0
| 3 | Transformers |  |  | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) |  |  | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) |  |  | 0
| 6 | Civil Materials and Misc Hardware |  |  | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction |  |  | 0
| 2 | Electrical Construction |  |  | 0
| 3 | Construction Management Services |  |  | 0
| Total |  | 0 | 0 | 0
Environmental
| 1 | Environmental | 450 | 1250 | 1700
| Total |  | 450 | 1250 | 1700
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 147 | 1575 | 1722
| Total |  | 147 | 1575 | 1722
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## CRSE 7061 (hidden)
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7061 | New SPS to Trip up to 1,400MW of Generation Under the Devers - Red Bluff 500 kV #1 and #2 Double Contingency |  | 680 | 1813 | 2493
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 130 | 80 | 210
| 2 | Engineering and Design | 150 | 100 | 250
| 3 | Regulatory, Licensing, and Legal Costs |  | 0 | 0
| Total |  | 280 | 180 | 460
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) |  | 75 | 75
| 2 | Conductor and Conductor Hardware |  | 100 | 100
| 3 | Transformers |  | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) |  | 25 | 25
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 100 | 200 | 300
| 6 | Civil Materials and Misc Hardware | 50 | 50 | 100
| Total |  | 150 | 450 | 600
Construction
| 1 | Civil and Structural Construction | 100 | 300 | 400
| 2 | Electrical Construction |  | 543 | 543
| 3 | Construction Management Services | 25 | 150 | 175
| Total |  | 125 | 993 | 1118
Environmental
| 1 | Environmental | 25 | 10 | 35
| Total |  | 25 | 10 | 35
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 100 | 180 | 280
| Total |  | 100 | 180 | 280
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## Whirlwind
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7054/ 7066/ 7067/ 7068/ 7069 | Whirlwind Substation Expansion |  | 19700 | 11000 | 30700
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 300 | 200 | 500
| 2 | Engineering and Design | 1000 | 500 | 1500
| 3 | Regulatory, Licensing, and Legal Costs | 0 | 0 | 0
| Total |  | 1300 | 700 | 2000
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 250 | 200 | 450
| 2 | Conductor and Conductor Hardware | 250 | 150 | 400
| 3 | Transformers | 5500 | 3800 | 9300
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 100 | 100 | 200
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 750 | 4500 | 5250
| 6 | Civil Materials and Misc Hardware | 200 | 100 | 300
| Total |  | 7050 | 8850 | 15900
Construction
| 1 | Civil and Structural Construction | 2000 | 0 | 2000
| 2 | Electrical Construction | 5610 | 0 | 5610
| 3 | Construction Management Services | 1000 | 175 | 1175
| Total |  | 8610 | 175 | 8785
Environmental
| 1 | Environmental | 40 | 25 | 65
| Total |  | 40 | 25 | 65
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 2700 | 1250 | 3950
| Total |  | 2700 | 1250 | 3950
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## SOK(CWLTP)
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
7091/ 6902 | South of Kramer (Coolwater-Lugo 220kV Transmission Line Portion) |  | 10500 | 43710.3846 | 29777.6923
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 1961 | 4034.713 | 5995.713
| 2 | Engineering and Design | 6639 | 9593.9695 | 16232.9695
| 3 | Regulatory and Licensing | 180 | 246.7021 | 426.7021
| Total |  | 8780 | 13875.3846 | 22655.3846
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 1711.5385 | 0
| 2 | Conductor and Conductor Hardware | 0 | 10721.1538 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 2000 | 0
| Total |  | 0 | 14432.6923 | 0
Construction
| 1 | Civil and Structural Construction | 0 | 0 | 0
| 2 | Electrical Construction | 0 | 0 | 0
| 3 | Construction Management Services | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Environmental
| 1 | Environmental | 1300 | 3721.1538 | 5021.1538
| Total |  | 1300 | 3721.1538 | 5021.1538
Real Properties
| 1 | Real Properties Acquisitions | 0 | 10000 | 0
| Total |  | 0 | 10000 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 420 | 1681.1538 | 2101.1538
| Total |  | 420 | 1681.1538 | 2101.1538
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## SOK(Jasper)
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6902 | South of Kramer (Jasper 220/66kV Substation Portion) |  | 300.0625 | 0 | 300.0625
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 189.0269 | 0 | 189.0269
| 2 | Engineering and Design | 67.3643 | 0 | 67.3643
| 3 | Regulatory and Licensing | 6.0613 | 0 | 6.0613
| Total |  | 262.4525 | 0 | 262.4525
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction | 0 | 0 | 0
| 2 | Electrical Construction | 0 | 0 | 0
| 3 | Construction Management Services | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Environmental
| 1 | Environmental | 28.8901 | 0 | 28.8901
| Total |  | 28.8901 | 0 | 28.8901
Real Properties
| 1 | Real Properties Acquisitions | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 8.7199 |  | 8.7199
| Total |  | 8.7199 | 0 | 8.7199
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0

## WOD
PIN # | Description |  | Forecast | Forecast
|  |  | 1/1/2014 - 12/31/2014 | 1/1/2015 - 12/31/2015 | Total
6420 | West of Devers Upgrade Project |  | 10663.8428 | 26978.9994 | 37642.8422
Project Support
| 1 | Project Management (e.g. Proj. Mgmt, Proj Admin, Proj. Controls, Estimating) | 435.6353 | 457.1566 | 892.7919
| 2 | Engineering and Design | 4065.4263 | 2394.6804 | 6460.1068
| 3 | Regulatory and Licensing | 1969.3014 | 2345.1564 | 4314.4577
| Total |  | 6470.363 | 5196.9934 | 11667.3564
Materials
| 1 | Steel and Hardware (e.g. Stub Angles or Anchor Bolts) | 0 | 0 | 0
| 2 | Conductor and Conductor Hardware | 0 | 0 | 0
| 3 | Transformers | 0 | 0 | 0
| 4 | Transmission Line Major Equipment (e.g. Insulator, Ground Wire, Dampers) | 0 | 0 | 0
| 5 | Substation Major Equipment (e.g. Circuit Breakers, Disconnect Switch, Reactors, Structural Steel) | 0 | 0 | 0
| 6 | Civil Materials and Misc Hardware | 0 | 0 | 0
| Total |  | 0 | 0 | 0
Construction
| 1 | Civil and Structural Construction | 0 | 984 | 984
| 2 | Electrical Construction | 0 | 0 | 0
| 3 | Construction Management Services | 0 | 0 | 0
| Total |  | 0 | 984 | 984
Environmental
| 1 | Environmental | 3298.4017 | 12302.3747 | 15600.7765
| Total |  | 3298.4017 | 12302.3747 | 15600.7765
Real Properties
| 1 | Real Properties Acquisitions | 0 | 6714.7532 | 6714.7532
| Total |  | 0 | 6714.7532 | 6714.7532
Allocated
| 1 | Allocated (e.g., chargebacks, SCE labor loaders and Division Overhead) | 895.078 | 1780.878 | 2675.956
| Total |  | 895.078 | 1780.878 | 2675.956
Contingency
| 1 | Contingency | 0 | 0 | 0
| Total |  | 0 | 0 | 0