| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Residential Appliance Recycling Program - Procurement |
| Program Number: | 1157-04 |
| Month: | October 2004 |

- Program Status

Program Description

The Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,206,909 | -$9,400 | 0% | $1,553,266 | 21% |  |  | $1,553,266 | 21% | $5,853,643 |
| Admin | $284,832 | $8,078 | 3% | $41,668 | 15% |  |  | $41,668 | 15% | $243,164 |
| Marketing | $255,000 | $172 | 0% | $63,127 | 25% |  |  | $63,127 | 25% | $191,873 |
| DI | $9,460,168 | -$17,650 | 0% | $1,448,471 | 22% |  |  | $1,448,471 | 22% | $5,211,697 |
| EM&V | $206,909 |  |  |  |  |  |  |  |  | $206,909 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,285 |  |  | 1,317 | 23% |  |  | 1,317 | 23% | 4,501 |
| Annual kWh | 48,479,584 |  |  | 7,671,214 | 23% |  |  | 7,671,214 | 23% | 26,355,180 |
| Lifecyc kWh | 290,877,502 |  |  | 46,027,283 | 23% |  |  | 46,027,283 | 23% | 158,131,082 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- The SCE RARP Program Manager and Program Analyst conducted a random inspection of the refrigerators and freezers turned in to verify program compliance.  This verification process is performed monthly and the results of each inspection are tabulated and reviewed with the recycling contractor to monitor program compliance.

- Prepared documentation for a fund shift transfer of $255,000 in direct implementation costs to the Residential Home Energy Efficiency Rebate (HEER) program.

- SCE continues to await a final resolution to their Petition to Modify Decision 03-12-060 filed in May 2004 regarding the new age restriction on refrigerators and freezers.

    - Marketing -

- Continued to promote RARP using POP materials strategically positioned in the appliance retail stores located throughout the SCE service territory.

- Completed an “e-mail blast” to approximately 40K SCE customers (both HTR and non HTR).

- Continued to promote RARP through the use of the Mobile Educational Unit (aka Energy Star Bus) at various events held throughout the SCE service territory.

- Prepared cinema ads (15 sec.) to promote RARP at theaters prior to the showing of movies.  The ads will begin appearing at movie theaters throughout the SCE service territory beginning in November and running through December.

- Continued running an ad in an apartment owner/manager trade journal.

- Prepared an ad for the City of Ontario’s Recycling News publication in both Spanish and English.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization -

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

- Program Challenges

- Since July 1, the contractor has handled many customer calls that have resulted in rejections for pick up appointments due to the new age restriction on refrigerators and freezers.  As of October 31, over 3,000 customers have been rejected over the phone due to the new age restriction. These rejections do not take into consideration those customers who knew their unit did not qualify and, therefore, did not call at all.

- Since using the drivers to verify the age of units at the time of pick up, 79 customers have been denied participation in the program.  In these cases, the driver verifies the unit age by finding the manufacturers label which the customer could not find when scheduling the appointment. This has resulted in an increase in customer complaints.

- Due to a lack of industry standard on identifying the age of manufacture on refrigerators and freezers, it is very difficult and, in some instances, impossible to verify the specific age of manufacture on all units turned in through the program.

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older refrigerators and freezers as directed by the CPUC.  The literature also included the new RARP qualification (effective July 1, 2004) which requires that all refrigerators and freezers be manufactured prior to 1990.

Conducting random inspections and ride alongs with the recycling contractor to ensure program compliance.

- Coordination Activities

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey reports to the RARP program information/sign up web site page.

- Coordinated efforts with various SCE Energy Efficiency Partnership Programs (e.g., South Bay, Ventura, and Kern County) to promote RARP by distributing brochures through various events held within the cities/counties of those partnership territories.

- Coordinated efforts with the City of Ontario to include an ad in the next edition of The Recycling News, a publication distributed to all City of Ontario residents.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None