| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Residential Appliance Recycling Program - Procurement |
| Program Number: | 1157-04 |
| Month: | September 2005 |

- Program Status

Program Description

The Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,170,729 | $114,276 | 1% | $2,238,608 | 22% |  |  | $2,238,608 | 22% | $7,932,122 |
| Admin | $284,832 | $4,267 | 1% | $87,950 | 31% |  |  | $87,950 | 31% | $196,882 |
| Marketing | $255,000 | $105,907 | 42% | $382,002 | 150% |  |  | $382,002 | 150% | -$127,002 |
| DI | $9,423,988 | $1,080 | 0% | $1,751,411 | 19% |  |  | $1,751,411 | 19% | $7,672,577 |
| EM&V | $206,909 | $3,022 | 1% | $17,245 | 8% |  |  | $17,245 | 8% | $189,664 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,253 |  |  | 1,580 | 19% |  |  | 1,580 | 19% | 6,673 |
| Annual kWh | 48,295,687 |  |  | 9,201,501 | 19% |  |  | 9,201,501 | 19% | 39,094,186 |
| Lifecyc kWh | 289,774,120 |  |  | 55,209,005 | 19% |  |  | 55,209,005 | 19% | 234,565,115 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- The SCE RARP Program Manager and Program Analyst conducted a random inspection of the refrigerators and freezers turned in to verify program compliance.  This verification process is performed monthly and the results of each inspection are tabulated and reviewed with the recycling contractor to monitor program compliance.

- New verification procedures were implemented effective September 1 to more closely monitor program compliance as it relates to the working (cooling) condition of refrigerators/freezers when picked up by recycling contractor drivers.  Ride alongs were conducted by SCE inspectors on September 16, 21, and 22 to verify that units were cooling.  The disqualification results of those inspections were measured against the total disqualifications reported by the recycling contractor drivers for the month. These inspections will be ongoing to monitor contractor program compliance.

- The SCE RARP Program Manager and Program Analyst conducted a random inspection of the refrigerators and freezers turned in to verify program compliance.  This verification process is performed monthly and the results of each inspection are tabulated and reviewed with the recycling contractor to monitor program compliance.

    - Marketing -

- Planning a Recycling Pick-Up Day event on Catalina Island in conjunction with the Catalina Outreach event to be held on October 13-14.

- Planning an event to commemorate the 500,000th refrigerator/freezer picked up since program inception in 1994.  The event is tentatively scheduled for November.

- Continued to promote RARP through the use of the Mobile Educational Unit (aka Energy Star Bus) at various events held throughout the SCE service territory.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Number Installed in September |
| --- | --- |
| Refrigerators | 0 |
| Freezers | 0 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

Program challenges related to the unit age restriction have been removed as a result of the CPUC’s approval to lift the age restriction as of May 5.

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older, spare refrigerators and freezers as directed by the CPUC.

Conducting the following activities to monitor program compliance:

  - Random ride alongs with recycling contractor drivers to verify working (cooling) condition of refrigerators and freezers.

  - Random on-site recycling facility inspections of refrigerators and freezers to verify units collected by recycling contractor.

  - Random customer surveys to verify customer participation and to measure satisfaction levels

- Coordination Activities

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey reports to the RARP program information/sign up web site page.

- Coordinated efforts with various SCE Energy Efficiency Partnership Programs (e.g., South Bay, Ventura, and Kern County) to promote RARP by distributing brochures through various events held within the cities/counties of those partnership territories.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The procurement-funded Appliance Recycling program underwent a fundshift in the month of August that transferred $273,733 from Administrative and $2,526,267 from DI Incentives into the DI Incentives budget of the procurement-funded Single Family EE Rebates program.  A second shift, in December, transferred $255k from DI Incentives to the DI Incentives budget of the procurement-funded Single Family EE Rebates program.  A third shift, in December, transferred $85k ($40k from Administrative and $45k from DI non-Incentives into the Marketing budget.

The procurement-funded Appliance Recycling program underwent a fundshift in the month of August that transferred $273,733 from Administrative and $2,526,267 from DI Incentives into the DI Incentives budget of the procurement-funded Single Family EE Rebates program.  A second shift, in December, transferred $255k from DI Incentives to the DI Incentives budget of the procurement-funded Single Family EE Rebates program.  A third shift, in December, transferred $85k ($40k from Administrative and $45k from DI non-Incentives into the Marketing budget.