| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Residential Appliance Recycling Program - Procurement |
| Program Number: | 1157-04 |
| Month: | April 2004 |

- Program Status

Program Description

The Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,170,729 | $637,466 | 6% | $748,320 | 7% | $433,892 | 4% | $1,182,212 | 12% | $9,422,409 |
| Admin | $284,832 | $780 | 0% | $928 | 0% |  |  | $928 | 0% | $283,904 |
| Marketing | $255,000 | $1,714 | 1% | $1,714 | 1% |  |  | $1,714 | 1% | $253,286 |
| DI | $9,423,988 | $634,972 | 7% | $745,677 | 8% | $433,892 | 5% | $1,179,569 | 13% | $8,678,311 |
| EM&V | $206,909 |  |  |  |  |  |  |  |  | $206,909 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,253 | 355 | 4% | 736 | 9% | 391 | 5% | 1,127 | 14% | 7,517 |
| Annual kWh | 48,295,687 | 2,067,132 | 4% | 4,286,365 | 9% | 2,275,509 | 5% | 6,561,874 | 14% | 44,009,322 |
| Lifecyc kWh | 289,774,120 | 12,402,790 | 4% | 25,718,190 | 9% | 13,653,054 | 5% | 39,371,243 | 14% | 264,055,931 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- Program manager coordinated a meeting at the Compton, CA recycling facility with the Energy Division staff and SDG&E EE program managers.  The meeting was held in conjunction with the random sampling of additional refrigerators and freezers collected through RARP to assess the age and labeling of these units.

- manager ated in e-alongs with rr (ARCA) to evaluation gathered during the ride along included customees with theeduls and logicalsse pickup (csProgram manager provided findings from additional random samples of refrigerators and freezers taken at the recycling facilities in Compton, California to determine age and labeling of units. The results were similar to those found in  March where 1/3 of the sampled units were manufactured after 1989 and only 1/3 of all units sampled had the model year listed on the manufacturer’s labels.

provided results of the random sampling of refrigerators and freezers taken at the recycling facilities in Compton, California to determine age and labeling of units.  It was determined that about 1/3 of the sampled units were manufactred after 19sted on the manufacturer’s labels.

    - Marketing -

See Attachment A for list of marketing materials.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization -

| Types of Measures Recommended | Numbers of Measures Installed |
| --- | --- |
| Refrigerators | 2,641 |
| Freezers | 299 |

      - Calculated and Actual Payment Reconciliation -

The calculate rebate amount shown in the program’s corresponding workbook does not reflect the cost to pick-up and recycle the refrigerator/freezer.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older refrigerators and freezers as directed by the CPUC.  The literature also included the new RARP qualification (effective July 1, 2004) which will require refrigerators and freezers be manufactured prior to 1990.

- Coordination Activities

Discussions were coordinated with the LIEE group to utilize existing contractors to target RARP efforts specifically to the HTR group.

Coordinated efforts with Flex Your Power to obtain retailer market information on sales of new refrigerators and freezers in the SCE service territory.  This effort was initiated to target specific retailers for participation in the RARP POS marketing campaign.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None