| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Residential Appliance Recycling Program - Procurement |
| Program Number: | 1157-04 |
| Month: | July 2004 |

- Program Status

Program Description

The Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,206,909 | $26,289 | 0% | $1,514,441 | 15% |  |  | $1,514,441 | 15% | $8,656,289 |
| Admin | $284,832 | $1,933 | 1% | $30,643 | 11% |  |  | $30,643 | 11% | $254,189 |
| Marketing | $255,000 | $24,356 | 10% | $35,327 | 14% |  |  | $35,327 | 14% | $219,673 |
| DI | $9,460,168 |  |  | $1,448,471 | 15% |  |  | $1,448,471 | 15% | $7,975,517 |
| EM&V | $206,909 |  |  |  |  |  |  |  |  | $206,909 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,285 | -1 | 0% | 1,317 | 16% |  |  | 1,317 | 16% | 6,936 |
| Annual kWh | 48,479,584 | -5,410 | 0% | 7,671,214 | 16% |  |  | 7,671,214 | 16% | 40,624,473 |
| Lifecyc kWh | 290,877,502 | -32,457 | 0% | 46,027,283 | 16% |  |  | 46,027,283 | 16% | 243,746,837 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- As of July 1, began the implementation of the new program requirement to limit participation to refrigerators and freezers manufactured prior to 1990.  Informed all parties (SCE communications) and worked with the recycling services contractor to ensure compliance with the new requirement. SCE continues to await a final decision to the Petition to Modify Decision 03-12-060 filed in May 2004 regarding the new age restriction on refrigerators and freezers.

- The program is still contemplating shifting funds to the Single Family Energy Efficiency Rebate program.  This is possible in part to a lower customer participation due to the new age restriction on refrigerators and freezers.

    - Marketing -

Coordinated efforts with a local Spanish speaking media company (Univision) to run RARP radio spots on Univision stations beginning in July and continuing into August.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization -

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

Beginning July 1, the Implementer has handled many customer calls that have resulted in denials for pick up appointments due to the age restriction on refrigerators and freezers

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older refrigerators and freezers as directed by the CPUC.  The literature also included the new RARP qualification (effective July 1, 2004) which will require refrigerators and freezers be manufactured prior to 1990.

- Coordination Activities

- Coordinated efforts with the SCE Communications Group and the recycling services vendor to establish a link for Spanish speaking customers to schedule pick up appointments online through the SCE.com web site.

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey report to the RARP program information/sign up web site page.

- Coordinated efforts with the South Bay Partnership Program to promote RARP by distributing brochures through various events held within the cities of the South Bay.

- Radio spots began to run on the local Spanish speaking station (Univision) in July and will continue into August.

- Radio spots continued on LA-based station all through the month of July and into August.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

A total of 25 recycled refrigerator units were reported as recycled freezer units in the month of June.  In July’s workbook, we rectified the situation by backing out the misreported freezer units and adding to the refrigerator units.  That is why for the month of July, the program is showing negative kW and kWh results.