| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Residential Appliance Recycling Program - Procurement |
| Program Number: | 1157-04 |
| Month: | May 2005 |

- Program Status

Program Description

The Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,170,729 | $20,654 | 0% | $2,050,460 | 20% |  |  | $2,050,460 | 20% | $8,120,269 |
| Admin | $284,832 | $3,206 | 1% | $74,879 | 26% |  |  | $74,879 | 26% | $209,953 |
| Marketing | $255,000 | $13,650 | 5% | $220,884 | 87% |  |  | $220,884 | 87% | $34,116 |
| DI | $9,423,988 | $1,531 | 0% | $1,746,379 | 19% |  |  | $1,746,379 | 19% | $7,677,609 |
| EM&V | $206,909 | $2,267 | 1% | $8,318 | 4% |  |  | $8,318 | 4% | $198,591 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,253 |  |  | 1,580 | 19% |  |  | 1,580 | 19% | 6,673 |
| Annual kWh | 48,295,687 |  |  | 9,201,501 | 19% |  |  | 9,201,501 | 19% | 39,094,186 |
| Lifecyc kWh | 289,774,120 |  |  | 55,209,005 | 19% |  |  | 55,209,005 | 19% | 234,565,115 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- The SCE RARP Program Manager and Program Analyst conducted a random inspection of the refrigerators and freezers turned in to verify program compliance.  This verification process is performed monthly and the results of each inspection are tabulated and reviewed with the recycling contractor to monitor program compliance.

- SCE received final resolution to their Petition to Modify Decision 03-12-060 filed in May 2004 regarding the new age restriction on refrigerators and freezers. On May 5, 2005, the CPUC approved SCE’s Summer Initiative Program (additional $4M for RARP) and, as an integral part of the decision, lifted the age restriction on refrigerators and freezers and approved an increase in the freezer incentive from $35 to $50. The lifting of the age restriction and the increase in the freezer incentive should have an immediate and positive impact on program participation.

    - Marketing -

- Replaced RARP POP materials strategically positioned in the appliance retail stores located throughout the SCE service territory to reflect the lifting of the age restriction and increase in freezer incentives as a result of the CPUC’s approval of SCE’s Summer Initiative Program.

- Continued to promote RARP through the use of the Mobile Educational Unit (aka Energy Star Bus) at various events held throughout the SCE service territory.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Number Installed in May |
| --- | --- |
| Refrigerators | 0 |
| Freezers | 0 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

- The contractor has handled many customer calls that have resulted in rejections for pick up appointments due to the new age restriction on refrigerators and freezers.  Through May 4, 2005 over 7,700 customers were rejected over the phone due to the new age restriction. These rejections do not take into consideration those customers who knew their unit did not qualify (by reviewing program literature or the web site) and, therefore, did not call or sign up over the Internet to schedule a pick up appointment.  This program challenge has been removed as a result of the CPUC’s approval to lift the age restriction as of May 5.

- Since using the drivers to verify the age of units at the time of pick up, 138 customers have been denied participation in the program.  In these cases, the driver verifies the unit age by finding the manufacturers label which the customer could not find when scheduling the appointment. This has resulted in an increase in customer complaints and recycling contractor costs. These rejections and subsequent complaints and costs will end as a result of the CPUC’s approval to lift the age restriction as of May 5.

- Due to a lack of industry standard on identifying the age of manufacture on refrigerators and freezers, it is very difficult and, in some instances, impossible to verify the specific age of manufacture on all units turned in through the program.

As a result of the CPUC’s approval to lift the age restriction as of May 5, the manufacture age will no longer need to be verified.

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older, spare refrigerators and freezers as directed by the CPUC.

Conducting random on-site inspections at the contractor’s recycling facility, ride alongs with recycling contractor drivers, and customer surveys to verify customer participation and ensure program compliance.

- Coordination Activities

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey reports to the RARP program information/sign up web site page.

- Coordinated efforts with various SCE Energy Efficiency Partnership Programs (e.g., South Bay, Ventura, and Kern County) to promote RARP by distributing brochures through various events held within the cities/counties of those partnership territories.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The procurement-funded Appliance Recycling program underwent a fundshift in the month of August that transferred $273,733 from Administrative and $2,526,267 from DI Incentives into the DI Incentives budget of the procurement-funded Single Family EE Rebates program.  A second shift, in December, transferred $255k from DI Incentives to the DI Incentives budget of the procurement-funded Single Family EE Rebates program.  A third shift, in December, transferred $85k ($40k from Administrative and $45k from DI non-Incentives into the Marketing budget.