| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Single Family Energy Efficiency Rebates Program - Procurement |
| Program Number: | 1160-04 |
| Month: | July 2004 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program of 2004-2005 offers measures from the traditional part of the program as well as measures previously included in the Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program allows synergies and efficiencies in the areas of administration, materials preparation, and communications to the various market actors.  While all residential customers have the opportunity to participate in the program, additional marketing and promotional activity is targeted to customer segments defined as hard-to-reach (HTR).  This targeted marketing activity increases awareness and participation from these customers to ensure that the HTR goals are met or exceeded.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $24,507,379 | $2,715,603 | 11% | $7,192,221 | 29% | $3,887,816 | 16% | $11,080,037 | 45% | $17,296,378 |
| Admin | $850,600 | $9,672 | 1% | $77,723 | 9% |  |  | $77,723 | 9% | $772,877 |
| Marketing | $652,800 |  |  | $115,768 | 18% |  |  | $115,768 | 18% | $537,032 |
| DI | $22,496,600 | $2,705,931 | 12% | $6,998,730 | 31% | $3,887,816 | 17% | $10,886,546 | 48% | $15,479,090 |
| EM&V | $507,379 |  |  |  |  |  |  |  |  | $507,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 76,743 | 10,304 | 13% | 24,750 | 32% | 15,445 | 20% | 40,195 | 52% | 51,854 |
| Annual kWh | 438,462,103 | 56,355,127 | 13% | 137,339,527 | 31% | 100,460,675 | 23% | 237,800,202 | 54% | 300,230,818 |
| Lifecyc kWh | 4,449,723,390 | 532,644,721 | 12% | 1,341,444,800 | 30% | 1,030,065,461 | 23% | 2,371,510,262 | 53% | 3,106,861,852 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Submitted documentation in support of a possible fund transfer of approximately $2 M from the Appliance Recycling Program.

- Lighting measure allocations for April through October 2004 are set to achieve targets.   Incoming shipment reports and invoices show progress is on track, and ahead of previous years.  We’re experiencing fewer cancellations than previous years.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Number Installed in July |
| --- | --- |
| Pool Pump & Motors | 169 |
| Room AC | 6 |
| Windows | 174,214 |
| ENERGY STAR® qualified Refrigerators | 4,279 |
| Attic Insulation | 1,814 |
| Whole House Fans | 142 |
| Desert Area Air Conditioning | 141 |
| HVAC | 1,532 |
| Lighting | 821,365 |

      - Calculated and Actual Payment Reconciliation -

There is a discrepancy between the financial incentives paid in Tab “1A – Expenditures Worksheet” and the calculated incentives in Tab “2A – RecordedEEActivities” due an incorrect charge.  This charge is being corrected and will be reflected in next month’s report.

    - EM&V

The EM&V activity is being done as a supplement to the 2004-05 EM&V study of statewide Single Family Energy Efficiency Rebate program that is being managed by PG&E.

- Program Challenges

Obtaining additional funds to keep the program open is a continuous activity.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None