| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide CA Energy Star New Homes – Single Family, Multifamily Program - Procurement |
| Program Number: | 1169-04 |
| Month: | January 2005 |

- Program Status

Program Description

The California Energy Star® New Homes Program will influence the design and construction of single family and multifamily residential new construction. Working together with single and multifamily builders, architects, energy analysts, and other building industry professionals, this program will increase long term annual energy savings and coincident peak demand reduction and will be achieved through a combination of education, design assistance and financial incentives. Single family and low-rise multifamily builder projects meeting the program requirements will also meet the requirements of the U. S. Environmental Protection Agency (EPA) Energy Star Homes Program. (The EPA does not currently recognize high rise construction with the Energy Star label.)  SCE will again offer the high efficiency HVAC distributor buy-down program (“Buy-down Program) in the 2004-05 program years.  SCE piloted this innovative program in the summer of 2001 and met with success.  This program will complement the CESNHP as well as capture energy savings and demand from those homes that have progressed in the construction process beyond the timely “point of entry” into CESNHP, and would otherwise become a lost opportunity for increase energy efficiency.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $6,139,345 | $2,825 | 0% | $102,383 | 2% | $2,053,480 | 33% | $2,155,863 | 35% | $6,036,962 |
| Admin | $371,800 | $1,825 | 0% | $38,255 | 10% |  |  | $38,255 | 10% | $333,545 |
| Marketing | $207,400 |  |  | $2,035 | 1% |  |  | $2,035 | 1% | $205,365 |
| DI | $5,420,800 | $999 | 0% | $62,092 | 1% | $2,053,480 | 38% | $2,115,572 | 39% | $5,358,708 |
| EM&V | $139,345 |  |  |  |  |  |  |  |  | $139,345 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,235 |  |  | 67 | 1% | 3,809 | 41% | 3,876 | 42% | 9,168 |
| Annual kWh | 8,332,320 |  |  | 62,138 | 1% | 3,531,524 | 42% | 3,593,662 | 43% | 8,270,182 |
| Lifecyc kWh | 149,981,760 |  |  | 1,118,491 | 1% | 63,567,432 | 42% | 64,685,923 | 43% | 148,863,269 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Single Family and Multifamily California Energy Star New Homes Programs (CESNHP) were still in the “preparation” mode in January. Applications were reviewed and printed. RNC met with our vendors XXXXX on 1/21/05 and XXXXX  on 1/27/05 to review future plans and milestone goals for 2005.

- SCE is also sponsoring the Residential New Construction High Efficiency Air Conditioning Distributors Buy-down program. We continued to work with XXXXX to prepare application forms, inspection forms and a strategy for reaching our milestone goals in 2005. XXXXX revised the draft application material per our requests, developed a process flow chart and a website structure and design. RNC continues to work with XXXXX and will support in any fashion their efforts throughout 2005.

    - Marketing -

We are in development at this time of what type of marketing will be needed to promote this program.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measures | Installed in January | Committed |
| --- | --- | --- |
| SF Home 15% Inland | 0 | 1,263 |
| SF Home 20% Inland | 0 | 1,811 |
| MF Home 15% | 0 | 812 |
| SF Tier I | 0 | 0 |
| SF Tier II | 0 | 0 |
| MF Tier I | 0 | 0 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

The RNC team has been working closely with XXXXX  in preparation to roll out the 2005 program. RNC met with XXXXX on 1/28/05 to review status and provide strategies.

- Changes to Subcontractors or Staffing

XXXXX has joined Residential New Construction on a developmental opportunity and will be supporting Single Family, Multifamily and the RNC HVAC Buydown Program with internal and field support.

- Additional Items

None