| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Multifamily Energy Efficiency Rebate Program - Procurement |
| Program Number: | 1176-04 |
| Month: | December 2004 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $8,191,126 | $290,144 | 4% | $2,588,216 | 32% | $1,297,017 | 16% | $3,885,233 | 47% | $5,602,910 |
| Admin | $166,400 | $10,768 | 6% | $45,289 | 27% |  |  | $45,289 | 27% | $121,111 |
| Marketing | $230,000 | $5,691 | 2% | $29,163 | 13% |  |  | $29,163 | 13% | $200,837 |
| DI | $7,603,600 | $273,685 | 4% | $2,513,763 | 33% | $1,297,017 | 17% | $3,810,780 | 50% | $5,089,837 |
| EM&V | $191,126 |  |  |  |  |  |  |  |  | $191,126 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 3,530 | 157 | 4% | 1,485 | 42% | 741 | 21% | 2,226 | 63% | 2,044 |
| Annual kWh | 29,513,699 | 1,440,771 | 5% | 11,500,115 | 39% | 4,673,818 | 16% | 16,173,934 | 55% | 18,013,584 |
| Lifecyc kWh | 302,665,579 | 12,840,046 | 4% | 120,551,466 | 40% | 55,696,963 | 18% | 176,248,430 | 58% | 182,114,113 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2004 program year.

- The year 2004 has also seen a marked increase in the number of property managers and owners initiating rebate requests without prompting of a private installation contractor.  MFEER program awareness has increased significantly in this targeted customer segment as illustrated by roughly a  four-fold increase in the number of self-initiated rebate requests from property owners and managers.

- December proved to be a high volume month as a rush of end-of-the-year applications were received from SCE customers.

- Prepared for 2005 MFEER program implementation including developing a revamped MFEER application designed to facilitate customer participation.

    - Marketing -

- Ongoing advertisements in three monthly publications sent directly to apartment owners and managers.

- The MFEER program received many responses from customers receiving the October CFL postcard.  As has been the case this year, the program is seeing a marked increase in self-initiated rebate requests from smaller “mom-n-pop” property owners.  With a well-rounded outreach effort the program is realizing participation from all levels of multifamily property owners – from large to small.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in December | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 9,875 | 112,475 |
| Fluorescent Fixtures | 80 | 47,179 |
| T8/T5 Fluorescent Lamps | 95 | 7,098 |
| Low E Windows | 0 | 55,219 sq. ft. |
| Prog. Thermostats | 0 | 3,489 |
| Heating/Cooling Sys. | 0 | 3 |
| Room A/C | 9 | 53 |
| Ceiling Fan | 0 | 0 |
| Sensors | 0 | 7 |
| Package Terminal HP | 0 | 10 |
| Insulation | 0 | 0 |
| Pool Pumps | 0 | 4 |
| LED Exit Signs | 0 | 181 |
| Torchiere Exchange | 0 | 4,008 |
| Duct Test & Sealing Services | 750 | 2,702 |

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual customer purchase price.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Duct Test and Sealing (DT&S) activities leverage off the existing customer base of customers who have previously, or are currently, involved in the MFEER program.  As well, DT&S customers may receive lighting or other HVAC measures during the service.  As of December, the MFEER program has conducted duct test and sealing in over 1,300 dwelling units.

- Fluorescent torchiere exchange also leverages previous or current MFEER program customers.  Further, at least one torchiere subcontractor leverages existing multifamily complexes from other state-sponsored programs such as lead abatement or direct assistance programs.  As of December, nearly 4,000 halogen torchieres have been exchanged for energy saving, safer fluorescent torchieres.

- Changes to Subcontractors or Staffing

Program manager has not changed.

- Additional Items

The procurement-funded Multi-family EE Rebates program underwent a fundshift in the month of December that transferred $90k from Marketing and $110k from DI non-Incentives into the DI Incentives budget.

The procument-funded Multi-family EE Rebates program underwent a fundshift in the month of December that transferred $90k from Marketing and $110k from DI non-Incentives into the DI Incentives budget.