| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Multifamily Energy Efficiency Rebate Program - Procurement |
| Program Number: | 1176-04 |
| Month: | November 2005 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $8,191,126 | $173,933 | 2% | $6,928,678 | 85% | $913,750 | 11% | $7,842,428 | 96% | $1,262,448 |
| Admin | $166,400 | $3,802 | 2% | $129,963 | 78% |  |  | $129,963 | 78% | $36,437 |
| Marketing | $230,000 | $1,195 | 1% | $331,993 | 144% |  |  | $331,993 | 144% | -$101,993 |
| DI | $7,603,600 | $167,003 | 2% | $6,445,376 | 85% | $913,750 | 12% | $7,359,126 | 97% | $1,158,224 |
| EM&V | $191,126 | $1,933 | 1% | $21,345 | 11% |  |  | $21,345 | 11% | $169,781 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Nov-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 3,530 | 157 | 4% | 3,664 | 104% | 686 | 19% | 4,350 | 123% | -134 |
| Annual kWh | 29,513,699 | 881,138 | 3% | 25,483,264 | 86% | 3,502,940 | 12% | 28,986,205 | 98% | 4,030,435 |
| Lifecyc kWh | 302,665,579 | 12,090,414 | 4% | 289,921,248 | 96% | 42,418,422 | 14% | 332,339,669 | 110% | 12,744,331 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2004 program year.

    - Marketing -

- Ongoing advertisements in four monthly publications sent directly to apartment owners and managers.

- The statewide MFEER team held a meeting open to all independent contractors November 14, 2005 at the Gas Company Energy Resource Center located in Downey.  Roughly 60 individuals attended.  The IOUs presented program updates, conveyed valuable evaluation information, and presented 2006 – 08 MFEER program information

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in November | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 2,584 | 182,337 |
| Fluorescent Fixtures | 627 | 84,222 |
| T8/T5 Fluorescent Lamps | 2,628 | 29,614 |
| Low E Windows | 53 | 41,659 sq. ft. |
| Prog. Thermostats | 464 | 7,633 |
| Heating/Cooling Sys. | 0 | 41 |
| Room A/C | 0 | 70 |
| Ceiling Fan | 0 | 36 |
| Photocells/Sensors | 0 | 16 |
| Package Terminal AC/HP | 0 | 86 |
| Insulation | 0 sq. ft. | 54,867 sq. ft. |
| Pool Pumps | 0 | 6 |
| LED Exit Signs | 21 | 209 |
| Torchiere Exchange | 0 | 8,208 |
| Duct Test & Sealing Services | 137 | 3,691 |
| Electric Water Heater | 0 | 1 |
| Faucet Aerator | 0 | 0 |
| Showerhead | 10 | 10 |

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual customer purchase price.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Duct Test and Sealing (DT&S) activities leverage off the existing customer base of customers who have previously, or are currently, involved in the MFEER program.  As well, DT&S customers may receive lighting or other HVAC measures during the service.  At the conclusion of duct test and seal activities, the MFEER program has conducted duct test and sealing in over 3,800 dwelling units.

- Fluorescent torchiere exchange also leverages previous or current MFEER program customers.  Further, at least one torchiere subcontractor leverages existing multifamily complexes from other state-sponsored programs such as lead abatement or direct assistance programs.  At the conclusion of exchange activities, 8,200 halogen torchieres have been exchanged for energy saving, safer fluorescent torchieres.

- Ongoing follow-up of previous coordination activities continues by program management.  Work and coordination with major property management firms is being conducted with an eye toward implementing retrofit projects beginning in 2006.

- Changes to Subcontractors or Staffing

Program manager has not changed.  Program manager and subcontractors have not changed.

- Additional Items

None

The procurement-funded Multi-family EE Rebates program underwent a fundshift in the month of December that transferred $90k from Marketing and $110k from DI non-Incentives into the DI Incentives budget.