| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Express Efficiency Program - Procurement |
| Program Number: | 1178-04 |
| Month: | December 2004 |

- Program Status

Program Description

Express Efficiency is the only prescriptive rebate program that provides equitable financial incentives to all small-and medium-sized nonresidential customers on a seamless statewide basis. By having a design that actually prescribes what measures may be installed, it is a very straightforward and customer-friendly program that ensures that the smallest customers have a hassle-free, reliable means to decrease their utility bill and make their business more energy efficiency. One of the program’s goals is to focus on providing small and medium-sized customers access to energy efficient technologies that had previously been adopted by larger customers. To achieve this goal, SCE will draw upon the all the synergies that exist between its programs, such as the Energy Audit program.  Furthermore, the SCE will pursue opportunities to coordinate promotional activities with those of other, community based organizations.  Doing so will increase the economies of scale and create a greater positive impact for all present and future stakeholders.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,635,562 | $797,307 | 22% | $1,326,033 | 36% | $1,481,004 | 41% | $2,807,037 | 77% | $2,309,529 |
| Admin | $336,572 | $14,596 | 4% | $110,413 | 33% |  |  | $110,413 | 33% | $226,159 |
| Marketing | $272,500 | $4,463 | 2% | $24,154 | 9% |  |  | $24,154 | 9% | $248,346 |
| DI | $2,930,928 | $778,249 | 27% | $1,191,466 | 41% | $1,481,004 | 51% | $2,672,470 | 91% | $1,739,462 |
| EM&V | $95,562 |  |  |  |  |  |  |  |  | $95,562 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 10,000 | 850 | 8% | 4,312 | 43% | 7,580 | 76% | 11,893 | 119% | 5,687 |
| Annual kWh | 56,337,803 | 3,968,063 | 7% | 20,308,401 | 36% | 36,861,974 | 65% | 57,170,375 | 101% | 36,029,402 |
| Lifecyc kWh | 493,989,141 | 42,226,034 | 9% | 278,502,789 | 56% | 430,025,956 | 87% | 708,528,745 | 143% | 215,486,352 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Held bi-weekly telephone conferences with the statewide team to discuss program implementation status, performance, delivery strategy, and issues.

- The statewide team completed work on the 2005 applications in December.  The team will advise the Energy Division of proposed measure changes.

- The 2004 Express Efficiency program closed on October 22 as the one-year 50 percent allocated incentive budget had been fully committed.  Full commitment of the incentive budget included the baseline budget of $4,957,364, plus a $200,000 fund transfer from within the Express program, and a $1,400,000 fund transfer from the Standard Performance Contract program.

    - Marketing –

- No significant marketing efforts were initiated in the month of December.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| # Customer Sites (Paid in October) | Average Cost Per Site |
| --- | --- |
| 342 | $2,356 |

| Types of Measures Recommended | Measures Installed in December |
| --- | --- |
| Lighting | 19,590 |
| HVAC* | 839 |
| Refrigeration** | 0 |
| Food Service | 4 |
| Agricultural | 0 |

* Includes cool roofs and window film, measured in square feet.

** Includes gaskets and strip curtains, measured in linear feet.

      - Calculated and Actual Payment Reconciliation –

Underpayments:

1. (60) “Setback Programmable Thermostat” units installed, less $5.00 per unit to account for rebate amount exceeding installed cost. $300.00

2. (8) “T-8 or T-5 Lamp and Electronic Ballast, 2 foot installed”, less $2.00 per unit to account for customer previously receiving rebate for “Electronic ballast, non-dimming”.

3. (102) “T-8 or T-5 Lamp and Electronic Ballast, 4 foot installed”, less $2.00 per unit to account for customer previously receiving rebate for “Electronic ballast, non-dimming”.

4. (28) “Setback Programmable Thermostat” units installed, less $5.40 per unit to account for the rebate amount in the program year 2003 being less than the rebate amount in the 2004 program year.

Overpayments:

1. (75) “Screw-in Compact Fluorescent Lamp, 14-26 watts w/Reflector” units installed, payment was increased by $3.60 per unit to account for the rebate amount in the program year 2003 being more than the rebate amount in the 2004 program year..

2. (1560) “T-8 or T-5 Lamp and Electronic Ballast, 4 foot installed”, payment was increased by $2.55 per unit to account for the rebate amount in the program year 2003 being more than the rebate amount in the 2004 program year.

Adjustment:

Cost Transfer for $35,821.09 for four payments mistakenly charged to incentive budget in December.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The procurement-funded Express Efficiency program underwent a series of two fundshifts in the month of October.  The first shift, an internal fundshift took $15k from Administrative, $85k from Marketing and $100k from Direct Implementation and put it into the Incentives budget.  The second shift transferred $1.4M into the incentives budget from the incentives budget of the procurement-funded SPC program.