| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Express Efficiency Program - Procurement |
| Program Number: | 1178-04 |
| Month: | May 2005 |

- Program Status

Program Description

Express Efficiency is the only prescriptive rebate program that provides equitable financial incentives to all small-and medium-sized nonresidential customers on a seamless statewide basis. By having a design that actually prescribes what measures may be installed, it is a very straightforward and customer-friendly program that ensures that the smallest customers have a hassle-free, reliable means to decrease their utility bill and make their business more energy efficiency. One of the program’s goals is to focus on providing small and medium-sized customers access to energy efficient technologies that had previously been adopted by larger customers. To achieve this goal, SCE will draw upon the all the synergies that exist between its programs, such as the Energy Audit program.  Furthermore, the SCE will pursue opportunities to coordinate promotional activities with those of other, community based organizations.  Doing so will increase the economies of scale and create a greater positive impact for all present and future stakeholders.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,635,562 | $12,610 | 0% | $2,567,628 | 71% | $7,934 | 0% | $2,575,562 | 71% | $1,067,934 |
| Admin | $336,572 | $4,638 | 1% | $138,450 | 41% |  |  | $138,450 | 41% | $198,122 |
| Marketing | $272,500 | $6,162 | 2% | $51,397 | 19% |  |  | $51,397 | 19% | $221,103 |
| DI | $2,930,928 | $776 | 0% | $2,373,753 | 81% | $7,934 | 0% | $2,381,687 | 81% | $557,175 |
| EM&V | $95,562 | $1,034 | 1% | $4,028 | 4% |  |  | $4,028 | 4% | $91,534 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 10,000 |  |  | 11,498 | 115% | 33 | 0% | 11,531 | 115% | -1,498 |
| Annual kWh | 56,337,803 |  |  | 53,659,327 | 95% | 162,080 | 0% | 53,821,407 | 96% | 2,678,476 |
| Lifecyc kWh | 493,989,141 |  |  | 638,862,979 | 129% | 2,363,978 | 0% | 641,226,957 | 130% | -144,873,838 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Held monthly telephone conference with the statewide team to discuss program implementation status, performance, delivery strategy, and issues.

    - Marketing –

- Continued design and development of energy savings calculation brochures for CFL retrofit, T-8 lighting retrofit, HID lighting retrofit and high bay lighting retrofit projects.

- Completed planning activities for the West Coast Energy Management Congress to be held in San Diego in June.  The statewide Express Efficiency team will host a booth in the exhibit hall.

- Completed design of bundled direct mail brochure that includes Express Efficiency contact information.

- Completed design of industry specific direct mail pieces that promote Express Efficiency exclusively to office, institutional food service, and warehouse customers.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| # Customer Sites (Paid in May) | Average Cost Per Site |
| --- | --- |
| 95 | $981 |

| Types of Measures | Measures Installed in May |
| --- | --- |
| Lighting | 0 |
| HVAC* | 0 |
| Refrigeration** | 0 |
| Food Service | 0 |
| Agricultural | 0 |

* Includes window film, measured in square feet.

** Includes gaskets and strip curtains, measured in linear feet.

      - Calculated and Actual Payment Reconciliation –

- Cost transfer for $1160.78 for two payments mistakenly charged to incentive budget in May.

- Two customer payments were returned to SCE (Reference number 426427) and cancelled/voided for a total of $ 8,169.00.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The procurement-funded Express Efficiency program underwent a series of two fundshifts in the month of October.  The first shift, an internal fundshift took $15k from Administrative, $85k from Marketing and $100k from DI and put it into the Incentives budget.  The second shift transferred $1.4M into the incentives budget from the incentives budget of the procurement-funded SPC program.