| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Upstream HVAC and Motors Rebates Program - Procurement |
| Program Number: | 1179-04 |
| Month: | September 2004 |

- Program Status

Program Description

The Upstream Motors and Air Conditioning program is a prescriptive rebate program that provides upstream financial incentives to distributors to stock and sell qualifying high efficiency products.  All incentives will be paid upstream.  No rebates will be offered to end users.  SCE’s commercial, industrial and agricultural customers are eligible to participate.  Program marketing will be targeted toward transmission-constrained and geographically hard to reach markets in order to maximize program benefits.  Both nonresidential retrofit and new construction applications qualify for the program, as this is an upstream program focused on changing distributors’ stocking practices to favor qualifying energy-efficient equipment. SCE’s customers from the smallest to the largest are eligible to receive the advantage of the upstream incentives.  Packaged air conditioning is used by small commercial customers; motors are used by all customer classes. Incentives are offered for high efficiency packaged and split system air conditioners, heat pumps, integral HVAC smart controls, package chillers, and motors. Depending on market response, additional measures may be added in the second year of the program (i.e., 2005).  The program is offered to customers within Southern California Edison’s (SCE) service territory and is part of both the Commercial and Industrial Hardware Incentive Programs described in SCE’s Long-Term Resource Plan Testimony.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $5,079,453 | $19,456 | 0% | $194,990 | 4% | $176,886 | 3% | $371,875 | 7% | $4,884,463 |
| Admin | $303,354 | $19,456 | 6% | $50,449 | 17% |  |  | $50,449 | 17% | $252,905 |
| Marketing | $661,500 |  |  |  |  |  |  |  |  | $661,500 |
| DI | $3,995,146 |  |  | $144,541 | 4% | $176,886 | 4% | $321,427 | 8% | $3,850,605 |
| EM&V | $119,453 |  |  |  |  |  |  |  |  | $119,453 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

Expenses reported for September do not include the Energy Solutions invoice for August activity, which was submitted to SCE for payment after the close of September business.  This expense will thus be reflected in October business.

    - Energy Effects

| Energy Effects | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 7,438 |  |  | 11 | 0% | 570 | 8% | 582 | 8% | 7,427 |
| Annual kWh | 20,412,195 |  |  | 53,529 | 0% | 1,801,979 | 9% | 1,855,508 | 9% | 20,358,666 |
| Lifecyc kWh | 309,617,990 |  |  | 822,752 | 0% | 27,752,959 | 9% | 28,575,712 | 9% | 308,795,238 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative –

- The draft Program Policies and Procedures Manuel is under review.

- The third data exchange between the online application system and SCE’s tracking system was successfully completed.  The process of matching submittals with valid SCE service addresses continues to improve as a result of the team’s efforts to identify improvements to the routines to identify various street address conventions, etc.  The latest batch matched over 80% of the addresses submitted with valid SCE customer addresses.

- Phase II upgrades to the online application system are nearly complete, as only a few minor adjustments remain.

- The automated data exchange between SCE and US Air, a large HVAC distributor in the SCE territory, has been tested with an initial batch representing August 2004 package equipment sales.  This was delayed briefly by a virus in the US Air computer system.  The remaining data, for package unit sales and installations made since US Air signed onto the Program in April, will be entered during September.  This may represent a significant portion of SCE’s Upstream Program equipment goals for 2004.

    - Marketing –

- Continuing efforts to enroll major HVAC and motor distributors in SCE territory

22 HVAC Distributors enrolled

58 Motors Distributors enrolled

- A Participation Improvement Plan has been developed to improve our ability to track and analyze participant application data, support distributors in completing rebate applications, and allow us to identify participants who have not yet submitted applications and those who are not participating to their fullest potential.

- Distributors report that they are utilizing the Upstream Program rebates to reduce the sales price of high-efficiency equipment, and are also using pricing to influence designer/contractor equipment selections.  Ongoing distributor contacts focus on encouraging distributors to continue to leverage the installation of high-efficiency equipment and promote its benefits as envisioned in the Program Implementation Plan.

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

- Participating distributors continue to submit rebate applications, reporting that the rebates will help them to win bids for installation of high efficiency equipment, provide cost reductions to customers and increase sales volume.

- Implementation of the Participation Improvement Plan has helped us identify significant backlogs of qualifying equipment sales and installations for several distributors.  We are working with these participants to motivate them to submit applications, and identify barriers to participation.

- Recent enhancements to the On-line Application process have received "rave" reviews from participating distributors.

| Measures | Measures Installed YTD September | Committed |
| --- | --- | --- |
| HVAC | 0 | 1,684 |
| Motors | 0 | 213 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

Verification/inspection protocols for program installations are under development.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Expenses reported for September do not include the Energy Solutions invoice for August activity, which was submitted to SCE for payment after the close of September business.  This expense will thus be reflected in October business.