| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Upstream HVAC and Motors Rebates Program - Procurement |
| Program Number: | 1179-04 |
| Month: | March 2004 |

- Program Status

Program Description

The Upstream Motors and Air Conditioning program is a prescriptive rebate program that provides upstream financial incentives to distributors to stock and sell qualifying high efficiency products.  All incentives will be paid upstream.  No rebates will be offered to end users.  SCE’s commercial, industrial and agricultural customers are eligible to participate.  Program marketing will be targeted toward transmission-constrained and geographically hard to reach markets in order to maximize program benefits.  Both nonresidential retrofit and new construction applications qualify for the program, as this is an upstream program focused on changing distributors’ stocking practices to favor qualifying energy-efficient equipment. SCE’s customers from the smallest to the largest are eligible to receive the advantage of the upstream incentives.  Packaged air conditioning is used by small commercial customers; motors are used by all customer classes. Incentives are offered for high efficiency packaged and split system air conditioners, heat pumps, integral HVAC smart controls, package chillers, and motors. Depending on market response, additional measures may be added in the second year of the program (i.e., 2005).  The program is offered to customers within Southern California Edison’s (SCE) service territory and is part of both the Commercial and Industrial Hardware Incentive Programs described in SCE’s Long-Term Resource Plan Testimony.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $5,579,453 | $723 | 0% | $2,029 | 0% |  |  | $2,029 | 0% | $5,577,424 |
| Admin | $678,900 | $723 | 0% | $2,029 | 0% |  |  | $2,029 | 0% | $676,871 |
| Marketing | $635,000 |  |  |  |  |  |  |  |  | $635,000 |
| DI | $4,146,100 |  |  |  |  |  |  |  |  | $4,146,100 |
| EM&V | $119,453 |  |  |  |  |  |  |  |  | $119,453 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 8,655 |  |  |  |  |  |  |  |  | 8,655 |
| Annual kWh | 23,760,007 |  |  |  |  |  |  |  |  | 23,760,007 |
| Lifecyc kWh | 360,406,168 |  |  |  |  |  |  |  |  | 360,406,168 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- Executed a purchase order with XXXXX to be the program implementer in SCE territory.

- Continued discussions with the statewide IOU team and XXXXX to coordinate program brochures, online application system, and a vendor participation agreement.

    - Marketing -

Design and development of distributor brochures is in process.

    - Direct Implementation –

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Additional Items

None