| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Savings By Design – Procurement |
| Program Number: | 1183-04 |
| Month: | September 2005 |

- Program Status

Program Description

Southern California Edison Company’s Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incentives as well as design team incentives.  SBD will leverage its resources and procure energy savings and demand reduction for this integrated resource planning purpose.  As a result energy savings will be achieved at a very cost-effective level.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,443,685 | $53,471 | 1% | $479,207 | 5% |  |  | $479,207 | 5% | $9,964,478 |
| Admin | $266,600 | $4,691 | 2% | $78,502 | 29% |  |  | $78,502 | 29% | $188,098 |
| Marketing | $447,600 |  |  |  |  |  |  |  |  | $447,600 |
| DI | $9,485,800 | $46,468 | 0% | $381,506 | 4% |  |  | $381,506 | 4% | $9,104,293 |
| EM&V | $243,685 | $2,312 | 1% | $19,198 | 8% |  |  | $19,198 | 8% | $224,487 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 12,757 |  |  |  |  |  |  |  |  | 12,757 |
| Annual kWh | 65,198,392 |  |  |  |  |  |  |  |  | 65,198,392 |
| Lifecyc kWh | 1,076,988,623 |  |  |  |  |  |  |  |  | 1,076,988,623 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Industry Specific Case Studies | TBD | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| 2005 Title 24 Seminars | 2 - 6 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 – 6 |
| Other Seminars (PY 2004) | 4 - 6 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 – 6 |

  - Activities/Accomplishments

    - Administrative -

None

    - Marketing -

No activity charged to procurement budget for this time period.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

No changes for this time period.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

SCE Savings By Design activities:

  - Held Savings By Design Program staff meeting

The procurement-funded Savings By Design program underwent a series of fundshifts in the month of September.  The first shift transferred $500k from DI Incentives into the DI Incentives budget of the procurement-funded Single Family EE Rebates program.  The second shift transferred $940k from DI Incentives to fund the procurement-funded VeSM Advantage Plus2 program.  In December, procurement-funded Savings By Design shifted $1M from DI Incentives to the DI Incentives budget of the procurement-funded Single Family EE Rebates program.