| Program Implementer Name: | Southern California Edison |  |  |  |
| --- | --- | --- | --- | --- |
| Program Title: | Community Energy Partnership – PGC |  |  |  |
| Program Number: | 1196-04 |  |  |  |
| Month: | October 2005 |  |  |  |

- Background

The Community Energy Partnership is a complementary delivery mechanism for energy efficiency that draws upon the unique strengths of a myriad of energy stakeholders to create a powerful synergy. The partnership is multidimensional, beginning with Southern California Edison and Southern California Gas as Utility Partners, The Energy Coalition as Facilitating Partner, and ten, partner southern California cities representing their 1,000,000 residents, institutions, and business constituents.

On one hand the Partnership is between cities that are out to make a difference in the energy equation. Through the model approach, the serving utilities have a unique opportunity to develop strong ties working with the program’s cities. It is about citizens and businesses working closely with community-based organizations to improve their financial condition. It is about dedicated school administrators, teachers, and students, working with their staffs and school districts to save precious resources and care for the environment. It is about hearing of a community event, and telling one’s neighbor. It is about creating Energy Champions in California cities to sustain the efficiency message.

The Community Energy Partnership model presented herein is nothing short of a movement. It involves people working together to foster responsible energy use and management in California cities. It involves leadership and tremendous levels of volunteerism.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,000,000 | $177,092 | 4% | $3,572,570 | 89% |  |  | $3,572,570 | 89% | $427,430 |
| Admin | $1,450,000 | $1,099 | 0% | $972,732 | 67% |  |  | $972,732 | 67% | $477,268 |
| Marketing | $298,000 |  |  | $286,573 | 96% |  |  | $286,573 | 96% | $11,427 |
| DI | $2,089,500 | $164,537 | 8% | $2,056,918 | 98% |  |  | $2,056,918 | 98% | $32,582 |
| EM&V | $162,500 | $11,456 | 7% | $256,347 | 158% |  |  | $256,347 | 158% | -$93,847 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Oct-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,298 |  |  | 4,635 | 108% |  |  | 4,635 | 108% | -337 |
| Annual kWh | 15,262,440 |  |  | 18,181,610 | 119% |  |  | 18,181,610 | 119% | -2,919,170 |
| Lifecyc kWh | 76,312,200 |  |  | 90,908,050 | 119% |  |  | 90,908,050 | 119% | -14,595,850 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Oct-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N/A |  |  |  |  |  |  |  |  |  |  |

  - Activities/Accomplishments

The CEP program continued implementation activities during October.  The primary focus being that of direct installation services for residences and small commercial customers.

The PEAK Student Energy Action component of the program continues to expand its role.  The educational booklet under development and to be disseminated in November to participating high schools has been well received.

    - Administrative

    - Marketing

    - Direct Implementation

      - Audits, Site Surveys and Partnerships -

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

      - Calculated and Actual Payment Reconciliation -

Total calculated expenses may be different than actual expenses as actual measure costs may be different than prescribed in the workbook.

    - EM&V

- None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

5.   Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None