| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Residential Appliance Recycling Program - PGC |
| Program Number: | 1232-04 |
| Month: | September 2005 |

- Program Status

Program Description

The Statewide Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.  The program is offered to customers within the investor-owned utilities’ (IOUs) service territories of Pacific Gas and Electric (PG&E), Southern California Edison (SCE), and San Diego Gas & Electric (SDG&E).

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,322,000 | $50,000 | 0% | $7,870,575 | 64% | $831,336 | 7% | $8,701,911 | 71% | $4,451,425 |
| Admin | $912,728 | $46,819 | 5% | $805,903 | 88% |  |  | $805,903 | 88% | $106,825 |
| Marketing | $220,000 |  |  | $188,196 | 86% |  |  | $188,196 | 86% | $31,804 |
| DI | $10,867,272 | $3,181 | 0% | $6,876,476 | 63% | $831,336 | 8% | $7,707,812 | 71% | $3,990,796 |
| EM&V | $322,000 |  |  |  |  |  |  |  |  | $322,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,514 | 2 | 0% | 6,209 | 65% | 751 | 8% | 6,960 | 73% | 3,305 |
| Annual kWh | 55,670,889 | 11,763 | 0% | 36,098,332 | 65% | 4,369,870 | 8% | 40,468,202 | 73% | 19,572,558 |
| Lifecyc kWh | 334,025,336 | 70,579 | 0% | 216,589,990 | 65% | 26,219,219 | 8% | 242,809,209 | 73% | 117,435,346 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Encourage program participation from the "hard-to-reach" (HTR) customer segment as defined by the CPUC in the Energyb Policy Manual | 57% of all customer participation | 0% | n/a | 52% | n/a | 0% | n/a | 52% | n/a |  |

  - Activities/Accomplishments

    - Administrative –

- The SCE RARP Program Manager and Program Analyst conducted a random inspection of the refrigerators and freezers turned in to verify program compliance.  This verification process is performed monthly and the results of each inspection are tabulated and reviewed with the recycling contractor to monitor program compliance.

- New verification procedures were implemented effective September 1 to more closely monitor program compliance as it relates to the working (cooling) condition of refrigerators/freezers when picked up by recycling contractor drivers.  Ride alongs were conducted by SCE inspectors on September 16, 21, and 22 to verify that units were cooling.  The disqualification results of those inspections were measured against the total disqualifications reported by the recycling contractor drivers for the month. These inspections will be ongoing to monitor contractor program compliance.

    - Marketing -

- Planning a Recycling Pick-Up Day event on Catalina Island in conjunction with the Catalina Energy Efficiency Outreach event to be held on October 13-14.

- Planning an event to commemorate the 500,000th refrigerator/freezer picked up since program inception in 1994.  The event is tentatively scheduled for November.

- Continued to promote RARP through the use of the Mobile Educational Unit (aka Energy Star Bus) at various events held throughout the SCE service territory.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Number Installed in September |
| --- | --- |
| Refrigerators | 12 |
| Freezers | 4 |

      - Calculated and Actual Payment Reconciliation -

The calculated rebate amount shown in the program’s corresponding workbook does not reflect the cost to pick-up and recycle the refrigerator/freezer.

    - EM&V

By approval of the Energy Division staff and its evaluation consultants, one portion of the 2004-5 EM&V is moving ahead in advance of the remainder of the study.  Work is now underway to meter two samples of refrigerators recycled through the program.  One sample is metered under controlled Department of Energy testing procedures, and the other sample is metered at the sites from which the refrigerators are to be collected.  Dual Metering data collection will be completed by the end of summer 2005. A draft RFP was circulated for feedback from the project advisory committee. The finalized RFP is expected to be released by the end of August 2005.

- Program Challenges

- Program challenges related to the unit age restriction have been removed as a result of the CPUC’s approval to lift the age restriction as of May 5.

- Customer Disputes

None

- Compliance Items

Distributed RARP marketing literature at energy efficiency events that includes information on energy savings associated with the disposal of older, spare refrigerators and freezers as directed by the CPUC.

Conducting the following activities to monitor program compliance:

  - Random ride alongs with recycling contractor drivers to verify working (cooling) condition of refrigerators and freezers.

  - Random on-site recycling facility inspections of refrigerators and freezers to verify units collected by recycling contractor.

  - Random customer surveys to verify customer participation and to measure satisfaction levels.

- Coordination Activities

- Coordinated efforts with the Home Energy Survey Program to promote RARP by providing brochures in Mail-In Survey reports, distributing brochures during the In-Home Surveys and creating a web site link from the On-Line Survey reports to the RARP program information/sign up web site page.

- Coordinated efforts with various SCE Energy Efficiency Partnership Programs (e.g., South Bay, Ventura, and Kern County) to promote RARP by distributing brochures through various events held within the cities/counties of those partnership territories.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None

The PGC-funded Appliance Recycling program underwent a fundshift in December that transferred $350k from DI Incentives to the DI Incentives budget of the PGC-funded Single Family EE Rebates program.

The PGC-funded Appliance Recycling program underwent a fundshift in December that transferred $350k from DI Incentives to the DI Incentives budget of the PGC-funded Single Family EE Rebates program.