| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Residential Appliance Recycling Program - PGC |
| Program Number: | 1232-04 |
| Month: | March 2004 |

- Program Status

Program Description

The Statewide Residential Appliance Recycling program (RARP) is designed to produce cost effective coincident peak demand reduction and long-term annual energy savings by allowing eligible customers (single family and multifamily owners/landlords and tenants) to dispose of their operable, inefficient primary and secondary refrigerators and freezers in an environmentally safe manner.  The program is offered to customers within the investor-owned utilities’ (IOUs) service territories of Pacific Gas and Electric (PG&E), Southern California Edison (SCE), and San Diego Gas & Electric (SDG&E).

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,322,000 | $41,681 | 0% | $82,251 | 1% | $87,234 | 1% | $169,485 | 1% | $12,239,749 |
| Admin | $912,728 | $38,912 | 4% | $77,799 | 9% |  |  | $77,799 | 9% | $834,929 |
| Marketing | $220,000 |  |  |  |  |  |  |  |  | $220,000 |
| DI | $10,867,272 | $2,769 | 0% | $4,452 | 0% | $87,234 | 1% | $91,686 | 1% | $10,862,820 |
| EM&V | $322,000 |  |  |  |  |  |  |  |  | $322,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 9,514 |  |  |  |  | 79 | 1% | 79 | 1% | 9,514 |
| Annual kWh | 55,670,889 |  |  |  |  | 459,841 | 1% | 459,841 | 1% | 55,670,889 |
| Lifecyc kWh | 334,025,336 |  |  |  |  | 2,759,046 | 1% | 2,759,046 | 1% | 334,025,336 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Encourage program participation from the "hard-to-reach" (HTR) customer segment as defined by the CPUC in the Energyb Policy Manual | 57% of all customer participation | 0% | n/a | 0% | n/a | 0% | n/a | 0% | n/a | 57% |

  - Activities/Accomplishments

    - Administrative –

- Program manager participated in two daylong ride-alongs with recycling contractor (XXXXX) to evaluate and assess the program’s pick-up process. Information gathered during the ride along included customer experiences with the scheduling process and logistical issues with the pickup (customers not present for the scheduled pickup, units not plugged in, etc.).

- Program manager provided results of the random sampling of refrigerators and freezers taken at the recycling facilities in Compton, California to determine age and labeling of units.  It was determined that about 1/3 of the sampled units were manufactured after 1989 and only 1/3 of all units sampled had the model year listed on the manufacturer’s labels.

    - Marketing -

See Supporting Documentation section below.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

None

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

Developed RARP marketing literature to include information on energy savings associated with the disposal of older refrigerators and freezers as directed by the CPUC.  The literature also included the new RARP qualification (effective July 1, 2004) which will require refrigerators and freezers to be manufactured prior to 1990.

- Coordination Activities

Discussions were initiated with the South Bay Energy partnership program to promote RARP through outreach efforts conducted by the partnership.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None