| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Single Family Energy Efficiency Rebates Program - PGC |
| Program Number: | 1234-04 |
| Month: | December 2005 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program of 2004-2005 offers measures from the traditional part of the program as well as measures previously included in the 2003 Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program allows synergies and efficiencies in the areas of administration, materials preparation, and communications to the various market actors.  While all residential customers have the opportunity to participate in the program, additional marketing and promotional activity is targeted to customer segments defined as hard-to-reach (HTR).  This targeted marketing activity increases awareness and participation from these customers to ensure that the HTR goals are met or exceeded.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,438,000 | $522,016 | 5% | $10,258,743 | 98% | $695,940 | 7% | $10,954,683 | 105% | $179,257 |
| Admin | $2,149,126 | $102,749 | 5% | $1,841,559 | 86% |  |  | $1,841,559 | 86% | $307,567 |
| Marketing | $594,000 | -$5,192 | -1% | $466,856 | 79% |  |  | $466,856 | 79% | $127,144 |
| DI | $7,256,874 | $424,459 | 6% | $7,950,328 | 110% | $695,940 | 10% | $8,646,268 | 119% | -$693,455 |
| EM&V | $438,000 |  |  |  |  |  |  |  |  | $438,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Dec-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 21,993 | 2,165 | 10% | 25,569 | 116% | 732 | 3% | 26,302 | 120% | -3,576 |
| Annual kWh | 74,818,692 | 11,038,912 | 15% | 104,082,516 | 139% | 1,111,507 | 1% | 105,194,023 | 141% | -29,263,824 |
| Lifecyc kWh | 817,217,244 | 105,397,521 | 13% | 1,136,674,374 | 139% | 16,620,905 | 2% | 1,153,295,279 | 141% | -319,457,130 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Dec-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Single Family Rebate Program Hard-To-Reach: Achieve 34% of the program's applications from zip codes designated as hard-to-reach | 34% |  | n/a | 41% | n/a | 0% | n/a | 41% | n/a |  |
| Lighting: 15% of Incentives to go to geographical HTR areas outside L.A. Basin. | 15% |  | n/a | 48% | n/a | 0% | n/a | 48% | n/a |  |
| Lighting: 10% of Incentives to go to customers through grocery or drug retailers. | 10% |  | n/a | 36% | n/a | 0% | n/a | 36% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- The kW, kWh, and Hard-to-Reach goals for the program were achieved.

    - Marketing –  none

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Measures Installed in December 2005 |
| --- | --- |
| Pool Pump | 4 |
| Room ACs | 1,549 |
| Electric Water Heaters | 1 |
| High Performance Windows | 0 |
| Programmable Thermostats | 2,021 |
| Attic and Wall Insulation | 0 |
| Whole House Fans | 23 |
| Evaporative Coolers | 32 |
| HVAC | 180 |
| Lighting Measures | 143,372 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

The EM&V activity is being done as a supplement to the 2004-05 EM&V study of statewide Single Family Energy Efficiency Rebate program that is being managed by PG&E.

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None

The PGC-funded Single Family EE Rebates program underwent a fundshift in the month of October that took $80k from Administrative, $30k from Marketing, and $90k from Direct Implementation and put it into the Incentives budget.  The second shift, in December, transferred $350k into the DI Incentives budget from the DI Incentives budget of the PGC Appliance Recycling program.

The PGC-funded Single Family EE Rebates program underwent a fundshift in the month of October that took $80k from Administrative, $30k from Marketing, and $90k from Direct Implementation and put it into the Incentives budget.  The second shift, in December, transferred $350k into the DI Incentives budget from the DI Incentives budget of the PGC Appliance Recycling program.