| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Single Family Energy Efficiency Rebates Program - PGC |
| Program Number: | 1234-04 |
| Month: | March 2004 |

- Program Status

Program Description

The Single Family Energy Efficiency Rebate (SFEER) program of 2004-2005 offers measures from the traditional part of the program as well as measures previously included in the Residential Upstream Lighting program. Combining all these measures applicable to residential customers under the same program allows synergies and efficiencies in the areas of administration, materials preparation, and communications to the various market actors.  While all residential customers have the opportunity to participate in the program, additional marketing and promotional activity is targeted to customer segments defined as hard-to-reach (HTR).  This targeted marketing activity increases awareness and participation from these customers to ensure that the HTR goals are met or exceeded.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $10,437,999 | $494,511 | 5% | $698,569 | 7% | $1,168,508 | 11% | $1,867,077 | 18% | $9,739,430 |
| Admin | $2,149,125 | $88,551 | 4% | $227,692 | 11% |  |  | $227,692 | 11% | $1,921,433 |
| Marketing | $594,000 | $9,652 | 2% | $24,162 | 4% |  |  | $24,162 | 4% | $569,838 |
| DI | $7,256,874 | $396,308 | 5% | $446,715 | 6% | $1,168,508 | 16% | $1,615,223 | 22% | $6,810,159 |
| EM&V | $438,000 |  |  |  |  |  |  |  |  | $438,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 21,969 | 929 | 4% | 939 | 4% | 4,399 | 20% | 5,339 | 24% | 21,030 |
| Annual kWh | 74,664,923 | 1,119,885 | 1% | 1,131,558 | 2% | 27,161,275 | 36% | 28,292,833 | 38% | 73,533,364 |
| Lifecyc kWh | 815,046,340 | 16,633,133 | 2% | 16,805,293 | 2% | 278,667,286 | 34% | 295,472,579 | 36% | 798,241,047 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Single Family Rebate Program Hard-To-Reach: Achieve 34% of the program's applications from zip codes designated as hard-to-reach | 34% | 37% | n/a | 37% | n/a | 0% | n/a | 37% | n/a |  |
| 15% of Incentives to go to geographical HTR areas outside L.A. Basin. | 15% | 0% | n/a | 0% | n/a | 0% | n/a | 0% | n/a |  |
| 10% of Incentives to go to customers through grocery or drug retailers. | 10% | 0% | n/a | 0% | n/a | 0% | n/a | 0% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Completed agreements with Organizational Support Services for them to provide filed support services related to the implementation of point-of-sale.

- Completed point-of-sale agreement with Home Depot regarding programmable thermostats.  Entered discussions on expanding to room air conditioners.

- Completed lighting promotion initial allocations.

- Announced Summer/Fall lighting promotion.

    - Marketing -

See Supporting Documentation section below.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Installed | Numbers of Measures Installed |
| --- | --- |
| Pool Measures | 286 |
| Room AC’s | 1 |
| Electric Water Heaters | 6 |
| Windows | 125,577 |
| Programmable Thermostats | 1,495 |
| Whole House Fan | 36 |
| Evaporative Coolers | 30 |
| HVAC | 496 |
| Lighting Measures | 0 |

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

The program is rapidly becoming oversubscribed.  It is anticipated that all non-lighting funds will be expended by June 2004, just two months away.  Lighting funds will be expended according to a scheduled time-table spaced throughout the year.  Additionally, the non-lighting applications coming in are tending to favor those measures with the lower kWh/$.  This results in energy savings and demand reductions falling behind in proportion to the budget expended.  Efforts to correct this are underway, principally via the acceleration of the programmable thermostats point-of-sale effort.  This effort will alleviate this problem, but the larger problem of running out of funds early this summer still remains.

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program Manager and subcontractors have not changed.

- Additional Items

None