| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Multifamily Energy Efficiency Rebates Program - PGC |
| Program Number: | 1236-04 |
| Month: | May 2004 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,236,469 | $44,025 | 1% | $595,626 | 14% | $667,571 | 16% | $1,263,197 | 30% | $3,640,843 |
| Admin | $562,800 | $18,730 | 3% | $114,168 | 20% |  |  | $114,168 | 20% | $448,632 |
| Marketing | $88,800 | $6,905 | 8% | $7,040 | 8% |  |  | $7,040 | 8% | $81,760 |
| DI | $3,347,900 | $18,391 | 1% | $474,417 | 14% | $667,571 | 20% | $1,141,988 | 34% | $2,873,483 |
| EM&V | $236,969 |  |  |  |  |  |  |  |  | $236,969 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 2,036 |  |  | 279 | 14% | 519 | 25% | 798 | 39% | 1,758 |
| Annual kWh | 12,111,695 |  |  | 1,991,611 | 16% | 2,802,111 | 23% | 4,793,722 | 40% | 10,120,084 |
| Lifecyc kWh | 139,723,639 |  |  | 21,038,642 | 15% | 32,911,980 | 24% | 53,950,622 | 39% | 118,684,997 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

- Hard to Reach: The HTR target for 2004 is to have 36 percent of the project applications come from HTR customers.  As of May 2004, 63 percent of the submitted rebate applications came from HTR customers.

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2004 program year.

    - Marketing -

- MFEER program brochure translated into Spanish language and printed.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in May1 | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 0 | 31,703 |
| Fluorescent Fixtures | 0 | 14,167 |
| T8/T5 Lamps | 0 | 4,598 |
| Low E Windows | 0 | 4,975 sq ft. |
| Prog. Thermostats | 0 | 2,744 |
| Sensors | 0 | 25 |
| Exit Signs | 0 | 142 |
| Ceiling Fans | 0 | 37 |
| Room A/Cs | 0 | 10 |
| Package Terminal HP | 0 | 5 |

1 System constraints required a temporary accounting distribution adjustment resulting in all program measures being assigned to the Procurement budget in May.  The system has been corrected and necessary adjustments will be shown in the following month.

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual participant purchase price.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None