| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Multifamily Energy Efficiency Rebates Program - PGC |
| Program Number: | 1236-04 |
| Month: | March 2005 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,236,969 | $642,143 | 15% | $2,564,877 | 61% | $738,855 | 17% | $3,303,732 | 78% | $1,672,092 |
| Admin | $563,300 | $42,016 | 7% | $375,195 | 67% |  |  | $375,195 | 67% | $188,105 |
| Marketing | $88,800 | $6,615 | 7% | $53,063 | 60% |  |  | $53,063 | 60% | $35,737 |
| DI | $3,347,900 | $593,512 | 18% | $2,136,619 | 64% | $738,855 | 22% | $2,875,475 | 86% | $1,211,281 |
| EM&V | $236,969 |  |  |  |  |  |  |  |  | $236,969 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 2,036 | 374 | 18% | 1,373 | 67% | 534 | 26% | 1,906 | 94% | 664 |
| Annual kWh | 12,111,695 | 2,150,093 | 18% | 8,581,180 | 71% | 3,827,780 | 32% | 12,408,959 | 102% | 3,530,515 |
| Lifecyc kWh | 139,723,639 | 24,082,729 | 17% | 94,807,918 | 68% | 38,161,058 | 27% | 132,968,976 | 95% | 44,915,721 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The HTR target is to have 36 percent of all rebate applications come from HTR customers. | 36% |  | n/a | 54% | n/a |  | n/a | 54% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Conducted bi-weekly conference calls with Statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2005 program year.

- As of March, the MFEER program has essentially met the two-year energy and demand savings targets.

    - Marketing -

- Ongoing advertisements in three monthly publications sent directly to apartment owners and managers.

- Exhibitor at the Apartment Association of Orange County’s annual trade show.  Roughly 3,000 property owners and managers were in attendance.  SCE’s booth, promoting the MFEER program, experienced high traffic during the one-day event.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Paid in March | Total Paid & Committed |
| --- | --- | --- |
| CFLs | 14,997 | 97,790 |
| Fluorescent Fixtures | 7,271 | 34,959 |
| T8/T5 Lamps | 1,026 | 6,136 |
| Low E Windows | 3,749 | 6,984 sq ft. |
| Prog. Thermostats | 1,480 | 5,592 |
| Exit Signs | 26 | 401 |
| Room A/Cs | 0 | 47 |
| Ceiling Fan | 0 | 5 |
| Central HVAC/HP | 0 | 6 |

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual customer purchase price.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

One of the local apartment association chapters has approached the MFEER program management requesting assistance to develop a new member base in the San Gabriel Valley where there has historically been little trade support to multifamily property owners and managers.  SCE’s role in this effort is to be represented as one of the many resources available to potential members through their membership in the apartment association.  This type of networking indicates the value that the MFEER program brings to the multifamily industry and its actors.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None