| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Multifamily Energy Efficiency Rebates Program - PGC |
| Program Number: | 1236-04 |
| Month: | March 2004 |

- Program Status

Program Description

The Statewide Multifamily Energy Efficiency Rebate program is offered in the service areas of Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  The Multifamily program promotes energy savings by providing cash rebates for the installation of qualified energy-efficient products in apartment dwelling units, in the common areas of apartment and condominium complexes and common areas of mobile home parks.  Property owners, and property managers as authorized agents for property owners, of existing residential multifamily complexes with five or more dwelling units may qualify.  The Multifamily program uses an integrated approach of combining information, education, and energy surveys including targeted marketing and customer incentives to encourage property owners/managers to install energy-efficient measures.  This multi-faceted approach is important for reaching this underserved market, educating property owners/managers and their tenants about the benefits of installing energy saving products, and encouraging this customer segment to take the desired actions.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,236,469 | $286,946 | 7% | $341,408 | 8% | $843,702 | 20% | $1,185,110 | 28% | $3,895,061 |
| Admin | $562,800 | $25,555 | 5% | $65,636 | 12% |  |  | $65,636 | 12% | $497,164 |
| Marketing | $88,800 |  |  | $135 | 0% |  |  | $135 | 0% | $88,665 |
| DI | $3,347,900 | $261,391 | 8% | $275,636 | 8% | $843,702 | 25% | $1,119,339 | 33% | $3,072,264 |
| EM&V | $236,969 |  |  |  |  |  |  |  |  | $236,969 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

| Energy Effects | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 2,036 | 176 | 9% | 176 | 9% | 551 | 27% | 728 | 36% | 1,860 |
| Annual kWh | 12,111,695 | 1,204,054 | 10% | 1,204,054 | 10% | 3,349,759 | 28% | 4,553,813 | 38% | 10,907,641 |
| Lifecyc kWh | 139,723,639 | 12,852,749 | 9% | 12,852,749 | 9% | 38,564,170 | 28% | 51,416,919 | 37% | 126,870,890 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

Not applicable

  - Activities/Accomplishments

    - Administrative -

- Conducted weekly conference calls with statewide Multifamily IOU team for continuity of program implementation and planning for statewide marketing activities.

- Managed program funding and customer rebate reservations toward SCE’s goal of maintaining funding availability throughout the entire 2004 program year.

    - Marketing -

In addition to the information provided in the Supporting Documentation section of this report, SCE:

- Exhibited at the Apartment Association of Orange County’s annual trade show, March 18, 2004.

- Presented to the Apartment Association, California Southern Cities monthly membership meeting, March 25, 2004.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Rebate Measures

| Measure | Paid | Total |
| --- | --- | --- |
| CFLs | 9,448 | 31,144 |
| Fluorescent Fixtures | 3,666 | 15,481 |
| T8/T5 Lamps | 574 | 4,900 |
| Low E Windows | 1,378 sq ft. | 6,470 sq ft. |
| Prog. Thermostats | 436 | 2,030 |
| Heating/Cooling Sys. | 0 | 10 |
| Sensors | 0 | 7 |
| Exit Signs | 0 | 22 |

      - Calculated and Actual Payment Reconciliation -

Total calculated rebate payments will be higher than actual rebate payments as rebate amounts paid cannot exceed actual participant purchase price.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Initiated discussions with SCE-LA County Partnership program leveraging rebate dollars to supplement program offerings.

- Negotiating with existing LIEE subcontractors to utilize extensive multifamily network for the delivery of fluorescent torchieres to apartment residents.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None