| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | May 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,731 | $46,701 | 1% | $170,267 | 5% |  |  | $170,267 | 5% | $2,958,464 |
| Admin | $532,800 | $16,793 | 3% | $114,301 | 21% |  |  | $114,301 | 21% | $418,499 |
| Marketing | $538,000 | $5,475 | 1% | $6,780 | 1% |  |  | $6,780 | 1% | $531,220 |
| DI | $1,929,552 | $24,433 | 1% | $49,186 | 3% |  |  | $49,186 | 3% | $1,880,366 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | May-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 0 | 0% | 0 | 0% | 285 | 2.1% | 285 | 2.1% | 13,215 |
| On-line Energy Surveys | 9,000 | 1,208 | 13.4% | 0 | 0% | 0 | 0% | 1,208 | 13.4% | 7,792 |
| In-Home Energy Surveys | 4,000 | 315 | 7.9% | 601 | 15% | 214 | 5.4% | 815 | 20.4% | 3,185 |
| Telephone Energy Surveys | 500 | 3 | .6% | 23 | 4.6% | 19 | 3.8% | 42 | 10.5% | 458 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed | 50,000 | 100% | 50,000 | 100% | 0% | n/a | 50,000 | 100% | 0 |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed | 0% | n/a | 7% | n/a | 0% | n/a | 7% | n/a |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Reviewed and finalized details of contractor’s pricing proposal for the development of the new Asian energy surveys with the HEES Statewide Team.

- Finalized details with the HEES Statewide Team to provide Vietnamese Mail-In Surveys in September/October 2004.

- Mailed 50,000 Mail-In Survey solicitation packages.

- Coordinated efforts with the IOUs and the Bakersfield/Kern Energy Watch Partnership to utilize the Mail-In Survey instrument for their In-Home Survey.

- Began process of promoting the appliance recycling program by inserting brochures in the Energy Report packages mailed to participants of the survey.

On-Line Survey

- Began Starbucks campaign on 05/19/04 that offers $5 Starbucks Cards to customers who completed an On-Line Survey.  The campaign achieved 379 completed surveys thus far, which represents 29% of 1,296 surveys completed.

- Promotes energy efficiency programs and services by creating web site links to EE rebate application and appliance recycling programs.

In-Home Survey

- Completed 13 In-Home Surveys in Catalina’s outreach effort.

- Began the combined effort with SCG and completed 4 joint In-Home Surveys for both electric and gas customers.

- Submitted Statement of Work for an RFP to solicit proposals from vendors to implement the In-Home Survey component starting August 1, 2004.  RFP was issued late May 2004 and response are due June 2004.

- Finalized process to verify if customers received the In-Home Survey as reported by the Contractor.

- Began process of promoting the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

    - Marketing –

In addition to the list in Attachment A:

- Contractor mailed 50,000 Mail-In Survey solicitation packages on May 19, 2004.

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys |
| --- | --- |
| 285 Mail-In Surveys | $12.30 |
| 1,208 On-Line Surveys | $11.31 |
| 815 In-Home Surveys | $81.81 |
| 42 Telephone Surveys | $42.86 |

Note:  Data includes total number of customer surveys from January through May 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None.

- Coordination Activities

- Finalized details with the HEES Statewide Team to exchange, at no additional cost, PG&E, SCE and SCG’s Chinese Mail-In Survey with SDG&E’s Vietnamese Mail-In Survey.

- Began process of promoting the appliance recycling program by providing brochures to customers with the mailing of Mail-In Survey results as well as upon completion of the In-Home Survey.

- Promotes energy efficiency programs and services by creating web site links in the On-Line Survey to EE rebate application and appliance recycling programs.

- Coordinated efforts with the IOUs and the Bakersfield/Kern Energy Watch Partnership to utilize the Mail-In Survey instrument for their In-Home Survey.

- Provided giveaway items and flyers to the South Bay Energy Savings Center and the Ventura Partnership program.  These items were paid for with 2003 funds.

- Coordinated efforts with SCG to conduct In-Home Surveys for both electric and gas customers.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None