| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | May 2005 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $54,249 | 2% | $1,745,835 | 56% |  |  | $1,745,835 | 56% | $1,382,544 |
| Admin | $532,446 | $19,894 | 4% | $378,027 | 71% |  |  | $378,027 | 71% | $154,419 |
| Marketing | $538,000 | $26,016 | 5% | $304,082 | 57% |  |  | $304,082 | 57% | $233,918 |
| DI | $1,929,554 | $8,339 | 0% | $1,063,726 | 55% |  |  | $1,063,726 | 55% | $865,828 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 27,000 | 2,964 | 10.9% | 27,526 | 101.9% | 0 | 0% | 27,526 | 101.9% | 0 |
| On-Line Energy Surveys | 18,000 | 2,419 | 13.4% | 13,328 | 74.0% | 0 | 0% | 13,328 | 74.0% | 4,672 |
| In-Home Energy Surveys | 8,000 | 223 | 2.7% | 5,604 | 70.0% | 0 | 0% | 5,604 | 70.0% | 2,396 |
| Telephone Energy Surveys | 1,000 | 86 | 8.6% | 811 | 81.1% | 0 | 0% | 811 | 81.1% | 189 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed |  | 100% |  | 100% |  | n/a |  | 100% |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed |  | 78% |  | 78% |  | n/a |  | 78% |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Achieved processing of 2,884 mail-in surveys.  This brings program total to 27,526 completed and processed surveys in the 2004-2005 program year.  Of these completed surveys, 1,455 were completed and processed in Spanish, 2,451 in Chinese, and 319 in Vietnamese.

- Continue to work with Resource Action Programs to target sixth grade classrooms by distributing the LivingWise® activities kits containing electric and water measures.  Each kit includes a survey for completion by the student’s parents.  The pilot program distributed 2,167 kits to South Bay elementary and 846 kits to Torrance middle schools’ students.

- Continue to work with Asian Pacific American Community Service Center, a local community-based organization, to promote the program to the Chinese- and Vietnamese-speaking communities.  This collaboration achieved 500 Chinese and 170 Vietnamese completed surveys.

- Continue to work with the statewide team and finalized translations of the survey packages from English to Korean.  Scheduled mailing in 3rd quarter.

- Mailed 40,000 English surveys to 100 percent customers defined in the Energy Efficiency Policy Manual as in hard-to-reach segments.

- Scheduled mailing of Spanish, Vietnamese, Chinese and Korean surveys in 3rd quarter.

On-Line Survey

- Achieved processing of 2,419 on-line surveys.  This brings program total to 13,328 completed and processed surveys in the 2004-2005 program year.  Of the completed surveys, 50 took the survey in Spanish and 76 took the survey in Chinese.

- Marketing campaign launched on May 9, 2005, to increase survey participation.  Eligible SCE customer will receive a $5 Target Giftcard when they complete the survey online.  Campaign sent out 245,841 English e-mails to L.A. Times subscribers.  There were 1,579,362 English on-line banner ads appeared in AOL Network, Tribal Fusion and L.A. Newsgroup.  There were also 248,160 Chinese and 184,569 Spanish on-line banner ads appeared in Sina.com and Terra.com.

- Survey site enhanced to collaborate with SCE’s 20/20 Summer Savings Program.  SCE is encouraging customers to practice greater energy conservation during the summer to help maintain a stable electrical supply.  Qualifying residential and commercial customers will save by using 20% less and SCE will give a 20% credit on the first winter bill.  The enhancements provide last summer’s usage, and tips to save energy during this year’s hot summer months.

- Continue planning for development of the Vietnamese on-line interactive survey to be launched in 3rd quarter.

In-Home Survey

- Achieved 309 completed surveys.  This brings program total to 6,415 surveys conducted in the 2004-2005 program year.  Of these completed surveys, 1,500 surveys (23%) were conducted in Spanish.  Of these completed surveys, 4,998 customers (78%) are defined by the Energy Efficiency Policy Manual as in hard-to-reach segments.

- Completed 134 SCE/SoCalGas joint surveys for both electric and gas customers in shared service territories.  This brings total joint surveys conducted to 1,016 surveys in the 2004-2005 program year.

- Mailed 30,000 solicitation cards to customers in Palm Springs, Yucca Valley, Hemet and Temecula areas.  Energy Efficiency Policy Manual defined these areas as geographically hard-to-reach communities.  This was a joint effort with SoCalGas to target shared customers.

- Scheduled mailing of 30,000 solicitation cards to customers in Tulare and Visalia areas.

    - Marketing –

None

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 27,526 Mail-In Surveys | $12.30 | Same |
| 13,328 On-Line Surveys | $11.31 | Same |
| 5,604 In-Home Surveys | $81.81 | $91.46 |
| 811 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January 2004 through May 2005, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are increased in August as a result of the competitive bid issued in May 2004.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Completed 2006-2008 HEES program budget and concept paper to be filed on June 1, 2005.

- Continue to participate in the 2006-2008 HEES program planning process, and coordinate program planning with SoCalGas, PG&E and SDG&E.

- Continued dialogues with contractor in soliciting ideas for 2006-2008 program year and draft statement of work.

- Mail-In Survey

  - Continue to promote the appliance recycling program by inserting a brochure with all survey packages and energy report mailed.

- On-Line Survey

  - Continue to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

- In-Home Survey

  - Continue the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers in shared service territories.

  - Provided contractor with new program offerings, rebates applications, and rate increase information, in order to answer customers’ inquiries.

  - Continue to provide customers with two CFLs after completion of the survey, for immediate energy savings.

  - Continue to provide survey contractor with CARE applications for the low- and moderate-income customers that participated in the survey, and promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None