| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | September 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,731 | $123,308 | 4% | $689,905 | 22% |  |  | $689,905 | 22% | $2,438,826 |
| Admin | $532,800 | $23,407 | 4% | $195,315 | 37% |  |  | $195,315 | 37% | $337,485 |
| Marketing | $538,000 | $8,634 | 2% | $77,122 | 14% |  |  | $77,122 | 14% | $460,878 |
| DI | $1,929,552 | $91,267 | 5% | $417,469 | 22% |  |  | $417,469 | 22% | $1,512,083 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Sep-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 1,449 | 11% | 9,305 | 69% | 0 | 0% | 9,305 | 69% | 4,195 |
| On-Line Energy Surveys | 9,000 | 3,175 | 35% | 10,078 | 112% | 0 | 0% | 10,078 | 112% | Exceeded by 1,078 |
| In-Home Energy Surveys | 4,000 | 521 | 13% | 3,084 | 77% | 0 | 0% | 3,084 | 77% | 916 |
| Telephone Energy Surveys | 500 | 106 | 21% | 318 | 64% | 0 | 0% | 318 | 64% | 182 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed | 19,000 | 100% | 109,000 | 100% | 0 | n/a | 109,000 | 100% | 0 |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed | 491 | 14% | 2,707 | 80% | 0 | n/a | 2,707 | 80% | 0 |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Mailed 9,000 Chinese and 10,000 Spanish survey packages.

- Finalized statewide Vietnamese survey package translation with the Statewide Team members.

- Scheduled mailing of 6,000 Vietnamese survey packages in November.

- Scheduled mailing of 30,000 English survey packages to 100% customer in HTR areas.  Survey packages will be mailed in November; an appliance recycling program brochure will be included with each package.

- Continued to promote the appliance recycling program by providing brochures to customers after completion of a survey.

On-Line Survey

- Continue the Starbucks campaign in offering $5 Starbucks Cards to customers who completed an On-Line Survey.  SCE exceeds its goal by 12%.

- Continued to meet with team members, survey and marketing contractors discussing campaign status, coordinating weekly activities, and planning campaign shut-down.  SCE marketing contractor sent 225,000 e-mail blasts and posted 2,100,000 on-line advertising impressions.

- Continued to monitor and coordinate the weekly campaign fulfillment.  SCE mailed 5,306 Starbucks Cards to customers that completed the survey.

- Finalized Chinese translation of the Home On-Line Energy Survey web site.

- Continued to coordinate with survey contractor in developing and launching the Chinese interactive on-line survey in fourth quarter of 2004.

- Coordinated marketing activities with SCE’s marketing and corporate communication groups to launch the Chinese interactive on-line survey.

- Continued to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

In-Home Survey

- Completed 614 SCE/SoCalGas joint surveys for both electric and gas customers.

- Finalized the Inter-Utility Agreement with SoCalGas to share marketing and promotional mailing material and costs for customers residing in the shared service territories.

- Scheduled mailing of 25,000 solicitation cards to 100% customers in HTR areas.  Cards will be mailed in October.

- Coordinated with EM&V in extracting and verifying the HTR customers’ data on a monthly basis.

- Provided survey contractor with CARE applications to be handed out to lo-income customers that participated in the survey.

- Coordinated outreach to HTR multi-family residents through apartment managers who have previously participated in other statewide energy efficiency program.

- Continued to provide apartment complex’s customers that participated in the survey with a promotional flashlight keychain.

- Continued to promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

    - Marketing –

See the list in Attachment A.

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 9,305 Mail-In Surveys | $12.30 | Same |
| 10,078 On-Line Surveys | $11.31 | Same |
| 3,084 In-Home Surveys | $81.81 | $91.46 |
| 318 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January through September 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are changed in August as a result of the competitive bid issued in May.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Conducted statewide team meeting at SDG&E facility in San Diego.  The team discussed IOUs’ 2004 survey mailing and completion status, Vietnamese survey packages status, EM&V activities, and plan for 2005 mailing and marketing strategies.

- Attended the SCE sponsored Chinese Association Construction Professional Business Expo and promoted the on-line survey along with other energy efficiency programs and services.

- Provided Home On-Line Survey flyers to promote the survey and increase customer awareness of the program at the Local Government Initiative’s meeting.

- Continued the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None