| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | June 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,731 | $72,195 | 2% | $242,462 | 8% |  |  | $242,462 | 8% | $2,886,269 |
| Admin | $532,800 | $15,016 | 3% | $129,318 | 24% |  |  | $129,318 | 24% | $403,482 |
| Marketing | $538,000 |  |  | $6,780 | 1% |  |  | $6,780 | 1% | $531,220 |
| DI | $1,929,552 | $57,179 | 3% | $106,365 | 6% |  |  | $106,365 | 6% | $1,823,187 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 4,283 | 31.7% | 4,634 | 34.3% | 0 | 0% | 4,634 | 34.3% | 8,866 |
| On-line Energy Surveys | 9,000 | 830 | 9.2% | 2,120 | 23.6% | 0 | 0% | 2,120 | 23.6% | 6,880 |
| In-Home Energy Surveys | 4,000 | 516 | 12.9% | 1,682 | 42.1% | 0 | 0% | 1,682 | 42.1% | 2,318 |
| Telephone Energy Surveys | 500 | 43 | 8.6% | 115 | 23% | 0 | 0% | 115 | 23% | 385 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed | 50,000 | 100% | 50,000 | 100% | 0% | n/a | 50,000 | 100% | 0 |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed | 0% | n/a | 7% | n/a | 0% | n/a | 7% | n/a |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Finalized details of contractor’s pricing proposal for the development of the new Asian energy surveys, Chinese for PG&E, SCE and SoCalGas, and Vietnamese for SDG&E service territories.

- Finalized translations to the SCE Vietnamese survey packages, including cover letter, survey, and recommendations.

- Finalized the statewide cover letter to the survey packages, so all the IOUs are conveying the same message to the customers.

- Finalized the program manual binder documenting activities and reports in 2003.

- Continued to promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Updating the Chinese and Spanish recommendations to reflect the changes in 2004 energy efficiency programs.

On-Line Survey

- Finalized the 2Q Starbucks campaign with the on-line marketing vendor.

- Started initial discussion of the 3Q marketing strategy with the new on-line marketing vendor.

- Ended Starbucks campaign that offers $5 Starbucks Cards to customers who completed an On-Line Survey.  The campaign achieved 1,129 completed surveys from May 19 through June 30, 2004.

- Scheduled the 3Q Starbucks promotional flight to start in July.

- Finalized the program manual binder documenting activities and reports in 2003.

In-Home Survey

- Completed 90 SCE/SoCalGas joint surveys for both electric and gas customers.

- Evaluated responses to the RFP issued in May.  Recommendation will be submitted in July.  New contract will start on 08/01/04.

- Mailed 25,000 solicitation cards to customers in HTR areas.

- Continued to verify if customers received the In-Home Survey as reported by the Contractor, for surveys conducted in April and May.

- Continued to promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Finalized the program manual binder documenting activities and report in 2003.

    - Marketing –

In addition to the list in Attachment A:

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys |
| --- | --- |
| 4,634 Mail-In Surveys | $12.30 |
| 2,120 On-Line Surveys | $11.31 |
| 1,682 In-Home Surveys | $81.81 |
| 115 Telephone Surveys | $42.86 |

Note:  Data includes total number of customer surveys from January through June 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Coordinated translation efforts with the HEES Statewide Team to standardized the IOUs Vietnamese, Chinese and Spanish cover letters.

- Promoted the On-Line Surveys by providing flyers at the annual Summer Business Institute orientation held at USC.

- Continued the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None