| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | December 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $310,709 | 10% | $1,164,657 | 37% |  |  | $1,164,657 | 37% | $1,963,723 |
| Admin | $532,446 | $18,388 | 3% | $254,213 | 48% |  |  | $254,213 | 48% | $278,233 |
| Marketing | $538,000 | $49,606 | 9% | $168,416 | 31% |  |  | $168,416 | 31% | $369,584 |
| DI | $1,929,554 | $242,714 | 13% | $742,028 | 38% |  |  | $742,028 | 38% | $1,187,526 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 2,533 | 18.8% | 16,351 | 121% | 0 | 0% | 16,351 | 121% | 0 |
| On-Line Energy Surveys | 9,000 | 148 | 1.6% | 10,865 | 121% | 0 | 0% | 10,865 | 121% | 0 |
| In-Home Energy Surveys | 4,000 | 221 | 5.5% | 4,303 | 107.5% | 0 | 0% | 4,303 | 107.5% | 0 |
| Telephone Energy Surveys | 500 | 30 | 6% | 458 | 91.6% | 0 | 0% | 458 | 91.6% | 42 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed |  | 100% |  | 100% |  | n/a |  | 100% |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed |  | 80% |  | 80% |  | n/a |  | 80% |  |

  - Activities/Accomplishments

    - Administrative

- SCE is in the process of reconciling program expenses through December 2004 and plans to submit a fundshift in the coming months from the PGC HEES program to PGC Single Family EE Rebates program

Mail-In Survey

- Achieved processing of 2,533 mail-in surveys, bringing year-to-date program achievement to 16,351 surveys that exceeded the survey goal of 13,500 by 21 percent.

- Mailed 6,137 Vietnamese survey packages in December.

- Implemented with Resources Action Programs to deliver a school-based energy efficiency educational program within SCE’s service territory.  This school-based program is a joint effort with the Southern California Water Company, in providing outreach and educational services to sixth grade classrooms by distributing the LivingWise® activities kits containing electric and water measures.  The kit will include SCE’s HEES Mail-In Energy survey for completion by the student’s parents.

- Continued working with Asian Pacific American Community Service Center, a local community-based organization, to promote the program to the Asian communities.  The program achieved 462 completed Chinese surveys.

- Completed planning of the 2005 mailing strategies that include mailing of English survey to 100 percent hard-to-reach communities, and mailing of Spanish, Chinese, Vietnamese and a new Asian language surveys throughout SCE service territories.

On-Line Survey

- Achieved processing of 10,865 completed surveys that exceeded the survey goal of 9,000 by 21 percent.

- Started planning of the 2005 on-line survey marketing campaign and creating a new Asian language interactive survey in Vietnamese.

In-Home Survey

- Achieved 4,761 completed surveys that exceeded the survey goal of 4,500 by 6 percent.

- Completed 777 SCE/SoCalGas joint surveys for both electric and gas customers in shared service territories.  Continued discussion with SoCalGas on the 2005 joint efforts.

- Completed verifications of over 130 customers that participated in the survey in 2004.  The purpose is to verify that the survey was completed as reported, and to ensure customers are receiving quality and valuable service from the survey contractor.

- Completed planning of the 2005 mailing strategy strategies that include Los Angeles and Orange County beach areas and other hard-to-reach communities throughout SCE service territories.

    - Marketing –

None

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 16,351 Mail-In Surveys | $12.30 | Same |
| 10,865 On-Line Surveys | $11.31 | Same |
| 4,303 In-Home Surveys | $81.81 | $91.46 |
| 458 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January through December 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are increased in August as a result of the competitive bid issued in May.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Continued discussion and planning for the 2004 program close-out and reconciliation of surveys numbers.

- Continued discussion of the preliminary project plan for 2006 Request for Proposal with the statewide team members.  This solicitation will seek proposals from potential bidders for 2006-2008 program year.

- Coordinated activities to film SCE’s efforts in working with the community to promote energy efficiency programs.  Video scheduled to be released in 2005.

- Promoted energy efficiency programs to Bitely Elementary School and the Ventura County partnership program.

- Mail-In Survey

  - Coordinated activity to insert a refrigerator recycling program flyer with each of the 6,132 Vietnamese survey packages mailed.

  - Continued to promote the appliance recycling program by inserting a brochure with every energy report mailed.  In 2004, more than 16,000 brochures were mailed to customers that participated in the survey.

- On-Line Survey

  - Continued to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

- In-Home Survey

  - Continued the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers in shared service territories.

  - Finalized and extracted the number of hard-to-reach customers that participated in the survey, which represents 80 percent of customers’ participation.

  - Continued to target HTR multi-family residents through apartment managers who have previously participated in other statewide energy efficiency program.

  - Continued to provide apartment complex’s customers that participated in the survey with a promotional flashlight keychain.

  - Continued to provide survey contractor with CARE applications to be handed out to low- and moderate-income customers that participated in the survey, and promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None