| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | October 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $120,170 | 4% | $810,076 | 26% |  |  | $810,076 | 26% | $2,318,304 |
| Admin | $532,446 | $22,130 | 4% | $217,444 | 41% |  |  | $217,444 | 41% | $315,002 |
| Marketing | $538,000 | $41,232 | 8% | $118,355 | 22% |  |  | $118,355 | 22% | $419,645 |
| DI | $1,929,554 | $56,808 | 3% | $474,277 | 25% |  |  | $474,277 | 25% | $1,455,277 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 2,605 | 19.3% | 11,190 | 82.9% | 0 | 0% | 11,190 | 82.9% | 2,310 |
| On-Line Energy Surveys | 9,000 | 458 | 5.1% | 10,533 | 117% | 0 | 0% | 10,533 | 117% | 0 |
| In-Home Energy Surveys | 4,000 | 550 | 13.8% | 3,634 | 90.1% | 0 | 0% | 3,634 | 90.1% | 366 |
| Telephone Energy Surveys | 500 | 36 | 7.2% | 354 | 70.1% | 0 | 0% | 354 | 70.1% | 146 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed | 30,000 | 100% | 139,000 | 100% | 0 | n/a | 139,000 | 100% | 0 |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed | 527 | 14% | 3,234 | 81% | 0 | n/a | 3,234 | 81% | 0 |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Mailed 30,000 English survey packages to 100% customers in HTR areas.  Each package includes a brochure promoting the appliance recycling program.

- Approved the statewide Vietnamese survey package.

- Scheduled mailing of 6,000 Vietnamese survey packages in December.

- Started planning for 2005 mailing strategies.

On-Line Survey

- Ended the Starbucks campaign in mid-October.  SCE exceeds its on-line survey goal by 17%.

- Continued to meet with team members, survey and marketing contractors planning campaign shut-down.

- Continued to monitor and coordinate the weekly campaign fulfillment.  SCE mailed 402 Starbucks Cards to customers that completed the survey.

- Finalized testing of Chinese Home On-Line Energy Survey web site.

- Planned launching of the Chinese interactive on-line survey in November.

- Developed marketing plan to promote Chinese Home On-Line Energy Survey via internal SCE newsletters, press release, Chinese newspapers advertorials, web site banner ad, and radio PSAs.

- Started activities to translate the on-line survey flyer into Chinese.

In-Home Survey

- Completed 668 SCE/SoCalGas joint surveys for both electric and gas customers in 2004.

- Executed the Inter-Utility Agreement with SoCalGas to share marketing and promotional mailing material and costs for customers residing in the shared service territories.

- Mailed 25,000 solicitation cards to 100% customers in HTR areas.

- Discussed with survey contractor to ensure 2004 goal is met and planned 2005 mailing strategy.

    - Marketing –

See the list in Attachment A.

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 11,910 Mail-In Surveys | $12.30 | Same |
| 10,533 On-Line Surveys | $11.31 | Same |
| 3,634 In-Home Surveys | $81.81 | $91.46 |
| 354 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January through September 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are changed in August as a result of the competitive bid issued in May.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Attended the annual Energy Star Appliance and HVAC Partner and Stakeholders meetings in Chicago.  Key discussion topics were ES 2005 plan, appliance criteria update and promotion, advances in appliance technology, appliance recycling, market share tracking, and HVAC specification revision.

- Met with the statewide team members and survey contractor at PG&E facility in San Francisco.  The team discussed IOUs’ 2004 survey mailing and processing status, Vietnamese survey status, 2005 mailing and marketing strategies, Korean mail-in survey development, and plan for 2006 Request for Proposal.  Survey contractor reported administrative and support services status.

- Mail-In Survey

  - Continued to promote the appliance recycling program by inserting a brochure with every energy report mailed.

- On-Line Survey

  - Provided Home On-Line Survey flyers to promote the survey and increase customer awareness to the SCE’s Mobile Education Unit community events, and the US Navy’s Energy Awareness Day.

  - Continued to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

- In-Home Survey

  - Continued the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers.

  - Continued to target HTR multi-family residents through apartment managers who have previously participated in other statewide energy efficiency program.

  - Continued to provide apartment complex’s customers that participated in the survey with a promotional flashlight keychain.

  - Continued to provide survey contractor with CARE applications to be handed out to lo-income customers that participated in the survey, and promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None