| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | July 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,731 | $131,783 | 4% | $374,245 | 12% |  |  | $374,245 | 12% | $2,754,486 |
| Admin | $532,800 | $20,440 | 4% | $149,758 | 28% |  |  | $149,758 | 28% | $383,042 |
| Marketing | $538,000 | $37,553 | 7% | $44,333 | 8% |  |  | $44,333 | 8% | $493,667 |
| DI | $1,929,552 | $73,789 | 4% | $180,154 | 9% |  |  | $180,154 | 9% | $1,749,398 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 2,190 | 16.2% | 5,766 | 42.7% | 0 | 0% | 5,766 | 42.7% | 7,734 |
| On-line Energy Surveys | 9,000 | 398 | 4.4% | 2,517 | 28.0% | 0 | 0% | 2,517 | 28.0% | 2,120 |
| In-Home Energy Surveys | 4,000 | 425 | 10.6% | 2,121 | 53.0% | 0 | 0% | 2,121 | 53.0% | 1,879 |
| Telephone Energy Surveys | 500 | 55 | 11% | 170 | 34% | 0 | 0% | 170 | 34% | 330 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed | 50,000 | 100% | 50,000 | 100% | 0% | n/a | 50,000 | 100% | 0 |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed | 0% | n/a | 7% | n/a | 0% | n/a | 7% | n/a |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Mailed 50,000 English surveys to customers in HTR areas.

- Updated the survey’s recommendation page to reflect that the 2004 Home Energy Efficiency Rebate Program will no longer accept rebate applications postmarked after August 14, 2004 for High Performance Dual-Paned Windows.

- Completed translation in support of 10,000 Chinese and 10,000 Spanish surveys mailing scheduled for late August or early September 2004.

- Discussed with the Statewide Team members to finalized statewide new Asian energy surveys, Vietnamese for PG&E, SCE and SoCalGas, and Chinese for SDG&E service territories.

- Scheduled 9,000 Vietnamese surveys mailing in late September or early October, and posting the survey on SCE web site in August.

- Continued to promote the appliance recycling program by providing brochures to customers after completion of a survey.

- Started the program manual binder documenting activities and reports in 2004.

On-Line Survey

- Met with on-line marketing vendor to close out 2Q Starbucks campaign.

- Coordinated and planned the 3Q marketing strategy with the new on-line marketing vendor.

- Coordinated the campaign fulfillment by ordering Starbucks card, fulfillment cards and envelopes, and print shop services.

- On July 28, 2004, launched the Starbucks campaign offering $5 Starbucks Cards to customers who completed an On-Line Survey.  The campaign achieved 149 completed surveys in 4 days of promotion.

- Coordinated with Contractor in developing and launching the Chinese interactive on-line survey in late September or early October 2004.

- Started the program manual binder documenting activities and reports in 2004.

In-Home Survey

- Evaluated and recommended award of the 2004-2005 purchase order to the successful bidder.  New contract starts on August 2004 and expires March 2006.

- Completed 179 SCE/SoCalGas joint surveys for both electric and gas customers.

- Completed verification of customers that received the In-Home Survey as reported by the Contractor, for surveys conducted in April and May.

- Provided apartment complex’s customers that participated in the survey with a promotional flashlight keychain.

- Scheduled the distribution of 50,000 solicitation cards to customers in HTR areas for early August 2004.

- Continued to promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Started the program manual binder documenting activities and reports in 2004.

    - Marketing –

See the list in Attachment A.

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys |
| --- | --- |
| 5,766 Mail-In Surveys | $12.30 |
| 2,517 On-Line Surveys | $11.31 |
| 2,121 In-Home Surveys | $81.81 |
| 170 Telephone Surveys | $42.86 |

Note:  Data includes total number of customer surveys from January through July 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Finalized translation efforts with the HEES Statewide Team to standardize the IOUs Vietnamese, Chinese and Spanish cover letters and report texts.

- Continued the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers.

- Changes to Subcontractors or Staffing

Program manager have not changed.  Subcontractor for the on-line marketing vendor changed from XXXXX to XXXXX.

- Additional Items

None