| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | November 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options:  Mail-In, On-Line, and In-Home/Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,379 | $43,872 | 1% | $853,948 | 27% |  |  | $853,948 | 27% | $2,274,431 |
| Admin | $532,446 | $18,380 | 3% | $235,825 | 44% |  |  | $235,825 | 44% | $296,621 |
| Marketing | $538,000 | $455 | 0% | $118,810 | 22% |  |  | $118,810 | 22% | $419,190 |
| DI | $1,929,554 | $25,037 | 1% | $499,314 | 26% |  |  | $499,314 | 26% | $1,430,240 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 1,908 | 14.1% | 13,818 | 102.4% | 0 | 0% | 13,818 | 102.4% | 0 |
| On-Line Energy Surveys | 9,000 | 181 | 2.0% | 10,718 | 119.1% | 0 | 0% | 10,718 | 119.1% | 0 |
| In-Home Energy Surveys | 4,000 | 448 | 11.2% | 4,082 | 102.1% | 0 | 0% | 4,082 | 102.1% | 0 |
| Telephone Energy Surveys | 500 | 74 | 14.8% | 428 | 85.6% | 0 | 0% | 428 | 85.6% | 82 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed |  | 100% |  | 100% |  | n/a |  | 100% |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed |  | 80% |  | 80% |  | n/a |  | 80% |  |

  - Activities/Accomplishments

    - Administrative

Mail-In Survey

- Achieved 1,908 mail-in surveys, bringing year-to-date program achievement to 13,818 surveys that exceeded the survey goal of 13,500.

- Scheduled mailing of 6,000 Vietnamese survey packages in December.  Entire survey packages were approved in November.  Printing of survey packages will be completed by early December.

- Finalized planning for 2005 mailing strategies that include 100% mailing of English survey to hard-to-reach communities, and mailing of Spanish, Chinese and Vietnamese surveys throughout SCE service territories.

- SCE continued its efforts to achieve equity and remove market barriers by enhancing access of energy efficiency programs for non-English speaking customers.  SCE is working side-by-side with Asian Pacific American Community Service Center, a local community-based organization, to promote the program to the Asian communities.  The program achieved 188 completed surveys in Chinese in just eight days.

- Initiated discussion with survey contractor to develop the survey in additional Asian language.  In 2005, the statewide team will offer energy survey to Korean-speaking customers, in addition to Spanish, Chinese and Vietnamese surveys.

On-Line Survey

- Achieved 10,718 completed surveys that exceeded the 9,000 survey goal.

- Launched the Chinese Home On-line Interactive Survey on November 1, 2004.  This involved extensive work to complete preparation and testing, and for being the first California IOU that offers customers access to on-line Chinese interactive energy survey.  With the addition of the Chinese survey, the program has expanded its audience potential to include a larger segment of California’s diverse population.  These customers who in the past have not had the tools necessary to participate in this type of program, will now have the ability to benefit equally.

- Promoted the launch of the Chinese Home On-Line Energy Survey via internal SCE communication, press release, local Chinese newspapers advertorials, SCE web site banner ad, and radio PSAs to encourage Chinese-speaking customers to complete the survey.

- Coordinated translations and printed new English/Chinese fliers to promote the On-Line Survey.

In-Home Survey

- Achieved 4,510 completed surveys that met the survey goal of 4,500.

- Completed 755 SCE/SoCalGas joint surveys for both electric and gas customers in 2004.  Started discussion with SoCalGas on 2005 joint efforts.

- Participated and ride-along with the energy auditor in conducting the in-home survey to an SCE customer that resides in Long Beach.  The purpose is to verify that the survey is being completed and ensure customers are receiving quality and valuable service from survey contractor.

- Finalized planning of the 2005 mailing strategy strategies that include Los Angeles and Orange County beach and other hard-to-reach communities throughout SCE service territories.

- Started discussions to update layout and content of the existing survey instrument for second quarter of 2005.

    - Marketing –

None

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys | Cost Per Surveys effective 08/01/04 |
| --- | --- | --- |
| 13,818 Mail-In Surveys | $12.30 | Same |
| 10,718 On-Line Surveys | $11.31 | Same |
| 4,082 In-Home Surveys | $81.81 | $91.46 |
| 428 Telephone Surveys | $42.86 | $48.26 |

Note:  Data includes total number of customer surveys from January through November 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.  The In-Home and Telephone Surveys costs are changed in August as a result of the competitive bid issued in May.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Started discussion and plan for 2004 program close-out and reconciliation of surveys numbers.

- Started discussion and drafted the preliminary project plan for 2006 Request for Proposal with the statewide team members.  The plan is to prepare the solicitation in first and second quarter and issue RFP by third quarter of 2005.

- Mail-In Survey

  - Coordinated gathering and submission of documentation with the survey contractor to the verification consultant, to assist the evaluation of the 2003 HEES survey program.

  - Continued to promote the appliance recycling program by inserting a brochure with every energy report mailed.

- On-Line Survey

  - Continued to promote the residential energy efficiency services and programs.  Customers are able to click on the links provided in the survey results, and be instantly connected to web sites to obtain more information on other energy efficiency services and programs.

- In-Home Survey

  - Continued the combined efforts with SCG to conduct In-Home Surveys for both electric and gas customers.

  - Continued to target HTR multi-family residents through apartment managers who have previously participated in other statewide energy efficiency program.

  - Continued to provide apartment complex’s customers that participated in the survey with a promotional flashlight keychain.

  - Continued to provide survey contractor with CARE applications to be handed out to lo-income customers that participated in the survey, and promote the appliance recycling program by providing brochures to customers after completion of an In-Home Survey.

- Changes to Subcontractors or Staffing

Subcontractors or staffing have not changed.

- Additional Items

None