| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Home Energy Efficiency Surveys Program – PGC |
| Program Number: | 1238-04 |
| Month: | April 2004 |

- Program Status

Program Description

The Statewide Home Energy Efficiency Survey program (HEES) provides a comprehensive multi-lingual program approach, which is specifically designed to reach a wide range of customers by offering three types of survey options: Mail-In, On-Line, and In-Home/ Telephone.  HEES provides practical information that customers can immediately apply to better understand energy use in their homes and to empower them to make educated decisions related to energy efficiency and equipment upgrades.  This multifaceted approach recognizes that customers have distinct needs that may make one type of delivery channel more appealing than another.  As a result, the HEES program is positioned to reach the largest number of customers possible by providing more options for customer participation, including hard-to-reach customers who in the past have had less access and fewer program alternatives.  All delivery channels help customers understand how their behavior can affect energy costs, how to improve their homes’ energy efficiency and what additional resources and programs are available to help reduce energy use.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Apr-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,128,731 | $46,494 | 1% | $123,566 | 4% |  |  | $123,566 | 4% | $3,005,166 |
| Admin | $532,800 | $32,952 | 6% | $97,508 | 18% |  |  | $97,508 | 18% | $435,292 |
| Marketing | $538,000 | $1,205 | 0% | $1,305 | 0% |  |  | $1,305 | 0% | $536,695 |
| DI | $1,929,552 | $12,337 | 1% | $24,753 | 1% |  |  | $24,753 | 1% | $1,904,799 |
| EM&V | $128,379 |  |  |  |  |  |  |  |  | $128,379 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Apr-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mail-In Energy Surveys | 13,500 | 0 | 0% | 0 | 0% | 462 | 3.4% | 462 | 3.4% | 13,038 |
| On-line Energy Surveys | 9,000 | 0 | 0% | 0 | 0% | 763 | 8.5% | 763 | 8.5% | 8,237 |
| In-Home Energy Surveys | 4,000 | 131 | 3.3% | 286 | 7.2% | 529 | 13.2% | 815 | 20.4% | 3,185 |
| Telephone Energy Surveys | 500 | 9 | 1.8% | 20 | 4% | 22 | 4.4% | 42 | 8.4% | 458 |
| Home Energy Efficiency Survey - Mail-In Energy Survey. Customers receive a survey either through direct mail, or by printing a hardcopy via IOUs websites. | 50% HTR of total surveys mailed | 0% | n/a | 0% | n/a | 0% | n/a | 0% | n/a |  |
| Home Energy Efficiency Survey - In-Home and Telephone Energy Survey. Trained auditor inspects customer's home or interviews customer over the phone, and provide immediate answers to basic questions, as well as specific recommendations on how to save energy and manage cost based on their home and lifestyles. | 50% HTR of total surveys completed | 7% | n/a | 7% | n/a | 0% | n/a | 7% | n/a |  |

  - Activities/Accomplishments

    - Administrative – April 2004

- Met with the HEES statewide team on April 21, 2004 to discuss the 2004-2005 program implementation plan.

- Reviewed Contractor’s pricing proposal for the development of the new Asian energy surveys with the HEES Statewide Team.

- Developed and finalize the in-home survey process to target Catalina’s customers.

- Coordinated with Southern California Gas Company (SoCalGas) to combine efforts to conduct in-home energy surveys for both electric and gas customers.

- Coordinated with Sempra Utilities to provide gas training to in-home survey energy auditors.  Training was conducted on April 27, 2004 by representatives from SDG&E and SoCalGas at SCE’s Rancho Cucamonga facility.

- Mailed 25,000 in-home survey solicitation cards on April 29, 2004.

- Finalized 2004 mail-in survey mailing strategy.  The first mailing of 50,000 English mail-in survey solicitation packages is targeted for mid-May 2004.

- Prepared a draft Statement of Work to solicit proposals from vendors to implement the in-home survey component starting August 1, 2004.

- Extended mail-in and on-line surveys contract through 2005 program year.  The HEES statewide team agreed to continue with the existing contractor for the 2004-2005 mail-in survey service for all IOUs.

    - Marketing –

In addition to the list in Attachment A:

- Plan the second quarter on-line survey promotion with the on-line survey team.

    - Direct Implementation –

      - Surveys and Partnerships -

| Number of Customer Surveys | Cost Per Surveys |
| --- | --- |
| 462 Mail-In Surveys | $13.46 |
| 763 On-Line Surveys | $10.40 |
| 815 In-Home Surveys | $81.81 |
| 42 Telephone Surveys | $42.86 |

Note:  Data includes total number of customer surveys from January through April 2004, cumulative and committed surveys.  Cost per surveys includes all processing fees, on-line annual customer service and hosting fees, customer billing data update fees, and expenses including mileage, lodging and meals.

| Types of Measures Recommended | Numbers of Measures Recommended |
| --- | --- |
| Lighting | n/a |
| HVAC | n/a |
| Appliances | n/a |
| Pool Equipment | n/a |
| Insulation | n/a |

Note:  Exact numbers of measures recommended not available.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None.

- Coordination Activities

- SCE coordinated efforts with Southern California Gas Company to conduct in-home energy surveys for both electric and gas customers. Sempra Utilities provided gas training to in-home survey energy auditors on gas related topics, so the auditors will be better prepared to survey customers homes and response to customers’ inquiries.

- The HEES statewide team met and developed a plan to use existing Chinese and Vietnamese mail-in and on-line surveys for use by the other IOUs.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None