| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Nonresidential Standard Performance Contract Program - PGC |
| Program Number: | 1240-04 |
| Month: | July 2004 |

- Program Status

Program Description

The statewide Nonresidential Standard Performance Contract (SPC) program offered by Pacific Gas and Electric Company, Southern California Edison, and San Diego Gas and Electric Company is a pay-for-performance program that offers cash incentives for custom-designed, cost effective energy saving retrofits of existing business facilities.  Designed primarily for large and medium businesses, small and very small businesses can also participate if the energy efficiency measures do not qualify for the statewide Express Efficiency program. Depending on the energy-efficiency measure installed, an itemized or calculated approach is used to estimate the energy savings and incentive. An itemized measure will be based on a pre-determined rate and no kWh savings calculation by the applicant is necessary. For all other measures not included as an itemized measure, the estimated payment will be determined by the quantity of kilowatt-hours (kWh) or therms of gas saved.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $18,626,000 | $501,537 | 3% | $2,181,767 | 12% | $5,912,128 | 32% | $8,093,895 | 43% | $16,444,234 |
| Admin | $2,418,400 | $95,789 | 4% | $641,555 | 27% |  |  | $641,555 | 27% | $1,776,845 |
| Marketing | $1,579,000 | $59,399 | 4% | $407,623 | 26% |  |  | $407,623 | 26% | $1,171,377 |
| DI | $14,002,600 | $346,349 | 2% | $1,132,588 | 8% | $5,912,128 | 42% | $7,044,716 | 50% | $12,870,012 |
| EM&V | $626,000 |  |  |  |  |  |  |  |  | $626,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jul-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 15,291 | 371 | 2% | 1,078 | 7% | 8,443 | 55% | 9,521 | 62% | 14,213 |
| Annual kWh | 102,917,493 | 2,468,790 | 2% | 6,158,364 | 6% | 53,862,967 | 52% | 60,021,331 | 58% | 96,759,130 |
| Lifecyc kWh | 1,532,954,893 | 37,924,546 | 2% | 87,909,979 | 6% | 770,285,455 | 50% | 858,195,434 | 56% | 1,445,044,914 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

The difference in cumulative kWh savings is due to the annual adjustment of the SPC early retirement projects. For this feature, the SPC incentive is calculated for multiple years to account for the remaining years of useful life. If an applicant replaces their existing AC unit, chiller or motor before the end of its useful life, the SPC program pays for the savings achieved over those additional years.  In the workbook, since the reported savings are annual numbers, the kWh savings are adjusted to only reflect one year of savings rather than the multiple years which the program pays.

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- During the month of July, 7 projects were approved and contracted, and 13 installation reports were approved for payment.

- Updates were made to the program website including updated software links, current funding and commitments status, and additional program information.

- Program staff responded to 640 requests for program CDs.

- Weekly team meetings were held with internal staff to review current projects, and discuss new submittals.

- Weekly conference calls were held with SCE, PG&E, and SDG&E SPC program managers to discuss similar projects, resolve policy issues, and ensure program continuity statewide.

- Weekly phone conferences with project reviewers were held to discuss the status of submitted applications, resolve specific project issues and review other items as necessary to ensure timely completion of reviews.

- To track statewide incentive payments and commitments, a web-based database is under development to track utility level caps of projects funded through the statewide SPC programs. The system will be developed using Microsoft Access 2000 and Active Server Page (ASP.NET) software to allow web-based access to current program funding and commitment levels. The system will flag instances of potential cap overruns upon data entry of new project applications.

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Installed in July |
| --- | --- |
| Commercial Customized – Space Conditioning | 159,107 kWh |
| Com. Lighting Controls | 582,995 kWh |
| Com. Customized – Process | 534,742 kWh |
| Com. Customized – Refrigeration | 924,666 kWh |
| Com. Customized – Pumping | 195,551 kWh |
| LED Exit Signs | 3 units |
| T-8 or T-5 Lamp and Electronic ballast – 4 foot | 486 units |
| T-8 or T-5 Lamp and Electronic, 4-foot lamp removed | 157 units |
| T-8 or T-5 Lamp and Electronic, 8-foot lamp | 36 units |
| Interior HO T-5 4 lamp fixture retrofits | 782 units |

      - Calculated and Actual Payment Reconciliation -

Since actual incentives payable to customers are capped at 50% of each measure cost, certain measures only receive partial incentive payments. As a result, the financial incentives to customers in Tab 1A - Expenditures Worksheet may differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

SPC staff coordinated with Express Efficiency staff to transfer applications between the two programs as needed. Customers often submit applications in SPC when they are eligible for Express Efficiency, and vice versa.  Procedures have been established to assist customer with filling out forms for the appropriate rebate program they qualify for, and make for seamless coordination between the two programs.

Attended a meeting with SCE account executives to review the SPC process and provide general information on the policies and guidelines of the program. Additionally, account executives were provided with program materials and other resources to assist with the efficient processing of applications.

SPC program staff coordinated with program managers of SCEs local programs; Ventura Regional Energy Alliance, South Bay Partnership, and UC/CSU Partnership to provide SPC program materials, promotional items, and information for on-going disbursement.

- Changes to Subcontractors or Staffing

XXXXX was added as a subcontractor to review projects, conduct site inspections and verify applications.

- Additional Items

None