| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Nonresidential Standard Performance Contract Program - PGC |
| Program Number: | 1240-04 |
| Month: | June 2004 |

- Program Status

Program Description

The statewide Nonresidential Standard Performance Contract (SPC) program offered by Pacific Gas and Electric Company, Southern California Edison, and San Diego Gas and Electric Company is a pay-for-performance program that offers cash incentives for custom-designed, cost effective energy saving retrofits of existing business facilities.  Designed primarily for large and medium businesses, small and very small businesses can also participate if the energy efficiency measures do not qualify for the statewide Express Efficiency program. Depending on the energy-efficiency measure installed, an itemized or calculated approach is used to estimate the energy savings and incentive. An itemized measure will be based on a pre-determined rate and no kWh savings calculation by the applicant is necessary. For all other measures not included as an itemized measure, the estimated payment will be determined by the quantity of kilowatt-hours (kWh) or therms of gas saved.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $18,626,000 | $372,430 | 2% | $1,680,229 | 9% | $6,857,675 | 37% | $8,537,904 | 46% | $16,945,771 |
| Admin | $2,418,400 | $62,561 | 3% | $545,767 | 23% |  |  | $545,767 | 23% | $1,872,633 |
| Marketing | $1,579,000 | $72,713 | 5% | $348,224 | 22% |  |  | $348,224 | 22% | $1,230,776 |
| DI | $14,002,600 | $237,156 | 2% | $786,239 | 6% | $6,857,675 | 49% | $7,643,914 | 55% | $13,216,361 |
| EM&V | $626,000 |  |  |  |  |  |  |  |  | $626,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 15,291 | 261 | 2% | 708 | 5% | 9,850 | 64% | 10,557 | 69% | 14,584 |
| Annual kWh | 102,917,493 | 1,358,636 | 1% | 3,689,573 | 4% | 62,016,927 | 60% | 65,706,501 | 64% | 99,227,920 |
| Lifecyc kWh | 1,532,954,893 | 18,979,239 | 1% | 49,985,432 | 3% | 875,446,755 | 57% | 925,432,187 | 60% | 1,482,969,460 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

This program does not have performance goals.

  - Activities/Accomplishments

    - Administrative -

- During the month of June, 72 new applications were received and sent for review, and 59 projects were approved and contracted.

- Updates were made to the program website including updated software links, current funding and commitments status, and additional program information.

- Program staff responded to 640 requests for program CDs.

- Weekly team meetings were held with internal staff to review current projects, and discuss new submittals.

- Weekly conference calls were held with SCE, PG&E, and SDG&E SPC program managers to discuss similar projects, resolve policy issues, and ensure program continuity statewide.

- Weekly phone conferences with project reviewers were held to discuss the status of submitted applications, resolve specific project issues and review other items as necessary to ensure timely completion of reviews.

    - Marketing -

See Attachment A for list of marketing materials.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Measure | Installed in June |
| --- | --- |
| Commercial Early Retirement Chillers | 287,532 kWh |
| Com. Indoor Lighting Sys. Repl. | 575,004 kWh |
| Com. Lighting Controls | 3,679 kWh |
| Ind. Indoor Lighting Sys. Repl. | (575,004) kWh |
| Com. Customized – Process | 113,756 kWh |
| Ind. Customized - Process | 230,697 kWh |
| Variable Frequency Drives – HVAC fans | 80 units |
| Screw-in Compact Fluorescent Lamp, 14-26 watts | 156 units |
| LED Exit Signs | 20 units |
| T-8 or T-5 Lamp and Electronic ballast - 2 foot | 9 units |
| T-8 or T-5 Lamp and Electronic, 3-foot | 2 units |
| T-8 or T-5 Lamp and Electronic ballast – 4 foot | 17,857 units |
| T-8 or T-5 Lamp and Electronic, 4-foot lamp removed | 499 units |
| T-8 or T-5 Lamp and Electronic, 8-foot lamp | 36 units |
| Interior Pulse Start HID 0-35 watts incandescent basecase | 36 units |
| Occupancy Sensor wall mounted | 133 units |
| Occupancy Sensor ceiling mounted | 124 units |
| Timeclock | 71 units |

      - Calculated and Actual Payment Reconciliation -

Since actual incentives payable to customers are capped at 50% of each measure cost, certain measures only receive partial incentive payments. As a result, the financial incentives to customers in Tab 1A - Expenditures Worksheet may differ from the calculated financial incentives in Tab 2A - Recorded EE Activities Worksheet.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

SPC staff coordinated with Express Efficiency staff to transfer applications between the two programs as needed. Customers often submit applications in SPC when they are eligible for Express Efficiency, and vice versa.  Procedures have been established to assist customer with filling out forms for the appropriate rebate program they qualify for, and make for seamless coordination between the two programs.

SPC program staff coordinated with program managers of SCEs local programs; Ventura Regional Energy Alliance, South Bay Partnership, and UC/CSU Partnership to provide SPC program materials, promotional items, and information for on-going disbursement.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None