| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Express Efficiency - PGC |
| Program Number: | 1243-04 |
| Month: | September 2005 |

- Program Status

Program Description

Express Efficiency is the only prescriptive rebate program that provides equitable financial incentives to all investor owned utility (IOU) small-and medium-sized nonresidential customers on a seamless statewide basis. By having a design that actually prescribes what measures may be installed, it is a very straightforward and customer-friendly program that ensures that the smallest customers have a hassle-free, reliable means to decrease their utility bill and make their business more energy efficient. The program will continue its focus on customers who are defined as hard-to-reach (HTR), who traditionally are less likely to install energy efficient technologies due to geographic, ethnic and other market barriers.  To achieve this goal, SCE will draw upon the all the synergies that exist between its programs, such as the Energy Audit program and with other, community based organizations. Doing so will increase the economies of scale and create a greater positive impact for all present and future stakeholders.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,501,000 | $346,859 | 3% | $9,054,877 | 72% | $2,723,270 | 22% | $11,778,147 | 94% | $3,446,123 |
| Admin | $2,840,200 | $96,443 | 3% | $2,082,075 | 73% |  |  | $2,082,075 | 73% | $758,125 |
| Marketing | $1,303,200 | $63,188 | 5% | $775,582 | 60% |  |  | $775,582 | 60% | $527,618 |
| DI | $7,856,600 | $187,227 | 2% | $6,197,220 | 79% | $2,723,270 | 35% | $8,920,491 | 114% | $1,659,379 |
| EM&V | $501,000 |  |  |  |  |  |  |  |  | $501,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 46,407 | 1,028 | 2% | 24,874 | 54% | 11,630 | 25% | 36,504 | 79% | 21,533 |
| Annual kWh | 210,382,163 | 5,058,663 | 2% | 124,332,446 | 59% | 70,228,190 | 33% | 194,560,637 | 92% | 86,049,717 |
| Lifecyc kWh | 2,131,457,383 | 60,075,071 | 3% | 1,427,104,465 | 67% | 799,966,590 | 38% | 2,227,071,055 | 104% | 704,352,918 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard-to-reach customer participation as a percentage of total rebate applications paid | 40% |  | n/a | 39% | n/a |  | n/a | 39% | n/a |  |

  - Activities/Accomplishments

    - Administrative -

- Held monthly telephone conference with the statewide team to discuss program implementation status, performance, delivery strategy, and issues.

    - Marketing –

- Hosted a meeting of the Electric Foodservice Council on 9/22 to discuss the Express Efficiency program as it relates to the foodservice and hospitality industry.

- Co-hosted a statewide IOU exhibit at the National Association of Foodservice Equipment Manufacturer’s Show (NAFEM) held 9/23-25 at the Anaheim Convention Center.  The theme of this show was “Hot Rebates, Cool Savings”-- California Utilities Partnering for Energy Efficiency.  This event resulted in an unprecedented level of cooperation among the Express Efficiency and SPC statewide teams.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not Applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| # Customer Sites (Paid in June) | Average Cost Per Site |
| --- | --- |
| 121 | $1,326 |

| Types of Measures | Measures Installed in September |
| --- | --- |
| Lighting | 28,510 |
| HVAC* | 1,743 |
| Refrigeration** | 141 |
| Food Service | 0 |
| Agricultural | 0 |

* Includes window film, measured in square feet.

** Includes gaskets and strip curtains, measured in linear feet.

      - Calculated and Actual Payment Reconciliation -

Adjustments:

- Cost transfer for $29,997.86 for three payments mistakenly charged to incentive budget in September.

- Two customer payments were returned to SCE in August for $1,297.50 and $4,281.00 and were reissued in September.

- Two checks were received in September for $3,942.00 and $86.40 for repayment of overpayments made to the customer.

- EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

There were no activities beyond what may be described in the monthly reporting tables.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None