| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Nonresidential Energy Audits Program – PGC |
| Program Number: | 1248-04 |
| Month: | September 2005 |

- Program Status

Program Description

The Statewide Nonresidential Energy Audits program offered by Pacific Gas and Electric Company, Southern California Edison, San Diego Gas and Electric and Southern California Gas Company provides a full range of professional technical assistance to educate customers on how to implement no cost, low cost measures and cost-effective energy-efficiency retrofits in their buildings to increase long term annual energy savings and capture electric peak demand reduction while lower their energy bills.  The energy audit recommendations are based on the customer’s recent billing history and/or customer-specific information regarding equipment and building characteristics.  This program also addresses the California Public Utilities Commission’s goals regarding equitable program access to the hard-to-reach business sector.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,094,000 | $153,396 | 4% | $3,050,833 | 75% |  |  | $3,050,833 | 75% | $1,043,167 |
| Admin | $439,780 | $22,390 | 5% | $354,889 | 81% |  |  | $354,889 | 81% | $84,891 |
| Marketing | $221,520 | $4,572 | 2% | $102,645 | 46% |  |  | $102,645 | 46% | $118,875 |
| DI | $3,138,700 | $126,435 | 4% | $2,593,298 | 83% |  |  | $2,593,298 | 83% | $545,402 |
| EM&V | $294,000 |  |  |  |  |  |  |  |  | $294,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goal | Goal | Sep-05 | % of Goal | Cumulative | % of Goals | Committed | % of Goal | Cumulative & Committed | % of Goal | Goal Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy audits (including 8,220 HTR) | 14,200 | 509 | 3.6% | 15,187 | 107% | 0 | 0% | 15,187 | 107% | n/a |

  - Activities/Accomplishments

    - Administrative –

- Managed budget and audit activity tracking for the Nonresidential Energy Audit Program.

- Continuation of contractor bidding packages, RFP/RFI preparation.

- Coordination meeting with marketing group and the onsite audits supervisor.

    - Marketing –

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| Audit types Total ytd audits | Cost Per Site |
| --- | --- |
| Online 463 | $132 |
| Mail-in 117 | $87 |
| CD-ROM 1422 | $51 |
| Over-the phone 1,560 | $75 |
| Onsite 11,625 (MCD & Business Solutions) | $180 |
| Total Energy Audits 15,187 | $199 |

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Coordinated audit requests with Business Solutions and Major Account Divisions.

- Coordination of energy audit requests from other SCE departments.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None