| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Nonresidential Energy Audits Program – PGC |
| Program Number: | 1248-04 |
| Month: | May 2004 |

- Program Status

Program Description

The Statewide Nonresidential Energy Audits program offered by Pacific Gas and Electric Company, Southern California Edison, San Diego Gas and Electric and Southern California Gas Company provides a full range of professional technical assistance to educate customers on how to implement no cost, low cost measures and cost-effective energy-efficiency retrofits in their buildings to increase long term annual energy savings and capture electric peak demand reduction while lower their energy bills.  The energy audit recommendations are based on the customer’s recent billing history and/or customer-specific information regarding equipment and building characteristics.  This program also addresses the California Public Utilities Commission’s goals regarding equitable program access to the hard-to-reach business sector.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | May-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,067,200 | $192,842 | 5% | $733,002 | 18% |  |  | $733,002 | 18% | $3,334,198 |
| Admin | $412,980 | $28,727 | 7% | $96,416 | 23% |  |  | $96,416 | 23% | $316,565 |
| Marketing | $221,520 | $4,298 | 2% | $9,697 | 4% |  |  | $9,697 | 4% | $211,823 |
| DI | $3,138,700 | $159,816 | 5% | $626,889 | 20% |  |  | $626,889 | 20% | $2,511,811 |
| EM&V | $294,000 |  |  |  |  |  |  |  |  | $294,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goal | Goal | May-04 | % of Goal | Cumulative | % of Goals | Committed | % of Goal | Cumulative & Committed | % of Goal | Goal Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy audits (including 8,220 HTR) | 14,200 | 721 | 5.1% | 3,548 | 25% | 0 | 0% | 3,548 | 25% | 10,652 |

  - Activities/Accomplishments

    - Administrative –

- Managed budget and audit activity tracking for the Nonresidential Energy Audit Program.

- Held meeting with internal marketing group to plan mail-in audit promotion, material re-prints, new print materials and pop-up display banners.

- Held frequent internal discussions regarding coordination of energy audit activity.

- Continued to conduct regular meetings with new internal field audit tracking analyst to discuss on-site audit activity tracking and reporting.

    - Marketing –

See Attachment A for list of marketing materials.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| Audit types Total ytd audits | Cost Per Site |
| --- | --- |
| Online 72 | $470 |
| Mail-in 17 | $11 |
| CD-ROM 96 | $188 |
| Over-the phone 789 | $54 |
| Onsite 2,574 | $455 |
| Total Energy Audits 3,548 | $206 |

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Coordinated audit requests with Express Efficiency and SPC incentive programs

- Coordinated with the statewide partnerships to provide 300 printed NRA brochures for Community based organizations.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None