| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Nonresidential Energy Audits Program – PGC |
| Program Number: | 1248-04 |
| Month: | March 2004 |

- Program Status

Program Description

The Statewide Nonresidential Energy Audits program offered by Pacific Gas and Electric Company, Southern California Edison, San Diego Gas and Electric and Southern California Gas Company provides a full range of professional technical assistance to educate customers on how to implement no cost, low cost measures and cost-effective energy-efficiency retrofits in their buildings to increase long term annual energy savings and capture electric peak demand reduction while lower their energy bills.  The energy audit recommendations are based on the customer’s recent billing history and/or customer-specific information regarding equipment and building characteristics.  This program also addresses the California Public Utilities Commission’s goals regarding equitable program access to the hard-to-reach business sector.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,067,200 | $331,624 | 8% | $331,624 | 8% |  |  | $331,624 | 8% | $3,735,576 |
| Admin | $412,980 | $45,636 | 11% | $45,636 | 11% |  |  | $45,636 | 11% | $367,344 |
| Marketing | $221,520 | $2,304 | 1% | $2,304 | 1% |  |  | $2,304 | 1% | $219,216 |
| DI | $3,138,700 | $283,684 | 9% | $283,684 | 9% |  |  | $283,684 | 9% | $2,855,016 |
| EM&V | $294,000 |  |  |  |  |  |  |  |  | $294,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy audits (including 8200 HTR) | 14200 | 705 | 4.9% | 1615 | 11.4% | 0 | 0% | 1615 | 11.4% | 12585 |

  - Activities/Accomplishments

    - Administrative -

- Held further internal discussions to finalize the program administrative and direct implementation budget.

- Submitted a revised program implementation plan (PIP).

- Implemented program manager’s tracking form to capture audit activity and current budget expenditures for the Nonresidential Energy Audit program.

- Brought the new audit tracking system current for the year.

- Held discussions with several of the statewide IOUs to coordinate PIP.

- Held internal discussions regarding coordination of energy audit activity.

- Met with program supervisor to discuss current status of the program including energy audits year to date.

    - Marketing -

- Held internal discussions with the SCE marketing group to set program marketing activity

- Provided updates program description for marketing brochure

- Met with program supervisor to discuss current marketing status

- Held discussions with online contractor to coordinate online marketing changes

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

| Audit types Total ytd audits | Cost Per Site |
| --- | --- |
| Online 42 | $630 |
| Mail-in 17 | $20 |
| CD-ROM 48 | $284 |
| Over-the phone 299 | $74 |
| Onsite 1,209 | $217 |
| Total Energy Audits 1,615 | $205 |

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Held discussions with SCE Express Efficiency group to assess customer participation in the rebate incentive program.

- Coordinated with Express Efficeincy, SPC incentive program in setting marketing signs at Expo type events.

- Coordinated with the statewide IOUs with PIP refiling

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None