| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Building Operator Certification Program – PGC |
| Program Number: | 1252-04 |
| Month: | March 2004 |

- Program Status

Program Description

The Building Operator Certification (BOC) and Training Program offered by Pacific Gas and Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E) and Southern California Gas Company (SoCalGas) is a continuation of the uniform statewide building operator training and certification program that began in 2002.  Operators of medium and large commercial buildings (including governmental and institutional buildings and complexes) are the primary target group for this program.  The program content trains operators of these buildings to identify and implement long term annual energy savings and electric peak demand reduction opportunities as an integral part of their operations and maintenance activities.  As a certification program, BOC seeks to establish a recognized professional credential for building operators.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Mar-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,048,000 | $6,190 | 1% | $15,886 | 2% |  |  | $15,886 | 2% | $1,032,114 |
| Admin | $155,600 | $6,190 | 4% | $15,462 | 10% |  |  | $15,462 | 10% | $140,138 |
| Marketing | $60,000 |  |  | $424 | 1% |  |  | $424 | 1% | $59,576 |
| DI | $784,400 |  |  |  |  |  |  |  |  | $784,400 |
| EM&V | $48,000 |  |  |  |  |  |  |  |  | $48,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Mar-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Host 5 Level I BOC full-course sessions, with an average student enrollment of 20 per course | 5 courses - 100 students | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5 courses - 100 students |
| Host 1 Level II BOC full-course session, with a student enrollment of at least 15 | 1 course - 15 students | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 course - 15 students |

  - Activities/Accomplishments

    - Administrative -

- Implemented SCE’S www.sce.com/boc web site;

- Commenced development of SCE’s BOC policies and desk procedures manual; and

- Worked to develop, and provided coordination for, a 20-40 student on-site group training session at the Naval Air Weapons Station at China Lake, California.

    - Marketing -

- Delivered 1,000 customer testimonial brochures to internal SCE outreach organizations; and

- Finalized the student orientation kit, class registration forms, and general program information booklet.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None