| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Building Operator Certification Program – PGC |
| Program Number: | 1252-04 |
| Month: | July 2005 |

- Program Status

Program Description

The Building Operator Certification (BOC) and Training Program offered by Pacific Gas and Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E) and Southern California Gas Company (SoCalGas) is a continuation of the uniform statewide building operator training and certification program that began in 2002.  Operators of medium and large commercial buildings (including governmental and institutional buildings and complexes) are the primary target group for this program.  The program content trains operators of these buildings to identify and implement long term annual energy savings and electric peak demand reduction opportunities as an integral part of their operations and maintenance activities.  As a certification program, BOC seeks to establish a recognized professional credential for building operators.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $1,048,000 | $63,479 | 6% | $436,169 | 42% |  |  | $436,169 | 42% | $611,831 |
| Admin | $155,600 | $2,760 | 2% | $72,794 | 47% |  |  | $72,794 | 47% | $82,806 |
| Marketing | $60,000 | $2,120 | 4% | $5,160 | 9% |  |  | $5,160 | 9% | $54,840 |
| DI | $784,400 | $58,599 | 7% | $358,214 | 46% |  |  | $358,214 | 46% | $426,186 |
| EM&V | $48,000 |  |  |  |  |  |  |  |  | $48,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Jul-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Host 5 Level- I BOC full-course sessions, with an average student enrollment of 20 per course | 10 courses - 200 students | 0 | 0% 0% | 9 courses – 203 students | 90% 101% | 0 | 0% | 9 courses – 203 students | 90% 101% | 1 course – 0 students |
| Host 1 Level- II BOC full-course session, with a student enrollment of at least 15 | 2 courses – 30 students | 0 | 0% 0% | 2 courses - 34 students | 100% 113% | 0 | 0% | 2 courses – 34 students | 100% 113% | 0 |

  - Activities/Accomplishments

    - Administrative –

- Student Performance Goal for 2004-2005: 237 students enrolled in Level 1 classes and Level 2 classes

- Year to date results for all Student Performance Goal for 2004-2005: 203 students enrolled and attended in Level 1, or 101%, and 34 students enrolled in Level 2 classes, or 113%

- Class Performance Goal for 2004-2005: 10 Level - I; 2 Level - II

- Classes offered to date: 9 Level-I courses and 2 Level-II courses

    - Marketing –

- Drafted new BOC program marketing brochure.

- A BOC registration drive for Level 1 class course for September

- Planning exhibit for next month’s Energy 2005 conference in Long Beach, CA.

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not applicable

      - Calculated and Actual Payment Reconciliation -

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

SCE coordinated with the other IOUs regarding planning for the 2006 - 2008 program cycle by holding discussions and submitting drafts of proposed plan.

- Changes to Subcontractors or Staffing

Program manager and subcontractors have not changed.

- Additional Items

None