| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Emerging Technologies Program - PGC |
| Program Number: | 1255-04 |
| Month: | November 2004 |

- Program Status

Program Description

The Statewide Emerging Technologies (ET) program is an information-only program that seeks to accelerate the introduction of innovative energy efficient technologies, applications, and analytical tools that are not widely adopted in California.  There are a daunting amount of market barriers a new energy efficient product must overcome to gain acceptance.  During initial marketing efforts, energy efficient products accepted by “innovators” may fail to gain wider acceptance with more risk adverse customers.  The intent of the ET program is to help accelerate a product’s market acceptance through a variety of approaches, but mainly by reducing the performance uncertainties associated with new products and applications.   The program targets all market segments.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,679,000 | $28,035 | 1% | $401,848 | 11% | $497,700 | 14% | $899,548 | 24% | $3,277,152 |
| Admin | $981,000 | $16,781 | 2% | $229,674 | 23% |  |  | $229,674 | 23% | $751,326 |
| Marketing | $20,000 | $2,312 | 12% | $2,425 | 12% |  |  | $2,425 | 12% | $17,575 |
| DI | $2,599,000 | $8,943 | 0% | $169,749 | 7% | $497,700 | 19% | $667,449 | 26% | $2,429,251 |
| EM&V | $79,000 |  |  |  |  |  |  |  |  | $79,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings goals.

    - Performance Goals

| Performance Goals | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Emerging Technologies Applications Assessments initiated in PY2004 | 10 | 0 | 0% | 0 | 0% | 8 | 80% | 8 | 80% | 2 |
| ETCC ET Database PY2004 update | 1 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 |
| PY2004 ETCC meetings | 4 | 0 | 0% | 3 | 75% | 0 | 0% | 3 | 75% | 1 |

  - Activities/Accomplishments

    - Administrative -

None

    - Marketing -

None

    - Direct Implementation -

      - Audits, Site Surveys and Partnerships -

Emerging Technologies Coordinating Council

The Emerging Technologies Coordinating Council (ETCC) did not meet during the month.  The ETCC has met three times this calendar year:  January 15, April 23, and September 13.

2004 Emerging Technology Application Assessments

The 2004 program has committed and initiated a total of eight assessment projects this year.  During the month of November, no new assessment projects were committed.

The following eight assessment projects were committed and initiated earlier this year:

- Optical Demand Defrost.  Project staff worked on the detailed work plans for this assessment during the month.  This assessment project will evaluate the use of optical sensors to provide demand defrost control and determine their energy saving potential.

- Wireless Power Meters & Sensors.  During the month, project staff discussed with the contractors their detailed project work plans and development activities.

- Light Emitting Diode (LED) Outdoor Lights.  During the month, two exterior, wall mounted LED light fixtures were installed at the Southern California Lighting Test Laboratory in Irwindale, and preliminary lighting measurements were performed.

- LED Task Lights.  During the month, project staff worked on the detailed plans for this assessment and investigated available products.

- Residential Economizer Cycle Retrofits.  The performance end-use monitoring and data collection at two sites continued during the past month.

- Advanced Heuristic Thermostatic Control System for Hotels. The end-use performance monitoring continued at the site.  Project staff’s preliminary analysis of the data collected so far indicates that room occupant behavior, i.e., users allowed to reset the thermostat setpoint, may impact the energy savings.

- Occupancy Sensor Nightlight Wall Switches for Hotel Guest Room Bathrooms.  Project staff continued to work with the data collection and end use monitoring at two hotel sites as well as with the verification of hotel room occupancy rates using monitored data.

- California Kitchen Down-Lights.  Volunteers have installed the PIER developed California Kitchen Lighting System into several Habitat for Humanity homes as part of this project.  The end-use performance monitoring phase of the project will start when the homes are occupied next month.

In addition, program staff continues to consider several possible technology application assessment projects for 2004 and 2005.  Assessment projects initiated in prior program years continue as summarized in the following sub-sections.

2003 Statewide Emerging Technology Application Assessments

The program staff was engaged in the following ongoing projects initiated in 2003:

- Rapid Start “Super” T-8 Fluorescent Lamp/Ballast.  Project staff worked on the final report and project fact sheet during the month.

- Instant Start “Super” T-8 Lamp/Ballast.  Project staff worked on the final report and project fact sheet during the month.

- Stairwell Lighting Bi-Level Switching.  The installation of lighting fixtures and controls proceeded at the retrofit sites, and monitoring equipment was acquired.

- Network Management of Computer Power Option Settings.  Project staff completed the participant recruitment for a test throughout four different SCE departments.  A “Welcome” note was sent to all participants along with a baseline survey of screensaver and personal knowledge of power option settings.

- Electrochromic Glazing.  Project staff continued to seek for a suitable location within SCE’s facilities where to perform this assessment project.

- Displacement Ventilation. The engineering contractor completed work on a final design recommendation during the month.

- Advanced Classroom Lighting System.  During the month, program staff worked on a draft fact sheet discussing the PIER-developed advanced lighting system in the CTAC Daylighting Center classroom.

- Anti Corrosion Coatings for Condenser Coils.  The end-use performance monitoring of the packaged air-conditioning equipment continued this month.

- Voltage Reducer System for Dimming Control.  Based on the review of test data, project staff concluded that additional performance tests are needed.  There was no significant progress during the month for this assessment project.

2003 Local Demonstration and Information Transfer ET Application Assessments

The program staff was engaged in the following ongoing projects initiated in 2003:

- Professional Wet Cleaning.  The assessment project contractor, Occidental College, completed the draft final report.  The draft report is under review.

- Cold Storage Refrigeration Control.  Performance tests of the new control system and sensors were underway at the site.

- Salt Reduction of Waste Water Precipitation of Salts for Fluid Bed/Lime Process.  Program staff received the consultant’s final report during the month and the report is undergoing final review and approval.

- Petroleum Dry Cleaning.  On site testing underway and additional test sites were sought during the month.

- Silicone Dry Cleaning.  On site testing underway and additional test sites were sought during the month.

- Carbon Dioxide Dry Cleaning.  On site testing underway and additional test sites were sought during the month.

- Advanced Control for Plastic Granulators.  During the month, project staff contacted and negotiated with the manufacturer of an electronic controller suitable for plastics granulators to arrange for an evaluation.

2002 Statewide Emerging Technologies Assessments

The program staff worked on the following projects that were initiated in 2002:

- Integrated Design for New Children’s Museum, and Underfloor Air Distribution.  During the month, the customer continued to seek for a new building site for the museum.

- T-5 High Output Lighting System for High Bay Workshop and Variable Geometry Reflector System for HID Lighting.  Project staff worked on the final report and fact sheet during the month.

- Integrated Efficiency Improvements for Small Grocery Stores.  Project staff incorporated review comments into the draft assessment report and created a draft project fact sheet.

- Integration of Energy Efficiency Improvements in a Small Sit-Down Restaurant.  End-use monitoring and data collection are underway for the new refrigeration system and new two-door freezer unit.

- Integrated Hood Exhaust Backwall Make-Up Air System for Commercial Kitchen Hood Exhaust. The project manager continued to work with the restaurant chain to select a suitable site.

- Perforated Supply Plenum Make-Up Air System for Commercial Kitchen Hood Exhaust.  Performance end-use monitoring and data collection continued at the site.  Project staff conducted a preliminary analysis of the collected data to verify data integrity.

- Variable Frequency Drive for Commercial Kitchen Hood Exhaust and Make-Up Air System.  Performance end-use monitoring and data collection continued at the site.  Project staff performed a preliminary data analysis to verify data integrity.

2002 Local Demonstration & Information Transfer ET Application Assessments

The program staff working on the following projects that were initiated in 2002:

- Integrated Design for Non-Residential Retrofit Buildings. Contractors completed their verification and pre-functional test work and were documenting their findings in the commissioning report.  In addition, program staff organized and sponsored a seminar on Integrated Design for school district personnel and designers during the month.

- Low-E Pigment for Stucco and Paints for Residential and/or Small Commercial Buildings.  Program staff continued to work the draft report.

- Spray-on Radiant Barrier for Existing Residential and/or Small Commercial Buildings.  Program staff continued to revise the draft final report.

2001 Emerging Technologies Showcases

The program staff worked on the following project that was initiated in 2001:

- Southeast Learning Center – Natural Ventilation, High Efficiency HVAC, and Daylighting Controls.  Contractor commissioning work continued during the site month.

2000 Emerging Technologies Showcases

The program staff worked on the following projects that were initiated in 2000:

- National Resource Defense Council (NRDC) Santa Monica Headquarters Natural Ventilation, High Efficiency HVAC, Daylighting Control, Water Recovery System, Occupancy Sensors, and Photovoltaic System.  Program staff worked on the project fact sheet this month and end-use monitoring continued at the site.

- Pomona Unified School District – Portable Classroom.  The assessment of the classroom’s skylight reflector continued during the month and project staff started work on a project fact sheet.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

      - Calculated and Actual Payment Reconciliation -

Not Applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

A contract Technical Writer staff position was added to assist the engineering staff efforts for the Information Transfer portion of the Emerging Technologies Program.  This staff position will also assist with the information dissemination activities of the Codes & Standards Advocacy Program.  The initial role for this staff position will be to help the engineering staff to complete and reduce the backlog of reports and project fact sheets from prior program years.

The following are additions to the list of Subcontractors in the program workbook:

  - XXXXX for HVAC installation and contractor services;

  - XXXXX for consulting, analysis, end use monitoring, and software development services;

  - XXXXX for consulting, analysis, end use monitoring, and equipment procurement services;

  - XXXXX for market research and conference services;

  - XXXXX for procurement of electrical equipment;

  - XXXXX for HVAC contractor services;

  - XXXXX for consulting services;

  - XXXXX for web site hosting services;

  - XXXXX for lighting design and installation services;

  - XXXXX for equipment calibration and training services;

  - XXXXX for meetings and events;

  - XXXXX for the Leading Edge Competition;

  - XXXXX for software development tools and information;

  - XXXXX for procurement of measurement equipment;

  - XXXXX for meetings catering services;

  - XXXXX for procurement of lighting controls;

  - XXXXX for meetings, events, and forums;

  - XXXXX for procurement of HVAC equipment; and the

  - XXXXX for obtaining and disseminating energy efficient building practices information.

- Additional Items

None