| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Emerging Technologies Program - PGC |
| Program Number: | 1255-04 |
| Month: | August 2004 |

- Program Status

Program Description

The Statewide Emerging Technologies (ET) program is an information-only program that seeks to accelerate the introduction of innovative energy efficient technologies, applications, and analytical tools that are not widely adopted in California.  There are a daunting amount of market barriers a new energy efficient product must overcome to gain acceptance.  During initial marketing efforts, energy efficient products accepted by “innovators” may fail to gain wider acceptance with more risk adverse customers.  The intent of the ET program is to help accelerate a product’s market acceptance through a variety of approaches, but mainly by reducing the performance uncertainties associated with new products and applications.   The program targets all market segments.

1.1.1	Budgets and Expenditures

| Budget and Expenditures | Budget | Aug-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,679,000 | $21,188 | 1% | $307,473 | 8% | $207,700 | 6% | $515,173 | 14% | $3,371,527 |
| Admin | $981,000 | $19,688 | 2% | $175,552 | 18% |  |  | $175,552 | 18% | $805,448 |
| Marketing | $20,000 |  |  | $114 | 1% |  |  | $114 | 1% | $19,886 |
| DI | $2,599,000 | $1,500 | 0% | $131,808 | 5% | $207,700 | 8% | $339,508 | 13% | $2,467,192 |
| EM&V | $79,000 |  |  |  |  |  |  |  |  | $79,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

1.1.2	Energy Effects

This program does not have energy savings goals.

1.1.3	Performance Goals

| Performance Goals | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Emerging Technologies Applications Assessments initiated in PY2004 | 10 | 0 | 0% | 0 | 0% | 6 | 60% | 6 | 60% | 4 |
| ETCC ET Database PY2004 update | 1 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 |
| PY2004 ETCC meetings | 4 | 0 | 0 | 2 | 50% | 0 | 0% | 2 | 50% | 2 |

1.2	Activities/Accomplishments

1.2.1	Administrative -

- No Activity

1.2.2	Marketing -

None

1.2.3	Direct Implementation -

1.2.3.1	Audits, Site Surveys and Partnerships -

Emerging Technologies Coordinating Council

The Emerging Technologies Coordinating Council (ETCC) did not meet during the month of August.  The ETCC has met twice this year:  January 15 and April 23.

2004 Emerging Technology Application Assessments

The 2004 program has committed and initiated a total of six assessment projects this year.  During the month of August, no new assessment projects were committed.  The following assessment projects were committed and initiated earlier this year:

- Light Emitting Diode (LED) Outdoor Lights.  During the month, program staff worked on detailed planning for this assessment project.  This assessment follows the ongoing development CEC PIER work on LED luminaries for exterior, porch, and perimeter lighting.

- LED Task Lights.  This assessment project follows ongoing PIER development work and other RD&D sources on LED task lighting.  During the month, program staff worked on the development of detailed plans for the assessment.

- Residential Economizer Cycle Retrofits.  Program staff has selected a second test site to retrofit a residential economizer.  Staff procured the economizer dampers and other equipment needed for the first retrofit site.   In addition, staff instrumented the existing HVAC system to establish the baseline for the assessment at the first site.

- Advanced Heuristic Thermostatic Control System for Hotels. The end-use monitoring continues at the site. Thermostat installations at the site began this month.

- Occupancy Sensor Nightlight Wall Switches for Hotel Guest Room Bathrooms.  Program staff conducted a preliminary data analysis for the two hotel sites where testing has concluded.  For the two additional test sites, the occupancy sensor nightlight switches were installed in half of the scheduled rooms at one hotel site, and at the other hotel test site, a one suite type guest room was retrofitted.

- California Kitchen Down-Lights.  The Habitat for Humanity test site homes are in construction.  Staff worked with the data monitoring contractor to expand upon the planned end-use monitoring at the sites.

In addition, program staff continues to evaluate several potential technology application assessment projects for 2004 and 2005.  Several assessment projects initiated in prior program years continue as summarized in the following narratives.

2003 Statewide Emerging Technology Application Assessments

The program staff was engaged in the following ongoing projects initiated in 2003:

- Rapid Start “Super” T-8 Fluorescent Lamp/Ballast.  Program staff continues to work on the final report and a project fact sheet.

- Instant Start “Super” T-8 Lamp/Ballast.  Program staff continues to work on the final report and has begun work on a project fact sheet.

- Stairwell Lighting Bi-Level Switching.  Equipment, lighting fixtures, and occupancy sensors were delivered to the retrofit sites in preparation for installation next month. Staff purchased special monitoring equipment to help establish the usage pattern for the stairwells that will be retrofitted.

- Network Management of Computer Power Option Settings.  Staff performed a preliminary analysis of the small pilot end use data monitoring.  In addition, internal business case development continued for IT Department approval and support for a companywide, large scale pilot.

- Electrochromic Glazing.  Program staff continues to search for potential sites within SCE’s facilities where to perform this assessment project. Due to size limitations of current electrochromic glazing, few locations are suitable for retrofitting the product since the glass cannot be trimmed in the field to fit existing window panes.

- Displacement Ventilation. Program staff finalized a contract with an engineering firm for the system design and working drawings.

- Advanced Classroom Lighting System.  The PIER advanced lighting system will be replaced with a new PIER fixture in the daylighting classroom.  The construction and monitoring plans are under development.

- Anti Corrosion Coatings for Condenser Coils.  Program staff completed the baseline end-use data collection on an existing rooftop package unit at an SCE facility.  The instrumentation was removed and the unit prepared for condenser coil cleaning and the application of an anti-corrosion coating.

- Voltage Reducer System for Dimming Control.  Staff performed a preliminary review of the test performance data.

2003 Local Demonstration and Information Transfer ET Application Assessments

The program staff was engaged in the following ongoing projects initiated in 2003:

- Professional Wet Cleaning.  Field testing and end use monitoring was completed and a draft report is being prepared.

- Cold Storage Refrigeration Control.  The new control system was installed at the site.  Control system testing continues from last month.

- Salt Reduction of Waste Water Precipitation of Salts for Fluid Bed/Lime Process.  The draft final report has undergone an internal review and comments are being incorporated.

- Petroleum Dry Cleaning.  Program staff and the project consultant continued wit the site selection process and negotiations with a potential customer for field test end use monitoring at an existing petroleum-based dry cleaning facility.

- Silicone Dry Cleaning.  Program staff and the project consultant continued to seek and negotiate with customers for potential field test sites for end use monitoring of existing silicone-based dry cleaning systems.

- Carbon Dioxide Dry Cleaning.  Program staff and the project consultant continued to seek and negotiate with customers for potential field test sites for end use monitoring of existing carbon dioxide-based dry cleaning systems.

- Advanced Control for Plastic Granulators.  During the month, program staff obtained manufacturer’s performance data on several granulators.  Staff is preparing to conduct initial tests at SCE’s CTAC facilities.

2002 Statewide Emerging Technologies Assessments

The program staff worked on the following projects that were initiated in 2002:

- Integrated Design for New Children’s Museum, and Underfloor Air Distribution.  The customer lost their rights to the originally planned building site.  The customer continues to search for a new site for the museum.

- T-5 High Output Lighting System for High Bay Workshop and Variable Geometry Reflector System for HID Lighting.  Program staff continues to work on the final report and a project fact sheet.

- Integrated Efficiency Improvements for Small Grocery Stores.  Staff completed the analysis of the end use monitoring data and initiated work on the final report and project fact sheet.

- Integration of Energy Efficiency Improvements in a Small Sit-Down Restaurant.  This field assessment was formerly the “Multiplex Refrigeration in Small Sit-Down Restaurant” project.  Due to roof structural concerns at the site and lack of other adequate equipment space, program staff recommended a new package of measures in lieu of the multiplex refrigeration system.  Specifically, the project will evaluate the combined use of over-sized condenser coils with PSC motors, ECM evaporator fan motors, electronic expansion valve, environmentally friendly refrigerants (R-404a and R-134a), and liquid-to-suction heat exchangers at the site. In addition, PVC wrapped and sealed insulation, used primarily in industrial refrigeration applications, will be used in this project.

- Integrated Hood Exhaust Backwall Make-Up Air System for Hood Exhaust.

Program staff continued to work with a restaurant chain to search for a site for this assessment.

- Perforated Supply Plenum Make-Up Air System for Hood Exhaust.  End-use monitoring and data collection continues at the site.  Program staff performed preliminary data review and analysis for quality assurance.

- Variable Frequency Drive for Commercial Kitchen Hood Exhaust and Make-Up Air System.  End-use data monitoring continued at the site and program staff continued to review and analyze the data for quality assurance.

2002 Local Demonstration & Information Transfer ET Application Assessments

The program staff working on the following projects that were initiated in 2002:

- Integrated Design for Non-Residential Retrofit Buildings. Contractors are proceeding with the verification and pre-functional testing of the Phase II construction work.

- Low-E Pigment for Stucco and Paints for Residential and/or Small Commercial Buildings.  Program staff completed its initial internal review of the draft final technical report during the month and incorporated recommended changes.  The report was submitted for further internal review and comment.

- Spray-on Radiant Barrier for Existing Residential and/or Small Commercial Buildings.  Program staff completed its initial internal review of the draft final technical report during the month and incorporated recommended changes.  The report was submitted for further internal review and comment.

2001 Emerging Technologies Showcases

The program staff worked on the following project that was initiated in 2001:

- Southeast Learning Center – Natural Ventilation, High Efficiency HVAC, and Daylighting Controls.  The facility remains under construction.  As part of the project, a “School Classroom Lighting Design Guide” was developed, targeting Southern California school districts, and was presented and distributed at a seminar at SCE’s Customer Technology Application Center (CTAC).

2000 Emerging Technologies Showcases

The program staff worked on the following projects that were initiated in 2000:

- National Resource Defense Council (NRDC) Santa Monica Headquarters Natural Ventilation, High Efficiency HVAC, Daylighting Control, Water Recovery System, Occupancy Sensors, and Photovoltaic System.  The draft report and commissioning data are under review.  Staff is working to resolve differences between the original pre-build analysis and the as-built data and occupancy patterns. End use data monitoring continues.

- Pomona Unified School District – Portable Classroom.  Contractors completed both the electrical and mechanical systems work for the portable classroom this month.  In Addition, contractors began the skylight installation work on the portable classroom.

1.2.3.2	Direct Installations, Rebates, Equipment Maintenance and Optimization –

Not Applicable

1.2.3.3	Calculated and Actual Payment Reconciliation -

Not Applicable

1.2.4	EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

None