| Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Savings By Design – PGC |
| Program Number: | 1261-04 |
| Month: | June 2004 |

- Program Status

Program Description

Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incentives as well as design team incentives.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jun-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $18,310,596 | $112,566 | 1% | $765,996 | 4% | $4,207,181 | 23% | $4,973,178 | 27% | $17,544,599 |
| Admin | $1,748,200 | $27,099 | 2% | $360,871 | 21% |  |  | $360,871 | 21% | $1,387,329 |
| Marketing | $1,285,000 | $1,809 | 0% | $2,658 | 0% |  |  | $2,658 | 0% | $1,282,342 |
| DI | $14,766,800 | $83,658 | 1% | $402,467 | 3% | $4,207,181 | 28% | $4,609,648 | 31% | $14,364,333 |
| EM&V | $510,596 |  |  |  |  |  |  |  |  | $510,596 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 17,557 |  |  | 3 | 0% | 4,846 | 28% | 4,849 | 28% | 17,554 |
| Annual kWh | 88,042,706 |  |  | 15,224 | 0% | 27,559,368 | 31% | 27,574,592 | 31% | 88,027,482 |
| Lifecyc kWh | 1,452,700,830 |  |  | 243,586 | 0% | 446,112,996 | 31% | 446,356,582 | 31% | 1,452,457,244 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Jun-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Industry Specific Case Studies |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  |
| 2005 Title 24 Seminars | 2 - 6 | 2 | 33% - 100% | 2 | 33% - 100% | 0 | 0% | 2 | 33% - 100% | 0 – 4 |
| eQUEST Training | 2 - 4 | 1 | 25% - 50% | 3 | 75% - 100% | 0 | 0% | 3 | 75% - 100% | 0 – 1 |
| Demystifying the Whole Building Approach to Energy Effic. Design | 2 - 4 | 0 | 0% | 3 | 75% - 150% | 0 | 0% | 3 | 75% - 150% | 0 - 1 |
| Cool Roofs (SBD Presentation) | 2 - 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 - 4 |

  - Activities/Accomplishments

    - Administrative -

- Tracked the addition of 16 newly committed construction projects where the customer received agreements with energy measure and incentive commitments.  These projects represent a potential of over 3.7 million kWh of energy savings when completed.

- Twenty-six new “pipeline” or potential customer projects were added to the tracking system.  These 26 projects are in the early development stages and add a potential of 5.1 million kWh of energy savings if development of these projects complete.

    - Marketing –

            - Association of Energy Services Providers International Strategies newsletter.  Article titled “Three Calif. Buildings Earn Energy Efficiency Integration Awards”.

1.2.3	Direct Implementation –

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures Recommended | kWh Committed | kWh Installed in June |
| --- | --- | --- |
| Whole Building Approach |  |  |
| Whole Building - Owner Incentive | 10,084,589 | -- |
| Whole Building - DTI | 1 |  |
| System Approach |  |  |
| HVAC: Energy Reduction | 14,200,235 | -- |
| Daylighting Controls | 553,728 | -- |
| LPD Reductions | 3,646,255 | -- |
| Supermarket Systems | -- | -- |
| Process Systems | 4,470,027 | -- |

      - Calculated and Actual Payment Reconciliation –

None

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

- Quarterly Statewide Savings By Design Program Staff Meeting.  Agenda included:  Program policies and procedures; activities in support of 2005 Title 24 Code; NPLV ratings; Energy Design Resources; and general updates.

- Savings By Design held statewide conference call with its partners to discuss program issues.

- Discussed and communicated activity related to supporting 2005 Title 24 Code changes with California Energy Commission.

- Changes to Subcontractors or Staffing

            - The Savings By Design (SBD) Field Delivery team added 3 technical specialists to enhance program delivery and effectiveness.  At this time, one representative’s time is allocated to the PGC budget.  Two representatives’ time will be allocated to the Procurement budget.

            - An additional technical specialist is anticipated to join the team in July.  This employee’s time will charged against PGC dollars.

- Additional Items

- Statewide Savings By Design Activities:

  - Savings By Design website had over 465,000 “hits” since January 2004;

  - Energy Design Resources website received over 10 million hits since January 2004;

- SCE SBD

  - Participated in and sponsored UC/CSU conference on “Building Confidence: From Sustainable Policy to Practice”, held at the UC Santa Barbara campus, from June 20 through June 23.  Sponsorship assisted in paying for design students to attend the conference.