| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Savings By Design – PGC |
| Program Number: | 1261-04 |
| Month: | January 2005 |

- Program Status

Program Description

Savings By Design (SBD) is an energy efficiency program for the nonresidential new construction industry started by the investor-owned utilities (IOUs) in 1999 to provide statewide consistency, program stability, and savings persistence to the new construction market.  SBD builds on the best elements of successful new construction programs run by the investor owned utilities since the early 1990’s.  The program promotes integrated design and emphasizes early design involvement by offering building owners and their design teams a wide range of services including education, design assistance, and owner incentives as well as design team incentives.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $18,310,596 | -$129,101 | -1% | $2,193,083 | 12% | $15,529,333 | 85% | $17,722,416 | 97% | $16,117,513 |
| Admin | $1,739,600 | -$27,135 | -2% | $717,782 | 41% |  |  | $717,782 | 41% | $1,021,818 |
| Marketing | $205,200 |  |  | $21,057 | 10% |  |  | $21,057 | 10% | $184,143 |
| DI | $15,855,200 | -$101,966 | -1% | $1,454,244 | 9% | $15,529,333 | 98% | $16,983,577 | 107% | $14,400,955 |
| EM&V | $510,596 |  |  |  |  |  |  |  |  | $510,596 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

| Energy Effects | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 17,557 | 374 | 2% | 1,224 | 7% | 16,145 | 92% | 17,369 | 99% | 16,334 |
| Annual kWh | 88,042,706 | 5,186,505 | 6% | 11,252,470 | 13% | 110,476,885 | 125% | 121,729,356 | 138% | 76,790,235 |
| Lifecyc kWh | 1,452,700,830 | 103,350,560 | 7% | 215,060,977 | 15% | 2,002,362,223 | 138% | 2,217,423,200 | 153% | 1,237,639,853 |
| Annual Therms |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc Therms |  |  | NA |  | NA |  | NA |  | NA |  |

    - Performance Goals

| Performance Goals | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Industry Specific Case Studies | 5 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |
| 2004 Title 24 Seminars | 2 | 0 | 0% | 2 | 100% | 0 | 0% | 2 | 100% | 0 |
| eQUEST Training | 2 | 1 | 50% | 6 | 300% | 0 | 0% | 6 | 300% | 0 |
| Demystifying the Whole Building Approach to Energy Effic. Design | 2 | 0 | 0% | 4 | 200% | 0 | 0% | 4 | 200% | 0 |
| Cool Roofs (SBD Presentation) | 2 | 0 | 0% | 1 | 50% | 0 | 0% | 1 | 50% | 1 |
| 2005 Title 24 Seminars | 2 | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 0% | 2 |
| Other Seminars (PY 2005) | 4 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4 |
| Integrated School Building Design | 3 | 0 | 0% | 2 | 67% | 0 | 0% | 2 | 67% | 1 |
| Design Strategies for High Performance Glass | 1 | 0 | 0% | 1 | 100% | 0 | 0% | 1 | 100% | 0 |

  - Activities/Accomplishments

    - Administrative -

None

    - Marketing –

1.2.3	Direct Implementation –

      - Audits, Site Surveys and Partnerships -

Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

| Types of Measures | kWh Committed in January | kWh Installed in January |
| --- | --- | --- |
| Whole Building Approach |  |  |
| Whole Building - Owner Incentive | 50,986 | 78,870 |
| Whole Building - DTI | -- | -- |
| System Approach |  |  |
| HVAC: Energy Reduction | 72,200 | 3,360 |
| Daylighting Controls | -- | -- |
| LPD Reductions | 298,394 | 32,646 |
| Supermarket Systems | -- | -- |
| Process Systems | -- | 5,417,348 |

      - Calculated and Actual Payment Reconciliation –

Reconciliation of January’s budget activity will be reported with the February monthly report. Budget reporting system has been enhanced.  Training on the system is pending.

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

Statewide:  2005 Savings By Design rollout

- Changes to Subcontractors or Staffing

No changes to subcontractors or staffing during this month.

- Additional Items

- SCE Savings By Design activities:

  - Held Savings By Design Program staff meeting

- SCE customer project activity:

  - Savings By Design prepared an energy analysis for the Temecula Unified School District.  Over 13 energy efficiency design alternatives were identified and presented as a recommendation report to the District.  Energy-efficient measures included cool roofs, increased wall and roof insulation, improved fenestration, high efficiency lighting systems with occupancy and daylighting controls.  As calculated, if these implemented, the facility would use 33% less energy than a minimally compliant Title 24 project design.  This would translate into estimated energy savings of 690,000 kWh per year.

  - SCE’s analysis for a Department of Correction’s expansion of a prison facility could reduce energy use estimates by calculated reductions of 1.468 million kWh per year and demand by 276 kW if all measures were implemented.

  - A municipal water district is planning a four phase expansion of their regional water reclamation facility.  Through SCE’s efforts, recommendations were made that include high efficiency motor applications for their secondary effluent and filter influent pumps and variable speed drive controls on their tertiary water treatment and plan effluent pumps.  The total recommendation package is calculated to reduce energy and power requirements by an estimated 89 kW and over 5 million kWh.