| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | December 2005 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $645,161 | 7% | $9,695,827 | 99% |  |  | $9,695,827 | 99% | $109,917 |
| Admin | $1,905,210 | $95,996 | 5% | $1,594,425 | 84% |  |  | $1,594,425 | 84% | $310,785 |
| Marketing | $3,055,234 | $147,144 | 5% | $3,173,038 | 104% |  |  | $3,173,038 | 104% | -$117,804 |
| DI | $4,648,300 | $402,020 | 9% | $4,928,363 | 106% |  |  | $4,928,363 | 106% | -$280,063 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Dec-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 61,000 | 5,419 | 8.8% | 96,743 | 158% | 0 | 0% | 96,743 | 158% | 0 |
| CTAC/AGTAC event seminars | 352 | 9 | 2.5% | 383 | 108% | 0 | 0% | 383 | 108% | 0 |
| Outreach events | 170 | 2 | 1.2% | 206 | 121% | 0 | 0% | 206 | 121% | 0 |

  - Activities/Accomplishments

    - Administrative

    - - Information Services

- In December continued program administration tasks, including program coordination with the SW Education & Training Program, management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| - CTAC 1st Quarter Calendar 2006 | Calendar | US MailUS Mail Handout | 36,000 |
| Irwindale Chamber of Commerce | Newsletter | n/a | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenter.com | Website | Internet | n/a |
| AGTAC Quarterly Calendar of Events | Quarterly Calendar of Events | US Mail Handout | 8300 |
|  | Quarterly Calendar of Events | US Mail |  |

Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during December of 2005 include:

Energy Centers:

Following are accomplishments from December 1st – December 31st 2005.

EE Events completed December =  9

Attendance at those events December  = 286

EE Events completed YTD = 180

Attendance at those events YTD = 4541

EE HTR Events completed December  = 3

Attendance at those events December  = 41

EE HTR Events completed YTD = 77

Attendance at those events YTD = 1182

Joint Utility events completed December  = 3

Joint Utility events YTD = 75

EE consultations December =12

Attendees in those consultations December = 13

EE consultations YTD = 445

Attendees in those consultations YTD = 1278

EE equipment demonstrations December = 67

Attendees at those demonstrations December= 61

EE equipment demonstrations YTD =909

Attendees at those demonstrations YTD = 914

EE consultations YTD =

New displays developed include:

- AGTAC

COMPRESSED AIR DISPLAY--At AGTAC, a Compressed Air Display was recently completed in the new ICF Building. This display will demonstrate advance technologies for energy efficiency in the compressed air market. The display features two - fifty horse power compressors, a thermal mass air drying system, efficient distribution piping, a power meter and an air flow meter. The efficiency of three control methods can be compared; Modulation, Load-Unload, and Variable Speed technology. The display will be incorporated into a number of educational seminars and be a key item on our guided tours.

- CTAC

At CTAC new ceiling lighting systems were installed in the lighting center featuring .featuring suspended direct/indirect fixtures with T-5 lamps, recessed direct/indirect, recesses direct fixtures with parabolic diffusers, and recessed compact fluorescent down lights. Commercial wall lighting displays highlight the latest in technology for Linear fluorescent and ballast systems, compact fluorescent systems, and High Intensity Discharge (H.I.D) lamp and ballast systems."

RTTC:

The summary description of activities which took place at the RTTC in December of 2005 is as follows:

EE Information Dissemination

Tours

- Provided a tour of the RTTC for XXXXX and Gas Company staff

- Provided a tour a tour of the RTTC for XXXXX

Publications

- None

- Customer Care

None

EE Program Support

- Training Seminars

  - None

- Review of 2006 Express Efficiency Program for Foodservice.  RTTC examined the methodology proposed for offering foodservice-related customer incentives under the Express Efficiency program in 2006.  The investigation specifically focused on measures proposed by XXXXX /PG&E for commercial ice machines and commercial refrigerators and freezers.

Investigate energy efficiency opportunities for refrigeration system.  In response to a request from Business Solutions group, RTTC assisted XXXXX store (located in Irvine) in their energy management efforts.  Specifically, RTTC investigated and identified energy efficiency opportunities for the existing refrigeration system of XXXXX store.  The objective of this effort was to provide the customer with general and specific energy efficiency recommendations.

Information Services Program:

There were 5,419 EE contacts reported in the month of December of 2005, bringing the cumulative two year total of energy efficiency (EE), contacts to 96,743 – 159%.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Due to the fact that Tab 7 of the workbook is full, below is a list of additional subcontractors that work on the program along with their associated monthly expenditures.