| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | December 2004 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $647,996 | 7% | $4,823,287 | 49% |  |  | $4,823,287 | 49% | $4,982,457 |
| Admin | $1,905,210 | $73,034 | 4% | $777,856 | 41% |  |  | $777,856 | 41% | $1,127,354 |
| Marketing | $3,055,234 | $130,580 | 4% | $1,622,434 | 53% |  |  | $1,622,434 | 53% | $1,432,800 |
| DI | $4,648,300 | $444,383 | 10% | $2,422,997 | 52% |  |  | $2,422,997 | 52% | $2,225,303 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 30,500 | 525 | 1.7% | 46,593 | 152% | 0 | 0% | 46,593 | 152% | 0 |
| CTAC/AGTAC event seminars | 176 | 7 | 4% | 203 | 115% | 0 | 0% | 203 | 115% | 0 |
| Outreach events | 85 | 1 | 1.2% | 93 | 109% | 0 | 0% | 93 | 109% | 0 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element – In December, continued program administration tasks, including management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| Premium Efficiency Motors & Adjustable Speed Drives | Flyer | US Mail | 948 |
| LEED (Leadership in Energy & Environmental Design) Advanced Training Workshop | Flyer | E-Mail | 2764 |
| 1st Quarter Calendar of Events | Calendar | US Mail Hand Deliver | 32,559 7,500 |
| www.sce.com/ctac | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Workshops – January classes | Email invite | Email | 358 |
| 1st Quarter Calendar of Events | Calendar | U.S. Mail | 8,193 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during December of 2004 include:

Energy Centers:

Following are accomplishments from December 1st – December 31st 2004.

*numbers reflect an adjustment to previously reported events

*EE Events completed December = 7

*Attendance at those events December = 164

*EE Events completed YTD = 203

*Attendance at those events YTD = 4766

*EE HTR Events completed December = 3

*Attendance at those events December = 43

*EE HTR Events completed YTD = 85

*Attendance at those events YTD = 1284

*Joint Utility events completed December = 4

*Joint Utility events YTD = 82

EE consultations December = 19

Attendees in those consultations December = 20

EE consultations YTD = 627

Attendees in those consultations YTD = 1392

EE equipment demonstrations December = 47

Attendees at those demonstrations December = 24

EE equipment demonstrations YTD = 1844

Attendees at those demonstrations YTD = 1241

New displays developed include:

- AGTAC

Business Center Lighting Energy Efficiency Project – Utilizes state-of-the-art energy management DALI protocol giving a wide variety of control options.

- CTAC

No new displays at CTAC in December.

RTTC:

The summary description of activities which took place at the RTTC in November and December of 2004 are as follows:

	 EE Information Dissemination

  - Taught a class on Energy Efficiency Strategies in Supermarkets at a joint utilities event sponsored by SDG&E

  - Provided an energy efficiency training in food refrigeration at Southern California Food Technical Advisory Committee (SCFTAC), held in Anaheim

  - Taught a class on energy efficiency opportunities in supermarkets at CTAC

	EE Program Support

  - Worked closely with SCE and PG&E’s program administrators to revise terms and conditions for 2005 Refrigeration Express Efficiency program.  In addition to T&C modifications, RTTC included new measures in the program

- Publications

  - Spoke at E-Source conference on the role of applied research conducted by SCE’s RTTC in the success of EE programs

- Customer EE Support

Lakeshore Towers

  - Performed a DOE2 simulation to estimate savings related to a chiller 	retrofit.  The customer is proposing to replace a reciprocating compressor 	with a high efficiency centrifugal compressor.  The simulation estimated 	90,000 kWh of expected energy savings and will allow the customer to 	apply for SPC rebates.

D. Gardikas Produce Company

  - Visited this customer’s warehouse in Santa Fe Springs and examined their 	existing refrigeration equipment which serves a large walk-in box.  	Provided several recommendations to increase the operational efficiency 	of their system.  Reviewed a proposed upgrade to the refrigeration system 	and quantified the expected energy savings to be used for an SPC rebate 	application

Information Services Program:

There were 525 EE contacts conducted in the month of December 2004, bringing the YTD total of EE contacts to 46,593.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Statewide Education, Training and Services 2003 Program Study - This statewide study has been initiated involving utility-owned energy centers throughout the State of California with two objectives:  (1) To evaluate 2003 program success by measuring indicators of program effectiveness and testing the assumptions underlying the program theory; (2) To provide ongoing feedback and corrective guidance regarding program design and implementation while identifying best practices.  The study is expected to be completed by year end.