| Program Implementer Name: | Southern California Edison |
| --- | --- |
| Program Title: | Statewide Education and Training – PGC |
| Program Number: | 1264-04 |
| Month: | October 2004 |

- Program Status

Program Description

The Statewide Energy Efficiency Education and Training Program is offered in the service territories of Pacific Gas & Electric (PG&E), Southern California Edison (SCE), San Diego Gas and Electric (SDG&E), and Southern California Gas Company (SoCalGas).  Overall, the program promotes energy efficiency to a variety of customer segments through energy centers (physical and virtual) and other informational programs.  The objective is to:  (1) disseminate information about energy efficient technology and practices to utility customers for the purpose of assisting them to reduce energy usage, lower their bills, reduce operation and maintenance costs, and improve their productivity; and, (2) to provide services to a variety of market actors, architects, engineers, distributors, and contractors who use information and tools to design more efficient buildings or processes and to conduct energy efficiency retrofits and renovations.

    - Budgets and Expenditures

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $9,805,744 | $400,869 | 4% | $3,709,116 | 38% |  |  | $3,709,116 | 38% | $6,096,628 |
| Admin | $1,905,210 | $48,348 | 3% | $641,207 | 34% |  |  | $641,207 | 34% | $1,264,003 |
| Marketing | $3,055,234 | $157,113 | 5% | $1,343,339 | 44% |  |  | $1,343,339 | 44% | $1,711,895 |
| DI | $4,648,300 | $195,407 | 4% | $1,724,570 | 37% |  |  | $1,724,570 | 37% | $2,923,730 |
| EM&V | $197,000 |  |  |  |  |  |  |  |  | $197,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

    - Energy Effects

This program does not have energy savings.

    - Performance Goals

| Performance Goals | Goals | Oct-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Energy Efficiency customer contacts | 30,500 | 1,935 | 9.4% | 44,072 | 138.2% | 0 | 0% | 44,072 | 138.2% | 0 |
| CTAC/AGTAC event seminars | 176 | 19 | 10.8% | 169 | 96% | 0 | 0% | 169 | 96% | 7 |
| Outreach events | 85 | 8 | 9.4% | 87 | 102% | 0 | 0% | 87 | 102% | 0 |

  - Activities/Accomplishments

    - Administrative

- Information Services Program Element – In October, continued program administration tasks, including management of activity and budget status reporting.

    - Marketing

| Event (CTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| Multifamily Energy Efficiency Design | Email invite | Email | 2764 |
| Rebuild America – Lighting For Tomorrow Available Today | Flyer | Email | 3025 |
| www.sce.com/ctac_work_classes | Website | Internet | n/a |

| Event (AgTAC) | Marketing Piece | Delivery Method | # Distributed |
| --- | --- | --- | --- |
| www.sce.com/agtac_work_classes | Website | Internet | n/a |
| www.energyefficiencycenters.com | Website | Internet | n/a |
| Workshops –November Classes | Email invite | Email | 400 |
| Electric Forklift Workshop | Flyer | Hand Deliver | 50 |
| Advanced VSD Workshop | Flyer | U.S. Mail Hand Deliver | 100 |

    - Direct Implementation

      - Audits, Site Surveys and Partnerships

In addition to the Performance Goals, other Education and Training activities during October of 2004 include:

Energy Centers:

Following are accomplishments from October 1st – October 31st 2004.

EE Events completed October = 19

Attendance at those events October = 347

EE Events completed YTD = 169

Attendance at those events YTD = 4093

EE HTR Events completed October = 8

Attendance at those events October = 61

EE HTR Events completed YTD = 70

Attendance at those events YTD = 1072

Joint Utility events completed October = 8

Joint Utility events YTD = 69

EE consultations October = 42

Attendees in those consultations October = 118

EE consultations YTD = 582

Attendees in those consultations YTD = 1348

EE equipment demonstrations October = 354

Attendees at those demonstrations October = 129

EE equipment demonstrations YTD = 1702

Attendees at those demonstrations YTD = 1131

New displays developed include:

- AGTAC

No new displays at AGTAC in October.

- CTAC

No new displays at CTAC in October.

RTTC:

The following provides a summary description of activities which took place at the RTTC in October 2004:

EE Information Dissemination

- Performed RTTC tour for CTAC’s Commercial Refrigeration Training Class

- Performed RTTC tour for Jerry Berger, from JSB Engineering

- Taught a class on Advanced Food Service Refrigeration Workshop at CTAC

EE Program Support

- Worked closely with SCE and PG&E’s program administrators to revise terms and conditions for 2005 refrigeration Express Efficiency program.  In addition to T&C modifications, RTTC included new measures in the program

Publications

- 2004 Energy Efficiency Emerging Technologies Summit

  - Made two presentations, one involving an overview two new PIER projects to be conducted at the RTTC, and the other on the RTTC’s EE projects in commercial refrigeration.

Customer EE Support

  - Projects in progress.

Information Services Program:

There were 1,935 EE contacts conducted in the month of October 2004; bringing the YTD total EE contacts to 44,072.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable

      - Calculated and Actual Payment Reconciliation

Not applicable

    - EM&V

None

- Program Challenges

None

- Customer Disputes

None

- Compliance Items

None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

None

- Additional Items

Statewide Education, Training and Services 2003 Program Study - This statewide study has been initiated involving utility-owned energy centers throughout the State of California with two objectives:  (1) To evaluate 2003 program success by measuring indicators of program effectiveness and testing the assumptions underlying the program theory; (2) To provide ongoing feedback and corrective guidance regarding program design and implementation while identifying best practices.  The study is expected to be completed by year end.